## Sheet1
CUBAN TECHNICAL ADVISORY PROGRAMME: IMPACT ASSESSMENT REPORT
NAME OF THE PROVINCE: LIMPOPO
PROJECT DESCRIPTION | PROJECT VALUE | PROJECT DURATION |  | PROGRESS STATUS OF PROJECT (IN %) | NAME OF CTA & % OF INVOLVEMENT IN PROJECT | EXPLANATION OF IMPACT |  | EFFECT OF NON-REGISTERED CTA
|  | START DATE | END DATE |  |  | BEFORE CTA | AFTER CTA
LDPW-B/08012 Fetakgomo Testing | 2750000 |  |  | Cancelled | Varon Tamayo, WH | Cancelled | Cancelled
LDPW-B/08057 Bela Bela Hospital | R 7 365 500. 80 | 2009-02-01 | 2009-12-01 | 100% Completed and Project is Handed to Client | Varon Tamayo, WH - 25%, with Pedro Hernandes, Peter Hertz | Project Manager was checking the project schedule | Improved technical verification with alternative methods to fast track completion of the works. | No effect as the design phase of the project was done by consultants
LDPW-B/070454 Mokopane Traffic Station | 11212080.25 | 2009-03-01 | 2009-11-01 | 100% Completed and Project is Handed to Client | Varon Tamayo, WH - 40%, with Phaswna Pfuluwani | Project Manager was checking the project schedule | Improved technical verification with alternative methods to fast track completion of the works. | No effect as the design phase of the project was done by consultants
LDPW-B/070438 Elandsdoorn/Marapong | 7625786 | 2009-01-01 | 2009-12-01 | 100% Completed and Project is Handed to Client | Varon Tamayo, WH - 50% with Abram Shoteli | Project Manager was checking the project schedule | Improved technical verification with alternative methods to fast track completion of the works. | No effect as the design phase of the project was done by consultants
LDPW-B/070427 Masisi Clinic | 6548500 | 2009-02-01 | 2010-01-01 | 100% Completed and Project is Handed to Client | Varon Tamayo, WH - 50% with Prince Swuhana | Project Manager was checking the project schedule | Improved technical verification with alternative methods to fast track completion of the works. | No effect as the design phase of the project was done by consultants
LDPW-B/070426 Vleinfontein Clinic | 7091000 | 2009-02-01 | 2010-01-01 | 100% Completed and Project is Handed to Client | Varon Tamayo, WH - 50% with NT Rikhotso | Project Manager was checking the project schedule | Improved technical verification with alternative methods to fast track completion of the works. | No effect as the design phase of the project was done by consultants
LDPW-B/070429 Zadu Clinic | 5768944.14 | 2008-09-01 | 2009-11-01 | 100% Completed and Project is Handed to Client | Varon Tamayo, WH - 30%, with Peter Hertz | Project Manager was checking the project schedule | Improved technical verification with alternative methods to fast track completion of the works. | No effect as the design phase of the project was done by consultants
New Offices at Works Towers | Unknown | 2009-03-01 | 2009-10-01 | Audit | Varon Tamayo, WH - 30% with Peter Hertz and Benny Mkhawana | Appoint consultants to audit the report for project completion | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the design phase of the project was done by consultants
Parliamentary MEC's Staff Houses | Unknown | 2010-03-01 |  | Audit/ March 2010 | Varon Tamayo, WH - 50% with one Trainee and other CTA's | Appoint consultants to audit the report for project completion | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
Nebo Government Complex Lifts | 5140000 | 2010-11-29 | 2011-07-29 | Contractor Appointed and Site Handed Over | Varon Tamayo, WH - 50% with Prince Swuhana | No verification of the design in detail for compliance with SABS and good practice. | Improved technical verification with alternative methods to construct affordably with low maintanance cost. | No effect as the design phase of the project was done by consultants
New Tribal Offices at Rapotokwane | 5200000 | 2010-04-01 |  | Design/ April 2010 | Varon Tamayo, WH - 50% with Chris Masha and other CTA's | Delays in the designing stage and Non-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | It has an effect as it requires that a registered person must sign of all the designs done by CTA's
New Tribal Offices at Mulima | 5200000 | 2010-06-01 |  | Design/ June 2010 | Varon Tamayo, WH - 50% with Chris Masha and other CTA's | Delays in the designing stage and Non-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | It has an effect as it requires that a registered person must sign of all the designs done by CTA's
June Furse Memorial Hospital | Unknown | 2010-03-01 |  | Audit/ March 2010 | Varon Tamayo, WH - 50% with one Trainee and other CTA's | Appoint consultants to audit the report for project completion | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
Giyani Government Complex Refurbishment | R 7 365 500. 80 (estimate) | 2010-11-29 | 2011-05-29 | Contractor Appointed and Site Handed Over | Varon Tamayo, WH - 50% with Benny Mkhawana | No verification of the design in detail for compliance with SABS and good practice. | Improved technical verification with alternative methods to construct affordably with low maintanance cost. | No effect as the design phase of the project was done by consultants
Lebowakgomo Government Complex Refurbishment | R 13 078 000 (Estimate) | 2010-02-01 | 2011-05-01 | In progress | Varon Tamayo, WH - 50% with Benny Mkhawana | No verification of the design in detail for compliance with SABS and good practice. | Improved technical verification with alternative methods to construct affordably with low maintanance cost. | No effect as the design phase of the project was done by consultants
Thoyandou Government Complex Refurbishment | R 7 365 500. 80 (estimate) | 2010-11-29 | 2011-05-29 | Contractor Appointed and Site Handed Over | Varon Tamayo, WH - 50% with Prince Swuhana | No verification of the design in detail for compliance with SABS and good practice. | Improved technical verification with alternative methods to construct affordably with low maintanance cost. | No effect as the design phase of the project was done by consultants
Department of Safety, Security & Liaison building | Unknown | 2010-06-01 |  | Audit/ June 2010 | Varon Tamayo, WH | Appoint consultants to audit the report for project completion | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
250 KILO LITRE STEEL TANK AT GIYANI GOVERNMEMT COMPLEX | R 1 200 000 | 2010-08-01 | 2010-11-01 | 100% Completed and Project is Handed to Client | Joaquin E Fuentes G - 60% with Trainee and RA Kekana | Appoint consultants to audit the report and conduct the designs for project completion | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | It has an effect as it requires that a registered person must sign of all the designs done by CTA's
EVALUATION OF DAMAGES IN ROOF AND WALLS AT SAFETY SECURITY AND LIASON BUILDING | UNKNOWN |  | JUNE, 2010 | AUDIT | Joaquin Fuentes - 50% with Chris Masha and other CTA's | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
RENOVATION OF THE BUILDINGS AT LEBOWAKGOMO GOVERNMENT COMPLEX | R 18 838 125 | FEBRUARY, 2010 | MAY, 2011 | PLANING PHASE | Joaquin Fuentes - 50% with RA Kekana and other CTA's | No verification of the design in detail for compliance with SABS and good practice. | Improved technical verification with alternative methods to construct affordably with low maintanance cost. | No effect as the design phase of the project was done by consultants
REFURBISHMENT OF GIYANI GOVERNMENT COMPLEX | R 14 580 752 | FEBRUARY, 2010 | MAY, 2011 | PLANING PHASE | Joaquin Fuentes - 50% with RA Kekana and other CTA's | No verification of the design in detail for compliance with SABS and good practice. | Improved technical verification with alternative methods to construct affordably with low maintanance cost. | No effect as the design phase of the project was done by consultants
REFURBISHMENT OF THOOYANDOU GOVERNMENT COMPLEX | R 11 748 722 | FEBRUARY, 2010 | MAY, 2011 | PLANING PHASE | Joaquin Fuentes - 50% with RA Kekana and other CTA's | No verification of the design in detail for compliance with SABS and good practice. | Improved technical verification with alternative methods to construct affordably with low maintanance cost. | No effect as the design phase of the project was done by consultants
AUDIT AT ZEBEDIELA TRIBAL AUTOTRITY OFFICES | UNKNOWN | FEBRUARY, 2010 |  | AUDIT | Fuentes J. - 35% and Benny Mkhawane and Ferreiro J. | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
LETABA HOSPITAL | UNKNOWN | 2010-04-01 |  | AUDIT | Joaquim Fuentes - 50% and Ferreiro Jorge | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
MANOTWANE CLINIC | UNKNOWN | 2009-07-01 |  | AUDIT | Joaquim Fuentes - 35% with Ferreiro and Kekana RA | No verification of the design in detail for compliance with SABS and good practice. | Improved technical verification with alternative methods to construct affordably with low maintanance cost. | No effect as the audit report for completion did not require registered persons
AUDIT AND EVALUATION OF ROOF LEAKAGE AND CRACKED BUILDING AT LIMPOPO COLLEGE OF NURSING . MANKWENG HOSPITAL |  | JULY, 2008 |  | AUDIT | Joaquin E Fuentes G - 35% with Chris Masha and other CTA's | Delays in the designing stage and Non-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | No effect as the audit report for completion did not require registered persons
AUDIT AT RAPOTOKWANE TRIBAL OFFICES |  | NOVEMBER, 2009 |  | AUDIT | Joaquin E Fuentes G - 35% with Chris Masha and other CTA's | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
EVALUATION OF TECHNICAL REPORT FOR LETABA HOSPITAL 48 HOURS STANDBY WATER SUPPLY. |  | OCTOBER, 2009 |  | AUDIT AND CHECKING THE SPECIFICATION | Joaquim Fuentes - 50% with Ferreiro and Kekana RA | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
AUDIT AT POLOKWANE PROVINCIAL HOSPITAL |  | FEBRUARY, 2010 |  | AUDIT | Joaquim Fuentes - 50% with Ferreiro and Benny Mkhawane | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
AUDIT AT MANKWENG HOSPITAL |  | FEBRUARY, 2010 |  | AUDIT | Joaquim Fuentes - 50% with Ferreiro and Benny Mkhawane | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
JANE FURSE MEMORIAL HOSPITAL |  | MARCH,2010 |  | AUDIT | Joaquin E Fuentes G - 35% with Chris Masha and other CTA's | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
WORK SHOP FOR ROADS & TRANSPORT MOKAOPANE | UNKNOWN | 2010-07-01 |  | AUDIT | Joaquim Fuentes - 45% and Ferreiro Jorge and two Trainees | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
AGANANG TESTING STATION | 2750000 |  |  | Advertised awaiting appointment of contractor | Joaquin E Fuentes G. - 5% with Pfuluwani Phaswana | Delays in the designing stage and Non-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | No effect as the audit report for completion did not require registered persons
HOEDSPRUIT TRAFFIC STATION | 17750000 |  |  | PLANNING PHASE | Joaquin E Fuentes G. - 5% with Pfuluwani Phaswana | Delays in the designing stage and Non-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | No effect as the design phase of the project was done by consultants
Rapotokwane Tribal Offices (DESIGN) | 48000 | 16/4/2010 | 16/6/2010 | Architectural Design Phase Completed-100% | Alexis Rosales Coll - 100% | Delays in the designing stage and Non-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | No effect as the audit report for completion did not require registered persons
Mulima Tribal Offices (DESIGN) | 62000 | 18/6/2010 | 30/6/2010 | Architectural Design Phase Completed-100% | Alexis Rosales Coll - 100% | Delays in the designing stage and No-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | No effect as the design phase of the project was done by consultants
Parlamentary Village Offices (DESIGN) | 20000 | 22/6/2010 | 29/6/2010 | Architectural Design Phase Completed-100% | Alexis Rosales Coll - 100% | Delays in the designing stage and No-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | It has an effect as it requires that a registered person must sign of all the designs done by CTA's
Hall for 500 peoples -Department of Education (DESIGN) | 85000 | 17/2/2010 | 2010-09-03 | Architectural Design Phase Completed-100% | Alexis Rosales Coll - 100% | Delays in the designing stage and No-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | It has an effect as it requires that a registered person must sign of all the designs done by CTA's
Jane Furse Hospital-Adapting Old Building to Offices (DESIGN) | 100000 | 22/2/2010 | 25/10/2010 | Design Phase -10% completed. | Alexis Rosales Coll - 30% | Delays in the designing stage and No-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | No effect as the audit report for completion did not require registered persons
Database for Real State |  | 01/07/2010 | 30/09/2010 | Design Phase -10% completed. | Alexis Rosales Coll - 10% | Delays in the designing stage and No-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | No effect as the design phase of the project was done by consultants
DICHOENG CLINIC | 7445031.36 | 2008-09-01 | 2009-10-01 | Completed | Ferreiro R J - 30% and Frans Kekana | Principal Agent would have to appoint a civil enginner for inspection quality of the work. | CTA's form part of the team to advice the project manager and the principal agent | No effect as the design phase of the project was done by consultants
MARISHANE CLINIC | 7200000 | 2008-09-01 | 2009-07-01 | Completed | Ferreiro R J - 30% and Benny Mkhawane | Principal Agent would have to appoint a civil enginner for inspection quality of the work and deisgn of the bridge. | CTA's form part of the team to advice the project manager and the principal agent | No effect as the audit report for completion did not require registered persons
IKAGENG CLINIC | 7750000 | 2008-09-01 | 2010-07-09 | Completed | Ferreiro R J - 30% and Raymond Chauke | Principal Agent would have to appoint a civil enginner for inspection quality of the work. | CTA's form part of the team to advice the project manager and the principal agent | No effect as the design phase of the project was done by consultants
AGANANG TRAFFIC STATION | 7450000 | 2010-07-01 | 2011-02-09 | Construction Phase | Ferreiro R J - 25% and Phaswana | Principal Agent would have to appoint a civil enginner for inspection quality of the work. | CTA's form part of the team to advice the project manager and the principal agent | No effect as the design phase of the project was done by consultants
SNAG LISTFOR NEW BUILDING (WORKS TOWERS) | UNKNOWN | 2009-03-01 | 2009-10-01 | Completed | Ferreiro R J - 20% and Masha, Peter Hertz and the CTA's | Delays in the designing stage and No-interaction with the end user of the building | Achievement of designs in short time and the end user's satisfaction. | No effect as the design phase of the project was done by consultants
PARLAMENTARY MEC STAFF HOUSES | UNKNOWN | 2010-03-01 |  | AUDIT | Ferreiro R J | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
PARLAMENTARY VILAGE STAFF HOUSSES | UNKNOWN | 2010-03-01 |  | AUDIT | Ferreiro R J | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the design phase of the project was done by consultants
PARLAMENTARY VILAGE WHITE HOUSE | UNKNOWN | 2010-07-01 |  | AUDIT | Ferreiro R J - 20% and other CTA's | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | It has an effect as it requires that a registered person must sign of all the designs done by CTA's
LEBOWAKGOMO GOVERNMENT COMPLEX | 18838125 | 2010-02-01 | 2011-05-01 | PLANNING | Ferreiro R J - 20% and other CTA's | Delays in appointment of consultants for the Audit and No-interaction with the end user of the building | Audit report was done by CTA's in a short time and the end user's satisfaction. | It has an effect as it requires that a registered person must sign of all the designs done by CTA's
THOHOYANDOU GOVERNMENT COMPLEX | 11748722 | 2010-02-01 | 2011-05-01 | PLANNING | Ferreiro R J - 20% and other CTA's | Delays in appointment of consultants for the Audit and No-interaction with the end user of the building | Audit report was done by CTA's in a short time and the end user's satisfaction. | No effect as the audit report for completion did not require registered persons
GIYANI GOVERNMENT COMPLEX | 14580752 | 2010-02-01 | 2011-05-01 | PLANNING | Ferreiro R J - 20% and other CTA's | Delays in appointment of consultants for the Audit and No-interaction with the end user of the building | Audit report was done by CTA's in a short time and the end user's satisfaction. | No effect as the design phase of the project was done by consultants
OLYMPIC TOWERS (DEPARTMENT OF SPORTS, ARTS & CULTURE) | UNKNOWN | 2009-10-01 |  | AUDIT | Ferreiro R J | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the design phase of the project was done by consultants
RAPATOKWANE TRIBAL OFFICES | R 5 200 000. 00 | 2010-04-01 |  | AUDIT | Ferreiro R J | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the design phase of the project was done by consultants
MULIMA TRIBAL OFFICES | R 5 200 000. 00 | 2010-06-01 |  | AUDIT | Ferreiro R J - 10% and other CTA's | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
EVALUATION OF LETABA HOSPITAL 48 HOURS ESTANBY WATER SUPPLY | UNKNOWN | Octuber 2009 |  | AUDIT | Ferreiro R J - 50% and other CTA's | No verification of the design in detail for compliance with SABS and good practice. | Improved technical verification with alternative methods to construct affordably with low maintanance cost. | No effect as the audit report for completion did not require registered persons
MANOTWANE CLINIC | UNKNOWN | 2009-07-01 |  | AUDIT | Ferreiro R J - 35% and Kekana RA and Joaquim Fuentes | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
ZEBEDIELA HOSPITAL | UNKNOWN | 2010-02-01 |  | AUDIT | Ferreiro R J - 35% and Benny Mkhawane and Joaquim Fuentes | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
VUVUMATSHENA SCHOOL | UNKNOWN | 2009-11-01 |  | AUDIT | Ferreiro R J - 35% and Vincent Maluleke and Joaquim Fuentes | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
EVALUATION OF ROOF TRUSSES IN THABAMOOPO HOSPITAL | UNKNOWN | 2009-08-01 |  | AUDIT | Ferreiro R J - 35% and Richard Nthabalala and Joaquim Fuentes | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
ZEBEDIELA TRIBAL OFFICES | UNKNOWN | 2010-02-01 |  | AUDIT | Ferreiro R J - 50% and Joaquim Fuentes | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons
JANE FURSE MEMORIAL HOSPITAL | UNKNOWN | 2010-03-01 |  | AUDIT | Ferreiro R J - 35% and Benny Manaka and other CTA's | Delays in appointment of consultants for the Audit and No-interaction with the end user of the building | Audit report was done by CTA's in a short time and the end user's satisfaction. | No effect as the audit report for completion did not require registered persons
WORK SHOP FOR ROADS & TRANSPORT MOKAOPANE | UNKNOWN | 2010-07-01 |  | AUDIT | Ferreiro R J - 45% and Joaquim Fuentes and two Trainees | Appoint consultants to audit the report for project completion. | No consultants were appointed resulting in no cost and saving time to appoint the consultants. | No effect as the audit report for completion did not require registered persons