TABLE OF CONTENTS

FOREWORD

PART A: STRATEGIC OVERVIEW

Overview by the Accounting Officer

Vision

Mission

Strategic Goals

Values

PART B: PROGRAMME AND SUB-PROGRAMME PERFORMANCE TARGETS

1. PROGRAMME ONE:	ADMINISTRATION

1.1	SUB-PROGRAMME: OFFICE OF THE MEC

1.1.1   Policies, programme objectives and priorities

1.1.2   Progress analysis

1.1.3   Analysis of constraints and measures to overcome them

1.1.4   Description of planned quality improvement measures

1.1.5   Specification of measurable objectives and performance indicators

1.2	SUB-PROGRAMME: STRATEGIC HUMAN RESOURCE MANAGEMENT

1.2.1   Policies, programme objectives and priorities

1.2.2   Progress analysis

1.2.3   Analysis of constraints and measures to overcome them

1.2.4   Description of planned quality improvement measures

1.2.5   Specification of measurable objectives and performance indicators

1.3   SUB-PROGRAMME: STRATEGIC FINANCING

1.3.1   Policies, programme objectives and priorities

1.3.2   Progress analysis

1.3.3   Analysis of constraints and measure to overcome them

1.3.4   Description of planned quality improvement measures

1.3.5    Specification of measurable objectives and performance indicators

1.4   SUB-PROGRAMME: CORPORATE SERVICES

1.4.1   Policies, programme objectives and priorities

1.4.2    Progress analysis

1.4.3   Analysis of constraints and measure to overcome them

1.4.4   Description of planned quality improvement measures

1.4.5   Specification of measurable objectives and performance indicators

1.5   SUB-PROGRAMME: GOVERNMENT INFORMATION TECHNOLOGY OFFICER

1.5.1   Policies, programme objectives and priorities

1.5.2   Progress analysis

1.5.3   Analysis of constraints and measure to overcome them

1.5.4   Description of planned quality improvement measures

1.5.5   Specification of measurable objectives and performance indicators

1.6   SUB-PROGRAMME: STRATEGIC MANAGEMENT

1.6.1   Policies, programme objectives and priorities

1.6.2   Progress analysis

1.6.3   Analysis of constraints and measure to overcome them

1.6.4   Description of planned quality improvement measures

1.6.5   Specification of measurable objectives and performance indicators

1.7    RECONCILIATION OF BUDGET WITH PLAN

2. PROGRAMME TWO: PROVINCIAL INFRASTRUCTURE DEVELOPMENT

2.1   SUB- PROGRAMME: PROFFESSIONAL SERVICES

2.1.1   Policies, programme objectives and priorities

2.1.2   Progress analysis

2.1.3   Analysis of constraints and measures to overcome them

2.1.4   Description of planned quality improvement measures

2.1.5   Specification of measurable objectives and performance indicators

2.2   SUB-PROGRAMME: PROJECT MANAGEMENT

2.2.1   Policies, programme objectives and priorities

2.2.2   Progress analysis

2.2.3   Analysis of constraints and measures to overcome them

2.2.4    Description of planned quality improvement measures

2.2.5   Specification of measurable objectives and performance indicators

2.3   SUB-PROGRAMME: REAL ESTATE

2.3.1   Policies, programme objectives and priorities

2.3.2    Progress analysis

2.3.3   Analysis of constraints and measures to overcome them

2.3.4   Description of planned quality improvement measures

2.3.5   Specification of measurable objectives and performance indicators

2.4   SUB-PROGRAMME : BUILDING MAINTENANCE

2.4.1   Policies, programme objectives and priorities

2.4.2   Progress analysis

2.4.3   Analysis of constraints and measures to overcome them

2.4.4   Description of planned quality improvement measures

2.4.5   Specification of measurable objectives and performance indicators

2.5   Reconciliation of budget with plan

3. PROGRAMME THREE: EXPANDED PUBLIC WORKS PROGRAMME

3.1   Policies, programme objectives and priorities

3.2   Progress analysis

3.3   Analysis of constraints and measures to overcome them

3.4   Description of planned quality improvement measures

3.5  Specification of measurable objectives and performance indicators

3.6   Reconciliation of budget with plan

4. IMPLEMENTATION OF THE CAPITAL INVESTMENT , MAINTENANCE  AND ASSET

MANAGEMENT PLAN

5. MEDIUM-TERM REVENUE

5.1 Summary of revenue

5.2 Departmental revenue collection

5.3 Conditional grants

5.4 Donor funding

6. CO-ORDINATION, CO-OPERATION AND OUTSOURCING PLANS

6.1 Interdepartmental linkages

6.2 Local government linkages

6.3 Public entities

6.4 Public private partnerships, outsourcing etc

7.1 FINANCIAL MANAGEMENT

7.1 Strategies to address audit queries

7.2 Implementation of PFMA

PART C: ANNUAL PERFORMANCE PLAN OF YEAR – 2007-2008

FOREWORD BY THE MEC

The Department of Public Works provides strategic leadership on the delivery of sustainable provincial government infrastructure.  Its contribution to the socio-economic transformation of the Province is achieved through:

- Sustainable job creation

- Skills transfer, and

- Poverty alleviation

It has been proven that where there has been State intervention in the economy through direct public investment in infrastructure, there has been economic growth and more job creation. Therefore, the Department of Public Works seeks to position itself to relate directly to the Provincial Growth and Development Strategy in terms of planning, development and management of provincial infrastructure. It will also seek to pursue measures that will assist in the transformation of the construction and property industries.

In an endeavor to alleviate poverty, create jobs and transfer skills, the department will put emphasis and resources towards the effective implementation of the Expanded Public Works Programme. This will require a more concerted effort towards Labour Intensive Construction projects. In this regard, a provincial five year EPWP business plan will be implemented from April 2007. The business plan will enable us to vigorously roll out EPWP to provincial departments and municipalities to ensure that its implementation is in compliance with the Division of Revenue Act and the Municipal Infrastructure Grant.

The department will continue using its property portfolio, the maintenance programme and the Expanded Public Works Programme for job creation and skills development as a way of contributing towards the reduction of unemployment in the Province. A maintenance plan for the provincial property portfolio is currently being developed to address both maintenance backlogs as well as future maintenance programmes.

The department intends to continue playing its crucial role in facilitating the provision of office accommodation to provincial departments. In this regard, a space audit to establish current and future office accommodation needs of provincial departments as well as the suitability of office space allocation is being undertaken. During the coming financial year this space audit will be extended to the districts.

Finally, the department, in pursuit of its mission and strategic goals, will seek to increase its flexibility in rendering effective services, embark on waste elimination and minimise lead times in responding to the needs of institutions and the people we serve in the course of infrastructure delivery.

………………………………………………….

Hon. M.R  Semenya

MEMBER OF THE EXECUTIVE COUNCIL

PART A: OVERVIEW BY ACCOUNTING OFFICER

The renewed focus of the Department of Public Works is to provide leadership in the delivery of provincial government building infrastructure and the management of government immovable assets. This is a challenge that requires continuous organizational review in order to fast track infrastructure delivery. It is against this background that the Department has underwent an intense process of reviewing its vision, mission, objectives and core mandates. This process has culminated in a thorough re-assessment of the strategic position of the Department in relation to its internal and the external environment. This re-assessment has highlighted an urgent need to address the following critical issues:

- Taking on board and providing sufficient resources, focus and time to critical mandates such as the Expanded Public Works Programme

- Paying particular attention to the efficient management of government immovable assets

- Addressing discontent often raised by client departments regarding the services rendered by the Department, in particular addressing project management issues, supply chain management delays and perceptions of fraud and corruption

- Having a clear understanding of the roles of various stakeholders in the construction and property industries and developing clear programmes of engaging these stakeholders in the government service delivery programmes

- Taking on board into our plans, programmes and projects the inputs of various stakeholders including our own officials and workers, contractors and their representative bodies, developers, professional experts and their institutions, communities, national and provincial departments, municipalities, parastatals, business, churches, NGOs and the general public

- Taking initiatives in driving the change management process in both the construction and property industries so that black people began to play a meaningful role in the command of these industries

- Undertaking an impact study of the construction boom on the availability of building materials as we move towards the 2010 Soccer World Cup. This should result in clear intervention strategies to assuage possible shortage in both building materials and skilled professionals

- As the coordinator of the Infrastructure Sub-Committee of the 2010 Soccer World Cup in the Province, the Department has to take strategic leadership in influencing the delivery of infrastructure for the World Cup

- Taking leadership in driving and influencing client departments to implement integrated planning and development in the delivery of social infrastructure.  This should result with infrastructure delivery following population and settlement patterns. In the final analysis infrastructure delivery by national, provincial and local municipalities should be able to complement each other

- Directing at least 30% of the infrastructure budgets of provincial departments and municipalities into the Expanded Public Works Porgramme to maximize job creation and skills transfer

- Initiating Public Works’ specific EPWP projects which should propel the Department into the forefront of EPWP implementation

- A clear analysis of the impact of HIV/AIDS on the construction industry as well as intervention strategies to reverse the scourge of the disease

- Determination of performance standards with regard to services rendered by the Department so that the public know, for example, how long it takes to build a four classroom block or how long it takes to process a tender from the date a tender closes to the date a site is handed over to a contractor to begin construction.

- Proper dissemination of information on policies and procedures used in the construction and property industries

- Aligning the Annual Performance Plan with the budget and prioritizing spending on service delivery mandates

- Developing clear performance targets for all the activities listed in the Annual Performance Plan to enable proper monitoring and evaluation

- Linking the Implementation Plan of the Risk Management Plan with the Annual Performance Plan so that risks identified through the Department risk assessment are simultaneously addressed during the implementation of the Annual Performance Plan

In the 2007/08 financial year the Department will develop programmes, projects and activity plans to address the above issues.  It will as a matter of urgency prioritise the following programmes:

- The Five-Year Expanded Public Works Programme Business Plan will be implemented with renewed vigour as implementing institutions will now be held accountable to achieve the performance targets they have listed in the Plan. Public Works will not only re-invigorate its coordinating institutional setup but will also take a lead in implementing its own distinct EPWP projects

- It is likely that the Government Immovable Assets Management Act (still a Bill) will come into effect in 2007/08.  The Department will prepare the ground for the implementation of this legislation so that in the end the roles and responsibilities of provincial departments regarding the management and maintenance of provincial government assets are clarified.  During this financial year the Department is hoping to complete the updating of its immovable asset register so that it can better manage this portfolio in the area of acquisition, disposal, maintenance as well as promoting value-generating investment on its properties.

- The Department has already begun with an integrated office accommodation plan which is premised on the space audit. In the coming financial year this audit will go to the districts.  It is anticipated that this audit will coincide with the study by PARU in the Provincial Treasury which is focusing on the structuring of regional offices in the province.  Through the office accommodation plan, the following departments will have new offices built within the institutional zone of Polokwane Municipality: Sports, Arts and Culture, Roads and Transport, Public Works and Local Government and Housing.  It is also anticipated that once the funding options are resolved, the construction of the Legislature will begin in Polokwane.

- It is anticipated that timeous implementation of social infrastructure projects for client departments, in particular the Departments of Education and Health and Social Development will be realized. The new planning framework adopted by the Executive Council compels client department to submit business plans to Public Works by June to enable documentation, designs and tendering to happen prior to April the following year. Although client departments delayed in submitting these plans for 2007/08, Public Works has already processed all tenders for the Department of Education with the hope that first payments will be made on 1 April 2007.  Planning, designs and documentation for the Department of Health and Social Development have been shortened and it is hoped that these projects will be handed over to contractors by 1 April 2007 for implementation. The assistance of the Provincial Technical Assistance Teams of the Infrastructure Delivery Improvement Programme (IDIP) run by National Treasury will also help improve in the delivery of infrastructure.  Public Works will also outsource certain project management functions to help cope with the increased volume of projects.  The re-alignment of our Supply Chain Management policy with the CIDB and the Provincial Preferential Procurement policy has been completed. This will provide parameters for the setting up of a dedicated Infrastructure Bid Adjudication Committee which will provide dedicated attention to expediting infrastructure tenders.

With this renewed strategic focus there should be no impediment for Public Works to resume its strategic leadership in the delivery of public infrastructure.  With a committed team of employees, assisted by capable technical teams both from the ILO and IDIP, there should be no doubt that Public Works will rise to its clarion call of “Re a Shoma” and that “South Africa works because of Public Works”.

……………………………….

Mr Johannes Rantete

Head of Department

Vision

A leader in the provision and management of provincial land and buildings

Mission

Optimal utilization of resources in the provision and management of provincial land and buildings and the coordination of the implementation of Expanded Public Works Programme.

Strategic goals

- Sustainable provincial building infrastructure to support service delivery

  - Maintenance of government buildings for safe and reliable use in accordance with norms and standards

  - Implementation of capital works projects within time lines, budget and quality in line with IDIP initiatives

  - Efficient management of immovable properties utilized for government service delivery

  - Facilitate infrastructure planning

- Poverty alleviation, skills transfer and job creation

  - Achievement of  EPWP goals using DPW capital and maintenance budgets

  - A well coordinated Provincial EPWP

  - Monitoring and evaluation of EPWP implementation

- Promotion of Broad Based Black Economic Empowerment

  - Implementation of preferential procurement policies in compliance with relevant

Government procurement prescript

- Improved service delivery and good corporate governance:

  - Optimum financial management

  - Implementation of service delivery improvement programme

  - Implement human resource development programme

  - Improved health and psycho-social functioning of staff

  - Implementation of Occupational Health and Safety Programme

  - Implementation of appropriate procurement and provisioning system which is fair, equitable, transparent, competitive and cost effective

  - Enhance and strengthen internal and external communication

Values

The Limpopo Department of Public Works prides itself on the following core values;

- Professionalism

- Humility

- Adherence to the Batho Pele principles

PART B: PROGRAMME AND SUB-PROGRAMME PERFORMANCE TARGETS

1. PROGRAMME ONE: ADMINISTRATION

The main objective of this programme is to provide support to line functions through the executive support services, strategic management, financial management, human resources, corporate services and information and communication technology services.

The Administration Programme includes the following sub-programmes:

- Strategic Human Resource Management

- Strategic Finance

- Corporate Services

- Government Information Technology Services

- Strategic Management

- MEC’s Support, and

- HOD’s Office

Policies, Programme Objectives and Priorities

Policies

The Department is guided by national policies aimed at transforming the public service, such as Batho Pele and the White Paper on Transformation of the Public Service. In addition, the Department functions within the regulatory framework governed by the Public Service Act, the Public Service Regulations, Skills Development Act, Skills Development and Levies Act, Basic Conditions of Employment Act, Labour Relations Act, Public Finance Management Act, Treasury Regulations, the Preferential Procurement Policy Framework Act, Occupational Health and Safety Act and many other legislation. The Department is also bound by centrally negotiated agreements regarding conditions of service for its employees.

Programme Objectives:

- Implementation of service delivery improvement programme

- Implementation of human resource development programme

- Improved health and psycho-social functioning of staff

- Implementation of Occupational Health and Safety Programme

- Implementation of appropriate procurement and provisioning system which is fair, equitable, transparent, competitive and cost effective

- Optimum financial management

- Implementation of effective, efficient and transparent systems of financial management, risk management and internal control

- Enhancement  and strengthening of  internal and external communication

Priorities

- Implementation of workplace skills plan

- Alignment of the organizational structure to the strategic plan

- Recruitment of staff

- Improve the implementation of the Performance Management System.

- Implementation of an integrated Employee Wellness Programme including HIV/AIDS

- Implementation of service delivery improvement programme

- Implementation of special programmes

- Implementation of Batho Pele

- Monitoring and evaluation of Departmental programmes

- Implementation of the Intergovernmental Relations Framework

- Coordination of regional integration programmes in line with the PGDS objectives

- Proper utilization of movable physical resources

- Provision of logistical facilities for Departmental functions

- Implementation of Occupational Health and Safety Programme

- Maintenance of an appropriate procurement and provisioning system which is fair, equitable, transparent, competitive and cost effective

- Optimum revenue collection

- Optimum budget management

- Optimum risk management

- Implementation of supply chain management policy

- Implementation of Broad Based Black Economic Empowerment

- Implementation of Minimum Information Security System

- Implementation of Master System Plan projects

- Provision of information and records management services

- Implementation of the communication strategy

- Coordinated executive support services

- Coordinated Parliamentary services

Progress Analysis

The Department has a five year strategic plan which is accompanied by an annual performance plan that is reviewed annually.  Human resource policies have been developed. Supply Chain Management policy is in place and has been aligned to the provincial preferential procurement policy. Financial management is guided by the PFMA and Treasury Regulations. GITO has developed a Master System Plan which guides the implementation of ICT projects.

Analysis of Constraints and Measures Planned to Overcome Them

The delays in funding the filling of vacant posts has resulted in many staff leaving the Department to other sister departments in the Province. This has had a negative impact on the running of the Department.  Many posts are vacant. There is a high rate of officials acting in critical posts. The review of the organisational structure has also taken too long without being finalised.  Delays in job evaluations and the requirement for organisational structures to be approved by the Minister of Public Service have also compounded the problem.  Although it is a highly technical department, Public Works is heavily reliant on manual work.  There is critical shortage of systems to manage critical programmes. Systems that have been acquired are not effectively utilised.  Although there is an elaborate planning process that is followed in the compilation of departmental plans, this needs enhancement especially with regard to involving critical stakeholders.

Measures that are planned to overcome the above constraints include expediting the appointment of an organisational development expert to help craft an appropriate organisational structure, the filling of vacant posts and devising means of attracting scarce skills. The Department will be acquiring relevant systems to alleviate reliance on manual operations. Officials will also be trained on the use of these systems.  Future planning process will ensure broader consultation with various stakeholders to ensure that departmental plans are enriched by their inputs.

Description of Planned Quality Improvement Measures

The Department will embark on a project to optimise its business processes and workflows across all its units to enable it to effectively support the core functions.

1.1 Sub-Programme: Office of the MEC

The Office of the MEC is responsible for the provision of a well coordinated executive service that is aimed at achieving the vision of the Department.

1.1.1 Policies, Programme Objectives and Priorities

Policies

The office is guided by both national and provincial policies which are pronounced from time to time. Key to the successful realisation of the Department’s vision is the vigorous implementation of transformation programmes embodied in the White Paper on the Transformation of the Public Service as well as Batho Pele policy framework.  The office is also guided by the Ministerial Handbook on a number of administrative issues.

Programme Objectives

- Intensify implementation of service delivery improvement programme

Priorities

- Coordinated executive support services

- Coordinated Parliamentary services

1.1.2 Progress analysis

The Sub-Programme has improved the Department’s interaction with its stakeholders, in particular the MEC’s meetings with contractors, built-environment professionals (consultants) and the conference on women in construction. Imbizos have also helped the Department to hear and address issues raised by communities. The visits conducted by the MEC to the Department’s district offices, has assisted in exposing head office to the service delivery challenges being experienced in the districts.  Conferences and workshops held for people living with disability and HIV/AIDS not only raised the moral status of the Department but also ensured that the Department take seriously issues affecting our vulnerable employees.

1.1.3 Analysis of Constraints and Measures Planned to Overcome Them

The Sub-programme is appropriately staffed, but most of the staff needs to be correctly placed in appropriate levels in the organisational structure. MEC’s support staff requires further training to enhance their effectiveness in executing executive support to the MEC.

1.1.4 Description of Planned Quality Improvement Measures

The sub-programme will continue with the consultation programme with various stakeholders.  Moreover, the Sub-programme will be evaluated so that employees are placed in correct levels.

1.1.5 Specification of measurable objectives and performance indicators

| Sub Programme Office of the MEC | Strategic Goal: Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Performance Measure/indicator | 2004/05 Actual | 2005/06 Actual | 2006/07 Estimate | 2007/08 Target | 2008/09 Target | 2009/10 Target |
| Implementation of service delivery improvement programme | Coordinated executive support service | Holding of Stakeholder meetings | To develop Executive Liaison Strategy | Implement Executive Liaison Strategy | Implement Executive Liaison Strategy | Hold 8 Imbizo Meetings | Hold 8 Imbizo Meetings | Hold 8 Imbizo Meetings |
|  |  |  | To develop Executive Liaison Strategy | To develop Executive Liaison Strategy | To develop Executive Liaison Strategy | Hold 2 District Visits | Hold 2 District Visits | Hold 2 District Visits |
|  |  |  | - | - | - | Hold 4 Meetings with councilors responsible for EPWP | Hold 4 Meetings with councilors responsible for EPWP | Hold 4 Meetings with councilors responsible for EPWP |
|  |  |  | - | - | - | Hold 3 consultative meetings with critical stakeholders | Hold 3 consultative meetings with critical stakeholders | Hold 3 consultative meetings with critical stakeholders |
|  |  |  | - | - | - | Address 3 Conferences | Address 3 Conferences | Address 3 Conferences |
|  |  | Implementation of protocol programmes | Implementation of protocol programmes | Implementation of protocol programmes | Implementation of protocol programmes | - | - | - |
|  |  | Implementation of constituency programmes | Implementation of constituency programmes | Implementation of constituency programmes | Implementation of constituency programmes | - | - | - |
|  |  | Handover of completed projects to client departments | - | - | - | Handover of 8 projects to client departments | Handover of 8 projects to client departments | Handover of 8 projects to client departments |
|  | Coordinated Parliamentary Service | Coordinate Parliamentary Service | Implementation of legislative programmes | Implementation of legislative programmes | Implementation of legislative programmes | Coordinate submission of 4 Quarterly Reports to Portfolio Committee | Coordinate submission of 4 Quarterly Reports to Portfolio Committee | Coordinate submission of 4 Quarterly Reports to Portfolio Committee |
|  |  |  | Implementation of legislative programmes | Implementation of legislative programmes | Implementation of legislative programmes | Preparation and Tabling of Budget Speech | Preparation and Tabling of Budget Speech | Preparation and Tabling of Budget Speech |

1.2 SUB- PROGRAMME : STRATEGIC HUMAN RESOURCE MANAGEMENT

The sub-programme is responsible for the attraction and provision of competent human resources, human resource development, performance management system and Employee Assistance Programme. Structural problems, capacity and inadequate funds have to a larger extent reduced the ability of this sub-programme to respond to challenges and service delivery requirements posed by external environment, new policy mandates and additional core functions within the Department.  However, these challenges have been addressed by the adoption of a new organisational structure to enable support for implementation of strategic plans.

1.2.1 Policies, Programme Objectives and Priorities

Policies

The Sub-Programme is guided by the Public Service Act and Regulations, Labour Relations Act, Skills Levy Act, Basic Conditions of Employment Act, White Paper on Transformation of the Public Service and Batho Pele amongst others.

Programme Objectives

- Implementation of service delivery improvement programme

- Implementation of human resource development programme

- Improved health and psycho-social functioning of staff

- Implementation of Occupational Health and Safety Programme

Priorities

- Implementation of workplace skills plan

- Alignment of the organizational structure to the strategic plan

- Recruitment of staff

- Improve the implementation of the Performance Management System

- Implementation of an integrated Employee Wellness Programme including HIV/AIDS

- Implementation of Occupational Health and Safety Programme

1.2.2  Progress Analysis

A consolidated human resource plan has been developed and comprises of a workplace skills plan, employment equity plan, affirmative action plan, redundancy plan, succession plan, retention plan and the recruitment plan.  The implementation of the performance management system is taking shape and the updating of personnel information on Persal has improved. All matters relating to the head count have attended to. The province has adopted a human development strategy and what remains is for the department to implement the plan. The Department is adequately implementing the Employee Wellness Programme including management of HIV/AIDS. The Occupational Health and Safety Programme is also being implemented.

1.2.3  Analysis of Constraints and Measures Planned to Overcome Them

Delays around the finalization of the organizational structure which is aligned to the Departmental Strategic and Operational Plans impact on the effective running of the administration. The high rate of vacant post and the time it takes to fill posts are matters of concern. In addition to this, the Department also faces challenges in attracting scarce skills in the built environment. Although there is national consensus on the need to attract scarce skills, there has been confusion on the measures to be followed in doing this. A recent analysis by the Premier’s Office on the capacity of departments to deliver services has revealed that Public Works has a significant number of officials at management and middle management who do not have relevant qualifications for the jobs they do. While officials do indicate areas where they need training in their performance instruments, the training provided during the course of the year does not systematically consider this and become in the most haphazard.

To reverse the negative trend described above, the Department expedite the review of the organisational structure and the filling of posts. It will develop a training programme which is linked to personal development plans of employees. Special attention will be paid to the capacity gaps in senior and middle management. Any available innovative way of attracting scarce skills will be pursued.  Learnership and Internship programmes to address skills shortage in the built-environment will be provided and bursaries will be given to serving and non-serving employees.

1.3.4 Description of Planned Quality Improvement Measures

The major focus of quality improvement will be around the turn around time in the filling of posts. Innovative approaches in attracting and retaining scarce skills will also be pursued.

1.2.5 Specification of measurable objectives and performance indicators

| Sub-Programme HRM | Strategic Goal: Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Performance Measure | Actual 2004/05 | Actual 2005/06 | Estimate 2006/07 | Target 2007/08 | Target 2008/09 | Target 2009/10 |
| Implement human resource development programme | Implementation of workplace skills plan | Implementation of skills programme to employees | Implement skills development programmes | Implement skills development programmes | Implement skills development programmes | Implementation of workplace skills programme to 530 employees | Implementation of workplace skills programme to 530 employees | Implementation of workplace skills programme to 530 employees |
|  |  |  | Award education and training grants | Award education and training grants | Award education and training grants | Awarding 170 bursaries for serving employees | Awarding 170 bursaries for serving employees | warding 170 bursaries for serving employees |
|  |  |  | ward education and training grants | Award education and training grants | Award education and training grants | Awarding 78 bursaries for external students | warding 78 bursaries for external students | Awarding 78 bursaries for external students |
|  |  |  | Implement learnership programmes | Implement learnership programmes | Implement learnership programmes | Awarding 247 learnerships to external learners | Awarding 247 learnerships to external learners | warding 247 learnerships to external learners |
|  |  |  | Implement internship programs | Implement internship programs | Implement internship programs | Implement internship programs | Implement internship programs | Implement internship programs |
|  |  |  | Develop framework for mentoring, coaching, exchange programme and career development | Develop framework for mentoring, coaching, exchange programme and career development | evelop framework for mentoring, coaching, exchange programme and career development | - | - | - |
|  | Alignment of the organisational structure to the strategic plan | Finalised and aligned organizational structure | Review organizational structure | Review organizational structure | Review organizational structure | Finalise and align organizational structure | Finalise and align organizational structure | Finalise and align organizational structure |
|  | Recruitment of staff | % of posts filled in the organogram | Review and implementation of HR plan | Review and implementation of HR plan | Review and implementation of HR plan | 100% filling of vacant posts | 100% filling of vacant posts | 100% filling of vacant posts |
| Improved health and psyco-social functioning of staff | Implementation of an integrated Employee Wellness Program (Incl. HIV/AIDS) | Increased number of employees utilizing the service | Implement an Employee Assistance Programme | Implement an Employee Assistance Programme | Implement an Employee Assistance Programme | 3500 employees utilizing Employee Wellness Programme | 3500 employees utilizing Employee Wellness Programme | 3500 employees utilizing Employee Wellness Programme |
| Implementation of Occupational Health and Safety Programme | Improved work environment | Implementation of a Workplace Relations Programme | Implement Occupational Health and Safety Programme | Implement Occupational Health and Safety Programme | Implement Occupational Health and Safety Programme | Implement Occupational Health and Safety Programme | Implement Occupational Health and Safety Programme | Implement Occupational Health and Safety Programme |
| Implementation of Performance Management System | Performance improvement | Meeting performance goals and targets | Implement Performance Management policy | Implement Performance Management policy | Implement Performance Management policy | Implement Performance Management policy | Implement Performance Management policy | Implement Performance Management policy |

1.3 SUB-PROGRAMME: STRATEGIC FINANCING

The sub-programme is responsible for implementing internal control measures and ensuring compliance to legislation governing financial management and corporate governance. The sub-programme further coordinates responses to the Auditor General’s requests, and the implementation of corrective measures in response to queries raised.  It is also responsible for budget management, revenue collection and supply chain management.

1.3.1 Policies, Programme Objectives and Priorities

Policies

The sub-programme is guided by the Supply Chain Management Policy Framework, PFMA, Treasury Regulations, Broad Based Black Economic Empowerment Act, Preferential Procurement Policy Framework Act, etc.

Programme Objectives

- Optimum financial management

- Implementation of appropriate procurement and provisioning system which is fair, equitable, transparent, competitive and cost effective

- Implementation of effective, efficient and transparent systems of financial management, risk management and internal control

Priorities

- Optimum revenue collection

- Optimum budget management

- Maintenance of an appropriate procurement and provisioning system which is fair, equitable, transparent, competitive and cost effective

- Optimum risk management

- Implementation of MISS

1.3.2 Progress Analysis

The Department has been meeting most of the deadlines for compliance with the PFMA, Treasury Regulations and other financial transcripts. The Department is currently implementing the Supply Chain Management policy which has been aligned to the Provincial Preferential Procurement policy.  It has adopted and is implementing a Risk Management Strategy and a Fraud Prevention Plan. A new risk assessment has been conducted in 2006/07 and risk assessment plans will be implemented in the coming financial year. Through the implementation of these plans, there has been a reduction in the number of fraud and corruption incidents. The Department has attained an acceptable level of awareness and culture change in the area of risk, at both strategic and operational levels. The Department has furthermore improved its activity based budgeting and costing and ensuring that all expenditures are allocated to the correct budgets.  The Department has improved the linkage between departmental plans and the budget within the Medium Term Expenditure Framework (MTEF). Through the Risk and Security Management Unit better relations have been developed with the office of the Auditor General leading to the minimisation of audit queries.

1.3.3 Analysis of Constraints and Measures Planned to Overcome them

There is consistent budget under-spending. There are delays in processing tenders in particular projects tenders. Perceptions of fraud and corruption, even though minimised, are still there. Administrative weaknesses that lead to audit queries still exist. Management of assets in the Finest system run by Provincial Treasury is still unreliable. Effective collection of debt, in particular arrear rentals still pose a challenge.

1.3.4 Description of Planned Quality Improvement Measures

- The component of Risk and Security management has established a programme of action to mitigate and address audit queries. An action plan has been drawn up for each of the financial year and expressions as pronounced by the Auditor General, and quarterly reviews are made as a means of addressing all issues raised in the Audit process.  In financial management, a strong focus has been in building capacity and increasing resources to attend to debt management and revenue collection. Training sessions have been concluded and personnel have been recruited to meet the new requirements of clearing debt in the department, especially internal staff debt. Although the implementation of the financial system is slow, the department will continue with training of staff to be able to manage the system.  Business process re-engineering will be made on Supply Chain Management to improve its implementation.

- 1.3.5 Specification of measurable objectives and performance indicators

| Sub-Programme: Strategic Financing | Strategic Goals: Improved Service Delivery and Good Corporate Governance Promotion of Broad Based Black Economic Empowerment |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Performance Measure | Actual 2004/05 | Actual 2005/06 | Estimate 2006/07 | Budget 2007/08 | Target 2008/09 | Target 2009/10 |
| Optimum financial management | Optimum budget management | Amount of revenue collected | Develop revenue collection strategy | Implement revenue collection strategy | Implement revenue collection strategy | 100% revenue collected within the tolerance level of 2% | 100% revenue collected within the tolerance level of 2% | 100% revenue collected within the tolerance level of 2% |
|  | Optimum revenue collection | 100% budget expenditure within the tolerance level of 2% | Sound budgeting and budgetary control practices | Sound budgeting and budgetary control practices | Sound budgeting and budgetary control practices | 100% budget spent within the tolerance level of 2% | 100% budget spent within the tolerance level of 2% | 100% budget spent within the tolerance level of 2% |
| Implementation of appropriate procurement and provisioning system which is fair, equitable, transparent, competitive and cost effective | Maintenance of an appropriate procurement and provisioning system which is fair, equitable, transparent, competitive and cost effective | Implementation of the Supply Chain Management policy Implementation of preferential procurement policies in compliance with relevant Government procurement prescripts | Well capacitated Department in managing SCM policies | Capacity building on Supply Chain Management policy | Capacity building on Supply Chain Management policy | Train 40 officials on SCM | Train 40 officials on SCM | Train 40 officials on SCM |
|  |  |  |  | Ensure compliance with SCM | Ensure compliance with SCM | Ensure compliance with SCM Development of standards and map processes including holding of 11 workshops | Ensure compliance with SCM | Ensure compliance with SCM |
|  |  |  |  | Develop and Implement BEE Policy | Implementation of BEE Policy | Development of strategy and implementation plan on BBBEE | Implementation of BBBEE Policy | Implementation of BBBEE Policy |
| Implementation of effective, efficient and transparent systems of financial management, risk management and internal control | Optimum Risk Management | Implementation of risk and fraud prevention | Minimised risk and fraud activities | Implement Risk management and fraud prevention plan | Implement Risk management and fraud prevention plan | Conduct 20 Risk and Fraud Awareness campaigns | Conduct 10 Risk and Fraud Awareness campaigns | Conduct 10 Risk and Fraud Awareness campaigns |
|  |  |  |  |  |  | Compilation of 4 quarterly risk management reports | Compilation of 4 quarterly risk management reports | Compilation of 4 quarterly risk management reports |
|  |  |  |  |  |  | Compilation of 4 quarterly security assessment and audit reports | Compilation of 4 quarterly security assessment and audit reports | Compilation of 4 quarterly security assessment and audit reports |
| Implementation of Minimum Information Security System (MISS) | Secure information | Implementation of Minimum Information Security System (MISS) | - | - | - | Implement MISS | Implement MISS | Implement MISS |

1.4 SUB-PROGRAMME: CORPORATE SERVICES

A strong Corporate Services that is aligned to the functional strategies of the Department and also supporting the overall strategy of the Department is a pre-requisite for the attainment of the vision of the Department. The main responsibility of this sub-programme is to strengthen the dynamism of the Department for continuous improvement and also provide management and administrative support functions which inter alia include facilities and fleet management.

1.4.1 Policies, Programme Objectives and Priorities

Policies

The Sub-Programme if guided by Supply Chain Management policy, PFMA, Treasury Regulations, Occupational Health and Safety Act, BBBEE and the Enterprise Resource Plan in its execution of functions.

Programme Objectives

- Implementation of service delivery improvement programme

Priorities

- Proper utilization of movable physical resources

- Provision of logistical facilities for Departmental functions

- Provision of clean, safe and secure environment

- Implementation of compliance measures to OHS Act

1.4.2 Progress Analysis

The Sub-Programme provides administrative support to line function programmes. There has been adequate administrative support provided to line function programmes in the past years. Improvements have been made in fleet and logistics management. Appropriate and adequate telecommunication systems have been procured.  This has also been extended to the districts.

1.4.3 Analysis of Constraints and Measures Planned to Overcome Them

There are no major constraints facing the Sub-Programme.  What needs to be done is quality service delivery improvement.

1.4.4 Description of Planned Quality Improvement Measures

- Improve telephone connectivity at Cost Centres

- Improve the filing system and methods used for risk free and user friendly system

- Ensuring of safe, secure storage and handling of documentation.

- Disposal of redundant files using the National Archives Act as a guide.

- Improve service delivery, internal and external, by ensuring fast and accurate

payments of services rendered.

- Quick cancellation and processing of orders.

- Decentralise budgets to Districts in order to procure according to needs

- Reduce fleet abuse and vehicle misuse

- Promote effective and wise vehicle usage

- Monitor and evaluate all procurement processes

1.4.5  Specification of measurable objectives and performance indicators

| Sub-Programme: Corporate Services | Strategic Goal: Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Performance Measure | Actual 2004/05 | Actual 2005/06 | Estimate 2006/07 | Budget 2007/08 | Target 2008/09 | Target 2009/10 |
| Implementation of service delivery improvement programme | Proper utilization of moveable physical resources | Implementation of Enterprise Resource Plan (ERP) | Development of ERP | Implementation of ERP Purchase of vehicles | Implementation of ERP Purchase of vehicles | Purchase of vehicles | Purchase of vehicles | Purchase of vehicles |
|  |  |  |  | Provision of labour saving devices and office equipment | Provision of labour saving devices and office equipment | Maintenance of vehicles | Maintenance of vehicles | Maintenance of vehicles |
|  |  |  |  |  |  | Lease and maintenance of photocopiers | Lease and maintenance of photocopiers | Lease and maintenance of photocopiers |
|  |  |  |  |  |  | Purchase of office equipment and office furniture | Purchase of office equipment and office furniture | Purchase of office equipment and office furniture |
|  |  |  |  |  |  | Stationery and printing | Stationery and printing | Stationery and printing |
|  |  |  |  |  |  | Management of telecommunication systems | Management of telecommunication systems | Management of telecommunication systems |
|  | Provision of logistical facilities for Departmental functions | Preparation for Departmental events | Preparation for Departmental events | Preparation for Departmental events | Preparation for Departmental events | Preparation for Departmental events | Preparation for Departmental events |  |
|  | Provision of clean, safe and secure environment | Payment of security and cleaning services | Payment of security and cleaning services | Payment of security and cleaning services | Payment of security and cleaning services | Payment of security and cleaning services | Payment of security and cleaning services | Payment of security and cleaning services |
|  |  | Installation of access control system and CCTV camera | Installation of access control system and CCTV camera | - | - | Installation of access control system and CCTV camera | Maintenance of the system | Maintenance of the system |
|  |  | Installation of Guard Monitoring System | Installation of Guard Monitoring System | - | - | Installation of Guard Monitoring System | Maintenance of the system | Maintenance of the system |
|  | Implementation of compliance measures to OHS Act | Adequate provision of protective clothing | Ensure compliance with OHS Act | Ensure compliance with OHS Act | Ensure compliance with OHS Act | Adequate provision of protective clothing | Adequate provision of protective clothing | Adequate provision of protective clothing |

1.5 SUB-PROGRAMME: GOVERNMENT INFORMATION TECHNOLOGY OFFICER

[GITO]

The sub-programme is responsible for the provision of Information Communication and Technology services to enhance electronic communication with both internal and external stakeholders. The sub-programme is also responsible for information management, communication and records management. It plays a critical in projecting the corporate image of the Department.

1.5.1 Policies, Programme Objectives and Priorities

As a matter of priority, the sub-programme will intensify control over the use of IT facilities to ensure service delivery through integrated management information systems. The main focus thereof is to modernise, enhance and align information systems with the core functions.

Policies

The Sub-Programme is guided by the Promotion of Access to Information Act, Departmental Communication policy, records management ITC prescripts.

Programme Objectives

- Improved Service Delivery and Good Corporate Governance

Priorities

- Implementation of service delivery improvement programme

- Enhancement and strengthening of internal and external communications

1.5.2 Progress Analysis

During 2006/2007 the Department developed the Information and Records Management strategy and the Promotion of Access to Information Act (PAIA) manual and translated it into three official languages.  Communication Services coordinated a number of outreach programmes which aimed at communicating what the Department is doing and how to access government tenders among others.  Two workshops on EPWP with the youth were also conducted in Mopani and Waterberg Districts. The Department has also completed the network infrastructure in all its cost centres including the risk assessment and business impact analysis for business continuity and disaster recovery plan.

The sub-programme successfully completed the development of a Master Systems Plan (MSP) which is aimed at aligning the department’s IT objectives to the overall business strategy. The sub-programme also developed structured cabling infrastructure in District Cost centres, and developed an RCC database for buildings at Head Office to enable them to optimise their maintenance services. All software used in the Department has been licensed in terms of industry best-practice. The information management unit has successfully responded to all requests for library materials and also ensured timeous delivery of all departmental reports.

1.5.3 Analysis of Constraints and Measures Planned to Overcome Them

There is a general lack of IT skills among users and the Department will embark on a training programme to address this challenge. A further challenge is to enhance information management. This will be achieved by exploring an integrated document management system.

There is a general misconception by the public regarding the services that are provided by the Department as a result of poor communication. The Department has adopted a communication strategy that contains a number of initiatives that are aimed at addressing this challenge.

1.5.4 Description of Planned Quality Improvement Measures

- To provide stable and efficient ICT infrastructure by means of improving network connectivity in all regions, cost centres and head office.

- Ensure that all Service Level Agreement, (SLA) are established with service providers

- Ensure planning in line with MSP guidelines for optimised, reliable ICT infrastructure to improve Internal and external communication.

- Ensure that at least 90% of hardware and software as well as related accessories are provided for the Department.

- Continue compliance with Legislative requirements and time schedule.

- Ensure the availability of reliable reports for better decision making and improve communication.

1.5.5 Specification of measurable objectives and performance indicators

| Sub-Programme: GITO | Strategic Goal: Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Performance Measure | Actual 2004/05 | Actual 2005/06 | Estimate 2006/07 | Budget 2007/08 | Target 2008/09 | Target 2009/10 |
| Implementation of service delivery improvement programme | Improved work Efficiency | Implementation of the Master System Plan | Network Management | Network Management | Network Management | Network Management | Network Management | Network Management |
|  |  |  | Establish and equip 4 resource centres | Establish and equip 4 resource centres | - | - | - | - |
|  |  |  | Implementation of the GIS | Implementation of the GIS | Management of GIS | Management of GIS | Management of GIS | Management of GIS |
|  |  |  | Management of the LAN | Management of the LAN | Management of the LAN |  |  |  |
|  |  |  | Implementation of Disaster Recovery Plan | Implementation of Disaster Recovery Plan | Implementation of Disaster Recovery Plan | Implementation of Disaster Recovery Plan | Implementation of Disaster Recovery Plan | Implementation of Disaster Recovery Plan |
|  |  |  | Maintenance of IT hardware Implementation of IM strategy | Maintenance of IT hardware Implementation of IM strategy | Maintenance of IT hardware | - | - | - |
|  |  |  | - | - | - | Development and implementation of website and intranet | Management of website and intranet | Management of website and intranet |
|  |  |  | - | - | - | Acquisition and management of Infrastructure Management Information Systems | Management of Infrastructure Management Information Systems | Management of Infrastructure Management Information Systems |
|  |  |  | Payment of software licences | Payment of software licences | Payment of software licences | Payment of software licences | Payment of software licences | Payment of software licences |
|  |  |  | Management of Service Level Agreements (SLAs) | Management of Service Level Agreements (SLAs) | Management of Service Level Agreements (SLAs) | Management of Service Level Agreements (SLAs) | Management of Service Level Agreements (SLAs) | Management of Service Level Agreements (SLAs) |
|  | Provision of information and records management services | Implementation of Information Management Strategy projects | - | - | Implementation of Information Management Strategy projects | Implementation of Information Management Strategy projects | Implementation of Information Management Strategy projects | Implementation of Information Management Strategy projects |
|  |  | Functional Resource Centre | - | - | - | Functional Resource Centre | Functional Resource Centre | Functional Resource Centre |
|  |  | Implementation of Promotion of Access to Information Act | - | - | - | Implementation of Promotion of Access to Information Act | Implementation of Promotion of Access to Information Act | Implementation of Promotion of Access to Information Act |
|  |  | Effective and efficient messenger and postal services | - | - | - | Effective and efficient messenger and postal services | Effective and efficient messenger and postal services | Effective and efficient messenger and postal services |
|  |  | Development of information architecture | - | - | - | Development of information architecture | Development of information architecture | Development of information architecture |
|  |  | Development of records management system (centralization and digitization) | - | - | - | Development of records management system (centralization and digitization) | Development of records management system (centralization and digitization) | Development of records management system (centralization and digitization) |
| Enhancement and strengthening of internal and external communication | Implementation of the communication strategy | Implementation of corporate communication | Implementation of corporate communication | Implementation of corporate communication | Implementation of corporate communication | Implementation of corporate communication | Implementation of corporate communication | Implementation of corporate communication |
|  |  | Implementation of corporate identity/marketing programme | - | - | - | Implementation of corporate identity/marketing programme | Implementation of corporate identity/marketing programme | Implementation of corporate identity/marketing programme |
|  |  | Media and Research | Media and Research | Media and Research | Media and Research | Media and Research | Media and Research | Media and Research |
|  |  | Stakeholder management | Stakeholder management | Stakeholder management | Stakeholder management | Stakeholder management | Stakeholder management | Stakeholder management |

1.6 SUB-PROGRAMME: STRATEGIC MANAGEMENT

The Strategic Management Sub-Programme plays a central role in the strategic planning process of the department. It is tasked with the responsibility to coordinate the development of strategic plans and monitor the implementation thereof. The Sub-Programme is also responsibility for the coordination of service delivery initiatives, Batho Pele programmes as well as special programmes with particular focus on women, youth and persons with disability. Fostering Inter-Governmental Relations and the alignment of municipal IDPs is also the responsibility of this Sub-Programme.  The Sub-Programme is also tasked with coordinating regional integration programmes.

1.6.1 Policies, Programme Objectives and Priorities

Policies

The Sub-Programme is guided by the Public Service Act and Regulations, Batho Pele policy, PFMA and Treasury Regulations, Intergovernmental Relations Framework, the Provincial Growth and Development Strategy, municipal IDPs and prescripts covering special programmes.

Programme Objectives

- Implementation of service delivery improvement programme

Priorities

- Implementation of service delivery improvement programme

- Implementation of special programmes

- Implementation of coordinated strategic management

- Monitoring and evaluation of Departmental programmes

- Implementation of the Intergovernmental Relations Framework

- Coordination of regional integration programmes in line with the PGDS objectives

1.6.2 Progress Analysis

Strategic Management is a new established in the Department.  To date it has facilitated the review of the Departmental Strategic Plan and the compilation of the Annual Performance Plan.  Batho Pele principles and initiatives are being implemented. Interaction with municipalities within the context of the Intergovernmental Framework has been successful. Municipalities are invited to participate in the Departmental planning workshops while the Department in turn sends officials to participate in municipal IDP processes. Inter-visits within the SADC community has been happening which fostered the essence of the regional integration programme.

1.6.3 Analysis of Constraints and Measures Planned to Overcome Them

The Strategic Planning Unit needs to be capacitated as most of its posts are vacant. Improvement need to be made in the management of special programmes and the service delivery improvement programme.  Big challenge is the development of process maps to help guide how the different programmes perform their tasks and the interrelations between them.

1.6.4 Description of Planned Quality Improvement Measures

On going strategic planning process and quarterly performance reviews will be conducted to monitor the implementation of the strategic goals. The Batho Pele Change Engagement programme will be rolled out to the district offices. The challenge that remains is to review the departmental service standards. In addition, the implementation of special programmes needs to be fast tracked to meet national imperatives.

1.6.5 Specification of measurable objectives and performance indicators

| Sub-Programme: Strategic Management | Strategic Goal: Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Performance Measure | Actual 2004/05 | Actual 2005/06 | Estimate 2006/07 | Budget 2007/08 | Target 2008/09 | Target 2009/10 |
| Implementation of service delivery Improvement programme | Enhanced public service delivery | Service delivery excellence | Review Departmental service standards | Development and implementation of service delivery improvement programme | Implementation of service delivery improvement programme | Implementation of service delivery improvement programme | Implementation of service delivery improvement programme | Implementation of service delivery improvement programme |
|  | Enhanced public service delivery | Development and implementation of Departmental Awards | - | - | - | Development and implementation of Departmental Awards | Development and implementation of Departmental Awards | Development and implementation of Departmental Awards |
|  | Enhanced public service delivery | Development and implementation of Contractor Awards | - | - | - | Development and implementation of Contractor Awards | Development and implementation of Contractor Awards | Development and implementation of Contractor Awards |
|  | Enhanced public service delivery | Implementation of Special Programmes | Implementation of Special Programmes | Implementation of Special Programmes | Implementation of Special Programmes | Implementation of Special Programmes | Implementation of Special Programmes | Implementation of Special Programmes |
|  | Enhanced public service delivery | Implementation of Batho Pele Programmes | Implementation of Batho Pele Programmes | Implementation of Batho Pele Programmes | Implementation of Batho Pele Programmes | Implementation of Batho Pele Programmes | Implementation of Batho Pele Programmes | Implementation of Batho Pele Programmes |
|  | Implementation of coordinated strategic management | Implementation of coordinated strategic management | Implementation of coordinated strategic management | Implementation of coordinated strategic management | Implementation of coordinated strategic management | Implementation of coordinated strategic management | Implementation of coordinated strategic management | Implementation of coordinated strategic management |
|  | Implementation of the Inter-governmental Relations Framework (IGR) | Implementation of the Inter-governmental Relations Framework (IGR) | - | - | Implementation of the Inter-governmental Relations Framework (IGR) | Implementation of the Inter-governmental Relations Framework (IGR) | Implementation of the Inter-governmental Relations Framework (IGR) | Implementation of the Inter-governmental Relations Framework (IGR) |
|  | Coordination of regional integration programmes in line with PGDS objectives | Coordination of regional integration programmes in line with PGDS objectives | - | - | - | Coordination of regional integration programmes in line with PGDS objectives | Coordination of regional integration programmes in line with PGDS objectives | Coordination of regional integration programmes in line with PGDS objectives |

1.7 RECONCILIATION OF BUDGET WITH PLAN

Programme 1: Administration

|  | Outcome |  |  | Main appropriation | Adjusted appropriation | Revised estimate | Medium-term estimates |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Audited | Audited | Audited |  |  |  |  |  |  |
| R thousand | 2003/04 | 2004/05 | 2005/06 | 2006/07 |  |  | 2007/08 | 2008/09 | 2009/10 |
| Subprogramme |  |  |  |  |  |  |  |  |  |
| Statutory Payments | 607 | 638 | 680 | 680 | 680 | 680 | 714 | 750 | 783 |
| Management | 9,073 | 7,083 | 6,181 | 14,477 | 15,877 | 16,477 | 15,201 | 16,027 | 16,910 |
| Corporate Support | 88,600 | 68,867 | 60,476 | 86,590 | 84,090 | 84,090 | 92,374 | 97,035 | 102,046 |
| Financial Management | 8,514 | 34,955 | 34,466 | 39,588 | 40,488 | 40,088 | 43,316 | 44,585 | 45,139 |
| Human Resources | 27,146 | 28,949 | 33,965 | 32,966 | 34,634 | 36,421 | 31,027 | 36,804 | 43,954 |
| Information Technology | 22,620 | 22,929 | 24,179 | 27,388 | 31,900 | 31,900 | 29,306 | 30,779 | 32,362 |
| Total payments and estimates | 156,560 | 163,421 | 159,947 | 201,689 | 207,669 | 209,656 | 211,938 | 225,980 | 241,194 |

Summary: Economic classification

|  | Outcome |  |  | Main appropriation | Adjusted appropriation | Revised estimate | Medium-term estimates |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Audited | Audited | Audited |  |  |  |  |  |  |
| R thousand | 2003/04 | 2004/05 | 2005/06 | 2006/07 |  |  | 2007/08 | 2008/09 | 2009/10 |
| Current payments | 139,590 | 137,690 | 137,995 | 183,341 | 184,864 | 187,131 | 199,438 | 212,943 | 227,570 |
| Compensation of employees | 84,324 | 88,317 | 81,540 | 114,598 | 118,507 | 120,494 | 118,944 | 128,986 | 139,834 |
| Goods and services | 55,266 | 49,373 | 56,455 | 68,743 | 66,357 | 66,637 | 80,494 | 83,957 | 87,736 |
| Interest and rent on land | - | - | - | - | - | - | - | - | - |
| Financial transactions in assets and liabilities | - | - | - | - | - | - | - | - | - |
| Unauthorised expenditure | - | - | - | - | - | - | - | - | - |
| Transfers and subsidies to: | - | 8,035 | 2,210 | 2,687 | 2,632 | 2,352 | 2,000 | 2,086 | 2,180 |
| Provinces and municipalities | - | 235 | 232 | 382 | 147 | 147 | 500 | 522 | 545 |
| Departmental agencies and accounts | - | - | - | - | - | - | - | - | - |
| Universities and technikons | - | - | - | - | - | - | - | - | - |
| Public corporations and private enterprises | - | - | - | - | - | - | - | - | - |
| Foreign governments and international organisations | - | - | - | - | - | - | - | - | - |
| Non-profit institutions | - | - | - | - | - | - | - | - | - |
| Households | - | 7,800 | 1,978 | 2,305 | 2,485 | 2,205 | 1,500 | 1,564 | 1,635 |
| Payments for capital assets | 16,970 | 17,696 | 19,742 | 15,661 | 20,173 | 20,173 | 10,500 | 10,951 | 11,444 |
| Buildings and other fixed structures | - | - | - | - | - | - | - | - | - |
| Machinery and equipment | 16,970 | 17,696 | 19,742 | 15,661 | 20,173 | 20,173 | 10,500 | 10,951 | 11,444 |
| Cultivated assets | - | - | - | - | - | - | - | - | - |
| Software and other intangible assets | - | - | - | - | - | - | - | - | - |
| Land and subsoil assets | - | - | - | - | - | - | - | - | - |
| Total economic classification | 156,560 | 163,421 | 159,947 | 201,689 | 207,669 | 209,656 | 211,938 | 225,980 | 241,194 |

2. PROGRAMME TWO: PROVINCIAL INFRASTRUCTURE DEVELOPMENT

Provincial Infrastructure Programme is made up of the following Sub-Programmes:

- Professional Services

- Project Management

- Building and Maintenance, and

- Real Estate

2.1 SUB-PROGRAMME : PROFESSIONAL SERVICES

Professional Services Sub-Programme is responsible for the provision and management of professional services in respect of professional norms. It co-ordinates and develop infrastructure planning for Public Works and client departments.

2.1.1Policies, Programme Objectives and Priorities

Policies

The operations of the Sub-Programme are guided by legislation governing the built environment professions such as Acts governing the Engineering, Quantity Surveying, Architecture professions. The programme is also guided by the Occupational Health and Safety Act, Environmental legislation, National Building Regulations and other built environment regulations.  CIDB prescripts also bind the Sub-Programme.

Programme Objectives

- Implementation of capital works projects within time lines, budget and quality in line with IDIP initiatives

Priorities

The programme will focus on the following priorities:

- Timely design of client department projects

- Management of Consultants

- Research and Development

- Coordination of 2010 Soccer World Cup infrastructure

2.1.2 Progress Analysis

Following the EXCO decision to fast track implementation of the infrastructure plan, the Sub-Programme implemented a monitoring and evaluation mechanism which resulted in monthly meetings with client departments at the levels of MECs, HODs as well as technical staff. The mechanism has enabled the sub-programme to focus on its core function of integrated planning.  The IDIP Programme run by National Treasury is providing the necessary assistance in unlocking bottlenecks in the planning and delivery of infrastructure.

2.1.3 Analysis of Constraints and Measures Planned to Overcome Them

Lack of joint planning with client departments with regard to infrastructure provision is a major challenge. The programme will endeavour to enter into Service Level Agreements with client departments in order to address issues of planning. Another major challenge facing the programme is the lack of skilled and experienced personnel in certain professional disciplines.

2.1.4 Description of Planned Quality Improvement Measures

Interaction with various professional bodies will take place to clarify grey areas pertaining to the registration of professionals. To capacitate the programme in terms of both skill and staff, the programme will absorb professionals who are in training and eligible to undertake the test of professional competency.

2.1.5 Specification of measurable objectives and performance indicator

| Sub-Programme: Professional Services | Strategic Goal: Sustainable provincial building infrastructure to support service delivery |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Performance Measure | Actual 2004/05 | Actual 2005/06 | Estimate 2006/07 | Budget 2007/08 | Target 2008/09 | Target 2009/10 |
| Planning of capital works projects within time lines, budget and quality in line with IDIP initiatives | Improved implementation of capital works projects | Development and implementation of a projects planning implementation plan | - | - | - | Develop and implement a projects planning implementation plan | Develop and implement a projects planning implementation plan | Develop and implement a projects planning implementation plan |
|  | Coordinated provincial infrastructure delivery on the 2010 Soccer World Cup infrastructure | Coordinate provincial infrastructure delivery on the 2010 Soccer World Cup infrastructure | - | - | - | Coordinate provincial infrastructure delivery on the 2010 Soccer World Cup infrastructure | Coordinate provincial infrastructure delivery on the 2010 Soccer World Cup infrastructure | Coordinate provincial infrastructure delivery on the 2010 Soccer World Cup infrastructure |
|  | Updated norms and standards | Research and development of norms and standards |  | Research and development of norms and standards | Research and development of norms and standards | Research and development of norms and standards | Research and development of norms and standards | Research and development of norms and standards |

2.2 SUB-PROGRAMME: PROJECT MANAGEMENT

The restructuring of the Department and the creation of the Project Management Executive programme has presented an opportunity for increased development and improvement of service delivery in the provision of building construction management and project management to other provincial government departments. Setting up this unit will strengthen institutional and operational efficiency through improved systems, structures and processes.

2.2.1 Policies, Programme Objectives and Priorities

Policies

The programme is guided by the National Building Regulations (NBR), Construction Industry Development Board (CIDB), Occupational Health & Safety Act (OHS), Environmental Legislation and other Built-Environment regulations.

Programme Objectives

- Implementation of capital works projects within time lines, budget and quality in line with IDIP initiatives

Priorities

The programme will focus on the following priorities:

- Successful execution of capital works projects

- The consolidation and strengthening of project management procedures and systems. This will include capacity building in the districts to ensure visible project management services.

- Focusing attention on specific outcomes and directing resources appropriately.

- Improving control and accountability mechanisms.

- Ensuring good corporate governance.

2.2.2 Progress Analysis

Early warning systems were put in place to ensure early detection of poor performance by contractors. Monthly meetings are being held with Project Managers to determine progress per project and assist those who have challenges in executing their projects on time and within budget. Monthly progress reports are being submitted to Cluster Committees, HOD Forum as well as EXCO to monitor both budget and project performance. IDIP has been introduced in the sub-programme and implementation is underway.

2.2.3 Analysis of Constraints and Measures Planned to Overcome Them

The identification and formulation of challenges derive from the probing of the maturity of our project management practices as well as pertinent observations made by stakeholders. An illustration of challenges experienced at various levels of the project management structures as we struggle at times to excute the work on behalf of our clients include but are not limited to:

- Delays in appointment of contractors.

- Delays in payments to contractors.

- Complaints of poor workmanship

- Endless post delivery snag lists.

- Inability on the part of contractors to deliver timeously the facilities.

- Interference by local authorities and communities in  the operations of appointed contractors.

- Inadequate monitoring of workmaship and quality due to the geographic spread of the projects.

- Inadequate management control systems

2.2.4 Description of Planned Quality Improvement Measures

The interventions guided by the need to improve project implementation and monitoring will be through strengthening of existing project management organisational structures and clarifying roles/functions of various units both at head office and district level. The programme has already started assigning project managers to projects in a manner that matches their individual level of competence to the magnitude and level of complexity. A structure is in place which enables technical personnel in the built environment to focus on specific aspects of a project cycle. The programme will maintain a critical mass of personnel at head office, whose functions will include general project management activities and it will also form part of capacity building teams for our project management structures at district level. The CIDB register of contractors has now been established with a comprehensive system of tracking contractors’ track record and verifying their levels of competence. It is envisaged that contractors appointed using this system will execute projects better.

2.2.5 Specification of measurable objectives and performance indicators

| Sub-Programme: Real Estate | Strategic Goal: Sustainable provincial building infrastructure to support service delivery |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Performance Measure | Actual 2004/05 | Actual 2005/06 | Estimate 2006/07 | Budget 2007/08 | Target 2008/09 | Target 2009/10 |
| Implementation of capital works projects within time lines, budget and quality in line with IDIP initiatives | Implementation of capital works projects | 100% implementation of Capital Works Projects | 100% implementation of Capital Works Projects | 100% implementation of Capital Works Projects | 100% implementation of Capital Works Projects | 100% implementation of Capital Works Projects | 100% implementation of Capital Works Projects | 100% implementation of Capital Works Projects |

2.3 SUB-PROGRAMME: REAL ESTATE

The sub-programme is responsible for the provision and management of immovable properties which serve as the platform for the efficient delivery of various government services.  It is also responsible for the provision of accommodation to departments.

2.3.1 Policies, Programme Objectives and Priorities

Policies

The Department has developed a draft policy in line with the White paper on Government-wide Immovable Asset Management to guide the management of the Provincial Property Portfolio including the acquisition and disposal of properties. In addition, the Department conducts activities in terms of the various legislation governing property matters, including: The National State Land Disposal Act, The Northern Province Land Administration Act and the Municipal Systems Act.

Programme Objectives

- Efficient management of immovable properties utilized for government service delivery

Priorities

The Sub-Programme will focus on the following priorities:

- Disposal of redundant properties

- Transfer of townships to municipalities

- Ownership of provincial properties

- Revenue optimisation

- Integrated district office accommodation plan

- Comprehensive reliable Provincial Asset Register

- Property investment

- Management of the prestige portfolio

- To continue with the Service Delivery Improvement (SDI) programme for cleaning, gardening and security.

2.3.2 Progress Analysis

While the arrear rental collection has been a course for concern to the Department and the Auditor-General, the sub-programme has thus far collected far better than the previous financial years due to the monitoring system that was employed. Most of the rent defaulters have entered into agreements with government to pay arrear rental through a stop order system after the due legal process. The sub-programme has completed the integrated office accommodation plan for head office departments which projects office needs for the next five years. A total of 129 of the 197 R293 towns have already been transferred to their respective municipalities.

2.3.3 Analysis of Constraints and Measures Planned to Overcome Them

The Sub-Programme is responsible for providing the provincial government with its property requirements and facilities management. This involves the renting, acquisition and disposal of properties, lease management of Government properties, registering of State-owned properties in the name of the Province, transfer of Provincial properties to Municipalities as well as the provision of cleaning, landscaping, gardening and security services.

The program faces huge challenges in the area of rental collection both in terms of rent-defaulters and a lack of capacity in rental collection management within the Department. The disposal programme is being hampered by the inability of preferred buyers to access finance as well as long-drawn-out legal processes to evict existing tenants. There is a lack of capacity within client Departments to manage their own respective leases with landlords. There is also a lack of capacity within the Department to monitor leases on behalf of client Departments. The programme also faces a challenge with regard to the updating of all the fields in the Provincial property asset register.

The programme will attempt to improve the collection of arrear rentals by dedicating staff to manage the rental collection. The programme will explore alternative ways of property disposal to preferred buyers. In addition, the programme will improve capacity within the Department to monitor the management of leases by client departments. The programme will continue to explore alternative methods to address the gaps in the Provincial property asset register.

2.3.4 Description of Planned Quality Improvement Measures

Following recommendations of our Service Delivery Improvement programme, the department has managed to improve its processes in the management of the Provincial properties and facilities, and in particular, further improvements were made to the security, cleaning, landscaping and gardening services. In order to effectively manage lease agreements, the Department will strengthen its systems to ensure timeous reporting of client accommodation requirements, lease renewals and terminations.

2.3.5 Specification of measurable objectives and performance indicators

| Sub-Programme: Real Estate |  | Strategic Goal: Efficient management of immovable property utilized for government service delivery |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective |  | Measurable Objective | Performance Measure | Actual 2004/05 | Actual 2005/06 | Estimate 2006/07 | Budget 2007/08 | Target 2008/09 | Target 2009/10 |
| Sustainable provincial building infrastructure to support service delivery | Management of immovable properties utilized for government service delivery |  | Disposal of redundant properties |  | 80 properties to be disposed | 80 properties to be disposed | 60 properties to be disposed | 60 properties to be disposed | 60 properties to be disposed |
|  |  |  | Transfer of towns to municipalities |  | 197 of R293 towns transferred to the relevant municipalities | 197 of R293 towns transferred to the relevant municipalities | 66 of R293 towns transferred to the relevant municipalities | 66 of R293 towns transferred to the relevant municipalities | 66 of R293 towns transferred to the relevant municipalities |
|  |  |  | Vesting of provincial properties |  | Vesting of 38 provincial properties | Vesting of 38 provincial properties | Vesting of 30 provincial properties | Vesting of 30 provincial properties | Vesting of 30 provincial properties |
|  |  |  | Development of Head Office and district offices plans |  | Development of provincial office accommodation plan | Integrated (Head Office) office accommodation plan | Integrated district office accommodation plan | Acquisition of offices | Acquisition of offices |
|  |  |  | Development and management of provincial asset register |  | Development and management of provincial asset register | Updating and management of provincial asset register | Updating and management of provincial asset register | Updating and management of provincial asset register | Updating and management of provincial asset register |
|  |  |  | Property investment |  | - | - | Property investment | Property investment | Property investment |
|  |  |  | Compilation of list of unutilized properties (land and buildings) |  | - | - | Compilation of list of unutilized properties (land and buildings) | Compilation of list of unutilized properties (land and buildings) | Compilation of list of unutilized properties (land and buildings) |
|  |  |  | Management of the Prestige Portfolio: Parliamentary Village, Premier’s Residence and Guest House |  | - | - | Management of the Prestige Portfolio: Parliamentary Village, Premier’s Residence and Guest House | Management of the Prestige Portfolio: Parliamentary Village, Premier’s Residence and Guest House | Management of the Prestige Portfolio: Parliamentary Village, Premier’s Residence and Guest House |

2.4 SUB-PROGRAMME: BUILDING MAINTENANCE

The sub-programme is responsible for the maintenance of government buildings, gardens and grounds under the Public Works portfolio. These include offices used by the Department in the execution of its service delivery mandates, prestige portfolio (Government complexes, the Parliamentary Village and Premier’s Residence) and residential accommodation which includes houses, flats and camps for workers. These building structures are generally old and some are in a state of disrepair due to lack of insufficient funding to render a planned preventative maintenance service. Unavailability of designs and plans for some of the buildings also creates problems with regard to problem diagnosis for maintenance purposes.

2.4.1 Policies, Programme Objectives and Priorities

Policies

Building and Maintenance is guided by the Occupational Health & Safety Act (OHS), Environmental Legislation, National Building Regulations (NBR), Construction Industry Development Board (CIDB) and other built-environment related Acts and regulations. The anticipated passing of the Government Immovable Assets Management Bill (GIAMA) will provide a more effective and collaborative way of asset management in government. The proposed bill places the obligation on accounting officers to develop Immovable Asset Management Plans for users and custodian. Maintenance as part of the asset management life cycle will be impacted by the passing of the Bill since there will be a need to develop a Custodian Asset Management Plan (CAMP) and the User Asset Management Plan (UAMP). The policy guidelines on the implementation of the Asset Management Plans as developed by the National Department of Public Works will help to facilitate implementation. In the meantime, the Department has developed maintenance policy which outlines and guides maintenance planning and execution for the Public Works Portfolio.

Programme Objectives

- Maintenance of government buildings for safe and reliable use in accordance with norms and standards

Priorities

The programme will focus on the following priorities:

- Using in-house building staff to construct and maintain the office and residential property portfolios

- Routine and preventative maintenance of buildings and facilities

- To render effective routine building maintenance services

2.4.2 Progress Analysis

The planned maintenance projects for 2006/07 were implemented and completed on time. The sub-programme had to also deal with urgent and unplanned maintenance works of other departments. Though successfully, this emergency work impacted negatively on the planned programme of work. Most of the client departments projects were executed timeously. A departmental maintenance policy has been developed and approved. A five year maintenance planned has been developed and approved. With the pending promulgation of GIAMA, the Department will put measures in place to ensure speedy its implementation in the Province.

2.4.3 Analysis of Constraints and Measures Planned to Overcome Them

One of the major challenges facing the Building programme over the previous years has been the lack of effective management control systems for internal building and maintenance teams. The lack of sufficient funding to address maintenance backlogs is a further challenge.     In order to address the lack of management control systems, the Department embarked on a programme of service delivery improvement during the financial year. This has led to the development of systems and processes that has resulted in a marked improvement in the output of the teams. These will be proceeded with in the coming year.

Lack of a comprehensive Asset Register and Integrated Buildings Management Systems creates challenges for assets maintenance and reporting. The need to improve the buildings to accommodate people with disabilities also poses a challenge since most of the old buildings were not designed to accommodate these requirements.

Ineffective service delivery has been identified as a weakness in the execution of maintenance activities.  Poor service delivery manifests itself in the long lead times in the execution of maintenance activities and poor work ethics. The sub-programme is also hampered by lack of skilled staff, high vacancy rates, ageing and sickly workforce. Lack of effective departmental recruitment and retention strategy also hampers the performance of the sub-programme.

The sub-programme is also faced with challenges in providing assistance to other provincial departments with regard to the maintenance of the buildings they individually occupy- such as schools, tribal offices, clinics, et cetera. The challenge stems from the fact that the Department gets called on an ad hoc basis to assist departments. The practice ultimately impacts on the planning and implementation of the maintenance programme for the Public Works Portfolio.

With the envisaged introduction of the Government Immovable Asset Management Bill (GIAMA), the organizational structure will require a review, new strategies need to be developed to accommodate additional mandate that the Department is required to execute as a custodian of government immovable assets. The incompleteness of the Immovable Asset Register will also create a challenge for the strategic plan period. The increase in the number of prestige accommodation will require additional capacity and budget during this period to ensure that a high level of maintenance is maintained which befits the status of this category of accommodation.

The Department currently has Cost Centres which are located in various municipal areas in the Province. There is a need to review the strategic intent that led to the existence of these Cost Centres. The sub-programme will engage in such a review.

The maintenance backlogs on the government complexes and the complaints received from clients residing in the prestige accommodation pose a challenge. The sub-programme will ensure that a new strategy is adopted for maintenance of this portfolio. The strategy will include the contracting out of certain specialised services such as Electrical, Electro- Mechanical, Plumbing and Landscaping. A team of dedicated personnel will be assembled to maintain this prestige portfolio.

In the light of the anticipated passing of the GIAMA, a comprehensive review of the programme structure will be required. This also calls for the development of the Provincial Maintenance Policy which will guide departments on maintenance of their portfolios.

The Maintenance Programme has been identified as a key driver of EPWP in the Department. This Program will also be used to implement the National Youth Service initiated by the National Department of Public Works and the National Youth Commission as pronounced in the President’s State of the Nation Address. The sub-programme will spend 30% of its budget to implement EPWP projects on refurbishment of the three government complexes in Giyani, Thohoyandou and Lebowakgomo.   The sub-programme will also participate in the National Youth Services Programme when implementing maintenance projects applying the principles of EPWP.

2.4.4 Description of Planned Quality Improvement Measures

As stated above, a large amount of the government buildings has not had sufficient planned and preventative maintenance for some time now. Central to the effective management of maintenance is the availability of a comprehensive Asset Register. In the absence of a comprehensive asset register, a risk exists that some assets will be excluded from maintenance planning. As a turn around strategy, the department has embarked on the compilation of a comprehensive Immovable Asset Register in 2006/07 financial year. The Register will go a long way in ensuring that a Buildings Maintenance Management System is developed and managed.

In order to address the lack of ineffective service delivery, the sub-programme will embarked on a programme of service delivery improvement during the financial year to ensure service improvement in line with the strategic objectives as set above. This will be realised through:

- Alignment of the Maintenance Policy Framework in line with the GIAMA and the National Infrastructure Maintenance Strategy. This will help in realising the vision of adequately maintained and operated infrastructure in support of sustained service delivery, growth and employment as envisaged by ASGISA.

- The use of Expanded Public Works elements in the implementation of the maintenance programme in order to support the Implementation of the National Youth Service in the Maintenance Programme.

  - Review of the organizational structure to cater for the added mandates dictated by the GIAMA Bill, National Infrastructure Maintenance Strategy and the creation for a Prestige Accommodation portfolio.

- Conducting annual maintenance requirement audits in order to develop maintenance plans in line with the departmental maintenance policy.

- Outsourcing of specialized maintenance work (electrical, mechanical and some grounds maintenance work for prestige portfolio)

- Implementing project based performance.

2.4.5 Specification of measurable objectives and performance indicators

| Sub-Programme: Building Maintenance | Strategic Goal: Maintenance of government buildings for safe and reliable use in accordance with norms and standards |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Performance Measure | Actual 2004/05 | Actual 2005/06 | Estimate 2006/07 | Budget 2007/08 | Target 2008/09 | Target 2009/10 |
| Maintenance of government buildings for safe and reliable use in accordance with norms and standards | Infrastructure maintenance plan in place and fully implemented | Maintenance plans implemented | Conduct audit on Lebowakgomo, Giyani and Thohoyandou government complexes | Conduct continuous inspections on all public works portfolio buildings and compile reports | Updating of the maintenance plan | Execution of the maintenance plan | Execution of the maintenance plan | Execution of the maintenance plan |
|  |  | Execute maintenance plan for government complexes | Develop a maintenance plan and schedule for the 3 government complexes | Implement the maintenance plan for the 3 government complexes | Finalize of implementation of maintenance plan in respect of public works portfolio | Execute maintenance plan for government complexes | Execute maintenance plan for government complexes | Execute maintenance plan for government complexes |
|  |  | Maintain gardens, landscapes and grounds: government, residential and offices |  |  |  | Maintain gardens, landscapes and grounds: government, residential and offices | Maintain gardens, landscapes and grounds: government, residential and offices | Maintain gardens, landscapes and grounds: government, residential and offices |
|  |  | Development of new hectare of landscaping: Parliamentary Village and residential accommodation |  |  |  | Development of new hectare of landscaping: Parliamentary Village and residential accommodation | Development of new hectare of landscaping: Parliamentary Village and residential accommodation | Development of new hectare of landscaping: Parliamentary Village and residential accommodation |
|  |  | Upgrading of Premier’s Residence |  |  |  | Upgrading of Premier’s Residence |  |  |
|  |  | Construction of MECs’ Houses |  |  | Construction of MECs’ Houses | Finalisation of MECs’ Houses | - | - |

2.5. RECONCILIATION OF BUDGET WITH PLAN

|  | Outcome |  |  | Main appropriation | Adjusted appropriation | Revised estimate | Medium-term estimates |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Audited | Audited | Audited |  |  |  |  |  |  |
| R thousand | 2003/04 | 2004/05 | 2005/06 | 2006/07 |  |  | 2007/08 | 2008/09 | 2009/10 |
| Subprogramme |  |  |  |  |  |  |  |  |  |
| Other Infrastructure | 237,088 | 243,180 | 308,231 |  |  |  |  |  |  |
| Project Management |  |  |  | 26,903 | 26,903 | 26,903 | 20,928 | 22,063 | 23,276 |
| Professional Services |  |  |  | 12,743 | 12,743 | 12,743 | 1,126 | 1,192 | 1,262 |
| Maintenance Management |  |  |  | 256,886 | 263,456 | 261,469 | 304,071 | 330,680 | 359,080 |
| Real Estate Management | 94,341 | 109,404 | 99,921 | 68,753 | 67,493 | 67,493 | 39,119 | 41,208 | 50,942 |
| Expanded Public Works Programme |  |  |  | 17,940 | 21,614 | 21,614 |  |  |  |
| Support Services |  |  |  | 4,005 | 4,005 | 4,005 | 2,763 | 2,928 | 4,103 |
| Total payments and estimates | 331,429 | 352,584 | 408,152 | 387,230 | 396,214 | 394,227 | 368,007 | 398,071 | 438,,663 |

Summary: Economic classification

|  | Outcome |  |  | Main appropriation | Adjusted appropriation | Revised estimate | Medium-term estimates |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Audited | Audited | Audited |  |  |  |  |  |  |
| R thousand | 2003/04 | 2004/05 | 2005/06 | 2006/07 |  |  | 2007/08 | 2008/09 | 2009/10 |
| Current payments | 293,962 | 295,363 | 302,188 | 287,764 | 291,455 | 292,112 | 276,493 | 302,622 | 338,918 |
| Compensation of employees | 241,355 | 240,014 | 241,756 | 229,479 | 232,696 | 234,062 | 234,711 | 259,043 | 293,379 |
| Goods and services | 52,607 | 55,349 | 60,418 | 58,285 | 58,744 | 58,035 | 41,767 | 43,563 | 45,523 |
| Interest and rent on land | - | - | 14 | - | 15 | 15 | 15 | 16 | 16 |
| Financial transactions in assets and liabilities | - | - | - | - | - | - | - | - | - |
| Unauthorised expenditure | - | - | - | - | - | - | - | - | - |
| Transfers and subsidies to: | - | 4,980 | 3,513 | 2,697 | 2,637 | 3,346 | 4,600 | 4,798 | 5,014 |
| Provinces and municipalities | - | 4,025 | 2,094 | 2,382 | 2,582 | 2,382 | 3,600 | 3,755 | 3,924 |
| Departmental agencies and accounts | - | - | - | - | - | - | - | - | - |
| Universities and technikons | - | - | - | - | - | - | - | - | - |
| Public corporations and private enterprises | - | - | - | - | - | - | - | - | - |
| Foreign governments and international organisations | - | - | - | - | - | - | - | - | - |
| Non-profit institutions | - | - | - | - | - | - | - | - | - |
| Households | - | 955 | 1,419 | 315 | 55 | 964 | 1,000 | 1,043 | 1,090 |
| Payments for capital assets | 37,467 | 52,241 | 102,451 | 96,769 | 102,122 | 98,769 | 86,914 | 90,651 | 94,731 |
| Buildings and other fixed structures | 10,897 | 48,883 | 97,506 | 77,061 | 76,248 | 72,361 | 80,814 | 84,289 | 88,082 |
| Machinery and equipment | 2,783 | 3,358 | 4,945 | 19,708 | 25,874 | 26,408 | 6,100 | 6,362 | 6,649 |
| Cultivated assets | - | - | - | - | - | - | - | - | - |
| Software and other intangible assets | - | - | - | - | - | - | - | - | - |
| Land and subsoil assets | 23,787 | - | - | - | - | - | - | - | - |
| Total economic classification | 331,429 | 352,584 | 408,152 | 387,230 | 396,214 | 394,227 | 368,007 | 398,071 | 438,663 |

3. PROGRAMME THREE: EXPANDED PUBLIC WORKS PROGRAMME

This programme is responsible for coordinating the Expanded Public Works Programme in the Province. This involves evaluating business plans, monitoring implementation, facilitating training and reporting progress on all EPWP programmes in the Province.

3.1 Policies, Programme Objectives and Priorities

Policies

The EPWP programme arose out of a national Cabinet decision and by a subsequent Provincial Executive Council decision which mandated Public Works to coordinate the implementation of EPWP in the Province.

Programme Objectives

- Job creation, skills transfer and poverty alleviation

Priorities

- Achievement of EPWP goals using DPW capital and maintenance budget

- A well-coordinated Provincial EPWP

- Monitoring and evaluation of EPWP implementation

3.2 Progress Analysis

The EPWP Programme has developed a draft Five Year EPWP Business Plan in 2006/07. Sector plans for the 4 sectors have also been completed and incorporated into the Business Plan.  There has been growing collaboration with the municipalities in using MIG funding to implement EPWP. The Provincial Executive Council has directed that provincial departments should ensure that they dedicate at least 30% of their infrastructure funding to EPWP.  Provincial EPWP steering committee has been established. Consultative meetings and workshops with Municipalities and Provincial departments are taking place.

3.3 Analysis of Constraints and Measures Planned to Overcome Them

Slow implementation of EPWP by municipalities and poor coordination of EPWP by implementing institutions.  The Department will continue with further engagements with municipalities through the MEC’s meetings with councillors responsible for EPWP. Coordination of EPWP will also be strengthened.  The Department will also use its ILO consultants to assist municipalities with identifying and planning EPWP projects.

3.4 Description of Planned Quality Improvement Measures

The development of outstanding sector guidelines needs to be finalised. There is also a need to raise the level of awareness around the EPWP concept, and to build capacity within the Province with regard to the implementation of the programme.  There is need for the introduction of monitoring and reporting mechanisms to measure the progress.

  - Specification of measurable objectives and performance indicators

| Sub-Programme: EPWP | Strategic Goal: Job Creation, Skills Transfer and Poverty Alleviation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Performance Measure | Actual 2004/05 | Actual 2005/06 | Estimate 2006/07 | Budget 2007/08 | Target 2008/09 | Target 2009/10 |
| Achievement of EPWP goals using Public Works capital and maintenance budgets | Job creation, skills transfer and poverty alleviation | Implementation of Public Works EPWP Programme (NYS Programme) |  |  |  | Implementation of Public Works EPWP Programme (NYS Programme) | Implementation of Public Works EPWP Programme (NYS Programme) | Implementation of Public Works EPWP Programme (NYS Programme) |
| A well coordinated Provincial EPWP | Provincial EPWP coordination | Coordinated intersectoral and departmental committees |  | Provincial EPWP coordination | Provincial EPWP coordination | Provincial EPWP coordination | rovincial EPWP coordination | Provincial EPWP coordination |
|  |  |  |  | Implementation of EPWP support | Implementation of EPWP support | Implementation of EPWP support | Implementation of EPWP support | Implementation of EPWP support |
|  |  |  |  | - | - | Development of sectoral norms and standards | Development of sectoral norms and standards | Development of sectoral norms and standards |
| Monitoring and evaluation of EPWP implementation | Monitored EPWP implementation | Quarterly reports |  | Monitoring of EPWP implementation |  | Monitoring of EPWP implementation | Monitoring of EPWP implementation | Monitoring of EPWP implementation |

3.6 RECONCILIATION OF BUDGET WITH PLAN

Programme 3: Expanded Public Works Programme

|  | Outcome |  |  | Main appropriation | Adjusted appropriation | Revised estimate | Medium-term estimates |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Audited | Audited | Audited |  |  |  |  |  |  |
| R thousand | 2003/04 | 2004/05 | 2005/06 | 2006/07 |  |  | 2007/08 | 2008/09 | 2009/10 |
| Subprogramme |  |  |  |  |  |  |  |  |  |
| Expanded Public Works Program | 5,000 |  |  | - | - |  | 21,653 | 24,506 | 28,811 |
| Training Programmes |  |  |  |  |  |  |  |  |  |
| Empowerment Impact Assessment |  |  |  |  |  |  |  |  |  |
| Poverty Eradication |  |  |  |  |  |  |  |  |  |
| Emerging Contractor Development |  |  |  |  |  |  |  |  |  |
| Total payments and estimates | 5,000 | - | - | - | - | - | 21,653 | 24,506 | 28,811 |

Summary : Economic classification

|  | Outcome |  |  | Main appropriation | Adjusted appropriation | Revised estimate | Medium-term estimates |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Audited | Audited | Audited |  |  |  |  |  |  |
| R thousand | 2003/04 | 2004/05 | 2005/06 | 2006/07 |  |  | 2007/08 | 2008/09 | 2009/10 |
| Current payments | - | - | - | - | - | - | 20,153 | 22,941 | 27,176 |
| Compensation of employees | - | - | - | - | - | - | 11,121 | 13,521 | 17,332 |
| Goods and services | - | - | - | - | - | - | 9,032 | 9,420 | 9,844 |
| Interest and rent on land | - | - | - | - | - | - | - | - | - |
| Financial transactions in assets and liabilities | - | - | - | - | - | - | - | - | - |
| Unauthorised expenditure | - | - | - | - | - | - | - | - | - |
| Transfers and subsidies to: | - | - | - | - | - | - | - | - | - |
| Provinces and municipalities | - | - | - | - | - | - | - | - | - |
| Departmental agencies and accounts | - | - | - | - | - | - | - | - | - |
| Universities and technikons | - | - | - | - | - | - | - | - | - |
| Public corporations and private enterprises | - | - | - | - | - | - | - | - | - |
| Foreign governments and international organisations | - | - | - | - | - | - | - | - | - |
| Non-profit institutions | - | - | - | - | - | - | - | - | - |
| Households | - | - | - | - | - | - | - | - | - |
| Payments for capital assets | 5,000 | - | - | - | - | - | - | - | - |
| Buildings and other fixed structures | 5,000 | - | - | - | - | - | - | - | - |
| Machinery and equipment | - | - | - | - | - | - | 1,500 | 1,565 | 1,635 |
| Cultivated assets | - | - | - | - | - | - | - | - | - |
| Software and other intangible assets | - | - | - | - | - | - | - | - | - |
| Land and subsoil assets | - | - | - | - | - | - | - | - | - |
| Total economic classification | 5,000 | - | - | - | - | - | 21,653 | 24,506 | 28,811 |

4. IMPLEMENTATION OF THE CAPITAL INVESTMENT, MAINTENANCE AND ASSET MANAGEMENT PLAN

Summary of payments and estimates

|  | Outcome |  |  | Main appropriation | Adjusted appropriation | Revised estimate | Medium-term estimates |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Audited | Audited | Audited |  |  |  |  |  |  |
| R thousand | 2003/04 | 2004/05 | 2005/06 | 2006/07 |  |  | 2007/08 | 2008/09 | 2009/10 |
| Programme 1: Administration1 | 156,560 | 163,421 | 159,947 | 201,689 | 207,669 | 209,656 | 211,938 | 225,980 | 241,194 |
| Programme 2: Public Works | 331,429 | 352,584 | 408,152 | 387,230 | 396,214 | 394,227 | 368,007 | 398,071 | 438,663 |
| Programme 3: Expanded Public Works Programme | 5,000 | - | - | - | - | - | 21,653 | 24,506 | 28,811 |
| Total payments and estimates | 492,989 | 516,005 | 568,099 | 588,919 | 603,883 | 603,883 | 601,598 | 648,557 | 708,668 |

Summary: Economic classification

|  | Outcome |  |  | Main appropriation | Adjusted appropriation | Revised estimate | Medium-term estimates |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Audited | Audited | Audited |  |  |  |  |  |  |
| R thousand | 2003/04 | 2004/05 | 2005/06 | 2006/07 |  |  | 2007/08 | 2008/09 | 2009/10 |
| Current payments | 433,552 | 433,053 | 440,183 | 471,105 | 476,319 | 479,243 | 496,084 | 538,506 | 593,664 |
| Compensation of employees | 325,679 | 328,331 | 323,296 | 344,077 | 351,203 | 354,556 | 364,776 | 401,550 | 450,545 |
| Goods and services | 107,873 | 104,722 | 116,873 | 127,028 | 125,101 | 124,672 | 131,293 | 136,940 | 143,103 |
| Interest and rent on land | - | - | 14 | - | 15 | 15 | 15 | 16 | 16 |
| Financial transactions in assets and liabilities | - | - | - | - | - | - | - | - | - |
| Unauthorised expenditure | - | - | - | - | - | - | - | - | - |
|  | - | - | - | - | - | - | - | - | - |
| Transfers and subsidies to: | - | 13,015 | 5,723 | 5,384 | 5,269 | 5,698 | 6,600 | 6,884 | 7,194 |
| Provinces and municipalities | - | 4,260 | 2,326 | 2,764 | 2,729 | 2,529 | 4,100 | 4,277 | 4,469 |
| Departmental agencies and accounts | - | - | - | - | - | - | - | - | - |
| Universities and technikons | - | - | - | - | - | - | - | - | - |
| Public corporations and private enterprises | - | - | - | - | - | - | - | - | - |
| Foreign governments and international organisations |  |  |  |  |  |  |  |  |  |
| Non-profit institutions | - | - | - | - | - | - | - | - | - |
| Households | - | 8,755 | 3,397 | 2,620 | 2,540 | 3,169 | 2,500 | 2,607 | 2,725 |
|  | - | - | - | - | - | - | - | - | - |
| Payments for capital assets | 59,437 | 69,937 | 122,193 | 112,430 | 122,295 | 118,942 | 98,914 | 103,167 | 107,810 |
| Buildings and other fixed structures | 15,897 | 48,883 | 97,506 | 77,061 | 76,248 | 72,361 | 80,814 | 84,289 | 88,082 |
| Machinery and equipment | 19,753 | 21,054 | 24,687 | 35,369 | 46,047 | 46,581 | 18,100 | 18,878 | 19,728 |
| Cultivated assets | - | - | - | - | - | - | - | - | - |
| Software and other intangible assets | - | - | - | - | - | - | - | - | - |
| Land and subsoil assets | 23,787 | - | - | - | - | - | - | - | - |
| Total economic classification | 492,989 | 516,005 | 568,099 | 588,919 | 603,883 | 603,883 | 601,598 | 648,557 | 708,668 |

5. MEDIUM –TERM REVENUE

5.1 Summary of Revenue

Revenue Budget

|  | Outcome |  |  | Main appropriation | Adjusted appropriation | Revised estimate | Medium-term estimates |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Audited | Audited | Audited |  |  |  |  |  |  |
| R thousand | 2003/04 | 2004/05 | 2005/06 | 2006/07 |  |  | 2007/08 | 2008/09 | 2009/10 |
| Tax receipts | - | - | - | - | - | - | - | - | - |
| Non-tax receipts | 5,267 | 12,115 | 18,425 | 9,871 | 20,566 | 17,258 | 23,124 | 26,074 | 29,399 |
| Sale of goods and services other than capital assets | 5,169 | 12,091 | 18,400 | 9,844 | 20,481 | 17,156 | 23,028 | 25,966 | 29,277 |
| Fines, penalties and forfeits | 98 | - | - | - | - | - | - | - | - |
| Interest, dividends and rent on land | - | 24 | 25 | 27 | 85 | 102 | 96 | 108 | 122 |
| Transfers received | - | - | - | - | - | - | - | - | - |
| Sale of capital assets | 7,036 | 2,000 | 2,600 | - | 447 | 3,798 | 504 | 568 | 641 |
| Financial transactions | - | 9 | 173 | 5 | 57 | 1,366 | 65 | 73 | 82 |
| Total departmental receipts | 12,303 | 14,124 | 21,198 | 9,876 | 21,070 | 22,422 | 23,693 | 26,715 | 30,122 |

5.2 Conditional Grants

The department of Public Works does not receive any conditional grants

5.3 Donor Funding

The department of Public Works does not receive any form of donor funding

6. CO-ORDINATION, CO-OPERATION AND OUTSOURCING PLANS

6.1 Interdepartmental Linkages

There is a good linkage with other departments, particularly because Department of Public Works is an Implementing agent of Capital projects

Of Departments such as Education and Health

6.2 Local Government Linkages

The Department attends IDP meetings to ensure Integrated Planning. Departmental Annual Plan is developed and informed by

Municipal Plans

6.3 Public Entities

Department of Public Works is not responsible for any public entities

6.4 Public, Private Partnerships, Outsourcing etc

The Department has no PPP project.

7. FINANCIAL MANAGMENT

7.1 Strategies to Address Audit Queries

7.2 Implementation of PFMA

PART C: ANNUAL PERFORMANCE PLAN 2007-2008

SUB-PROGRAMME: MEC’S OFFICE

| Strategic Goal | Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable Objectives | Performance Measure | Target | Budget | Quarter 1 | Quarter 2 | Quarter3 | Quarter 4 |
| Implementation of service delivery improvement programme | Coordinated executive support service | Holding of Stakeholder meetings | Hold 8 Imbizo Meetings | R1 800 000 | 2 Imbizo Meetings R150 000 | 2 Imbizo Meetings R280 000 | 2 Imbizo Meetings R300 000 | 2 Imbizo Meetings R200 000 |
|  |  |  | Hold 2 District Visits |  | District Visit to Vhembe and Capricorn |  |  |  |
|  |  |  | Hold 4 Meetings with councilors responsible for EPWP |  | One Meeting with councilors responsible for EPWP R70 000 | One Meeting with councilors responsible for EPWP R80 000 | One Meeting with councilors responsible for EPWP R90 000 | One Meeting with councilors responsible for EPWP |
|  |  |  | Hold 3 consultative meetings with critical stakeholders |  |  | One Consultative Meeting with Built-Environment Professional Institutions | One Consultative Meeting with Contractors | One Consultative Meeting with Material Suppliers |
|  |  |  | Address 3 Conferences |  | Address Youth in Construction Conference R180 000 | Address Women in Construction Conference R250 000 | Address Contractor Award Conference R200 000 |  |
|  |  | Handover of completed projects to client departments | Handover of 8 projects to client departments | R0 | Handover 2 projects to client departments | Handover 2 projects to client departments | Handover 2 projects to client departments | Handover 2 projects to client departments |
|  | Coordinated Parliamentary Service | Coordinate Parliamentary Service | Coordinate submission of 4 Quarterly Reports to Portfolio Committee | R0 | Quarterly Progress Report to Portfolio Committee | Quarterly Progress Report to Portfolio Committee | Quarterly Progress Report to Portfolio Committee | Quarterly Progress Report to Portfolio Committee |
|  |  |  | Preparation and Tabling of Budget Speech | R0 |  |  | Preparation of Draft Budget Speech | Budget Speech |

SUB-PROGRAMME: STRATEGIC HUMAN RESOURCE MANAGEMENT

| Strategic Goal | Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable Objectives | Performance Measure indicator | Target | 2007/2008 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Implement human resource development programme | Implementation of workplace skills plan | Implementation of skills programme to employees | 530 employees | R 2 500 000 | 133 employees R625 000 | 133 Employees R625 000 | 132 Employees R625 000 | 132 Employees R625 000 |
|  |  | Awarding 170 bursaries for serving employees | 170 employees | R1 000 000 |  | 1st payment for 85 employees R500 000 |  | Final payment for 85 employees R500 000 |
|  |  | Awarding 78 bursaries for external students | 78 external students | R1 500 000 | Enrolment of 78 learners | First payment for 39 students R750 000 |  | Final payment for 39 students R750 000 |
|  |  | Awarding 247 learnerships to external learners | 247 external learners | R3 000 000 | Enrolment of 247 learners R3 000 000 |  |  |  |
|  |  | Award 97 learnerships to serving employees | 97 learnerships | R1 000 000 | Enrolment of learners R1 000 000 |  |  |  |
|  |  | Implement Internship Programme | 89 Interns | R0 | Enroll 89 interns |  |  |  |
|  |  | Implementation of Emerging Contractor Development | Enrolling 40 contractors | R0 (DOL funding) | Develop funding proposal | Advertisement and recruitment |  |  |
|  | Alignment of the organisational structure to the strategic plan | Finalised and aligned organizational structure | Finalised and aligned organizational structure | R500 000 | Finalise and align organizational structure R500 000 |  |  |  |
|  | Recruitment of staff | % of posts filled in the organogram | 100% filling of vacant posts | R3 264 000 | 50% of critical posts filled | 00% of critical vacant posts R3 264 000 |  |  |
| Improved health and psyco-social functioning of staff | Implementation of an integrated Employee Wellness Program (Incl. HIV/AIDS) | Promote awareness on the use of the Programme | Hold 12 workshops to promote awareness on the use of the Programme | R2 000 000 | Hold 3 awareness Workshops R525 000 | Hold 3 awareness Workshops R525 000 | Hold 3 awareness Workshops R375 000 | Hold 3 awareness Workshops R575 000 |
| Implementation of Occupational Health and Safety Programme | Improved work environment | Implementation of a Workplace Relations Programme | Implementation and reporting on Occupational Health and Safety Programme | R0 | Implement Occupational Health and Safety Programme Produce quarterly report | Implement Occupational Health and Safety Programme Produce quarterly report | Implement Occupational Health and Safety Programme Produce quarterly report | Implement Occupational Health and Safety Programme Produce quarterly report |
| Implementation of Performance Management System | Performance improvement | Meeting performance goals and targets | Implement Performance Management policy and produce quarterly reports | R0 | Implement Performance Management policy Produce quarterly report | Implement Performance Management policy Produce quarterly report | Implement Performance Management policy Produce quarterly report | Implement Performance Management policy Produce quarterly report |

EXECUTIVE PROGRAMME: STRATEGIC FINANCE

| Strategic Goal | Improved Service Delivery and Good Corporate Governance Promotion of Broad Based Black Economic Empowerment |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable Objectives | Performance Measure indicator | Target | 2007/2008 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Optimum financial management | Optimum budget management | 100% revenue collected within the tolerance level of 2% | R23 000 000 collected | R0 | R5 750 000 To be collected | R5 750 000 To be collected | R5 750 000 To be collected | R5 750 000 To be collected |
|  | Optimum revenue collection | 100% budget expenditure within the tolerance level of 2% | R601 598 000 spent | R0 | 25% budget spent | 25% budget spent | 25% budget spent | 25% budget spent |
| Implementation of appropriate procurement and provisioning system which is fair, equitable, transparent, competitive and cost effective | Maintenance of an appropriate procurement and provisioning system which is fair, equitable, transparent, competitive and cost effective | Implementation of Supply Chain Management policy | Development of standards and map processes including holding of 11 workshops Ensure compliance with SCM | R300 000 | Develop standards and map processes On SCM Conduct 6 workshops on SCM – Internal clients Enforce compliance with SCM | Conduct 5 workshops on SCM – External clients Enforce compliance with SCM R100 000 | Compile 6 reports on workshops Enforce compliance with SCM R100 000 | Assess the impact and compile 6 reports Enforce compliance with SCM R100 000 |
|  |  |  | Training of 40 officials on SCM |  | Train 10 officials | Train 10 officials | Train 10 officials | Train 10 officials |
|  |  |  | Development of strategy and implementation plan on BBBEE |  | Develop strategy on BBBEE | Implement BBBEE | Implement BBBEE | Implement BBBEE |
| Implementation of effective, efficient and transparent systems of financial management, risk management and internal control | Optimum Risk Management | Implementation of risk and fraud prevention plans | Conduct 20 risk and fraud prevention awareness campaigns | R340 000 | 5 campaigns conducted | 5 campaigns conducted R120 000 | 5 campaigns conducted R120 000 | 5 campaigns conducted R100 000 |
|  |  |  | Compilation of 4 quarterly risk management reports | R0 | Quarterly Risk Management Report | Quarterly Risk Management Report | Quarterly Risk Management Report | Quarterly Risk Management Report |
|  |  |  | Compilation of 4 quarterly security assessment and audits reports | R0 | Quarterly security assessment and audit report | Quarterly security assessment and audit report | Quarterly security assessment and audit report | Quarterly security assessment and audit report |
| Implementation of Minimum Information Security System (MISS) | Secure information | Implementation of Minimum Information Security System (MISS) | Implementation of Minimum Information Security System (MISS) | R0 | Implementation of Minimum Information Security System (MISS) | Implementation of Minimum Information Security System (MISS) | Implementation of Minimum Information Security System (MISS) | Implementation of Minimum Information Security System (MISS) |

EXECUTIVE PROGRAMME:  CORPORATE SERVICES

| Strategic Goal | Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable objectives | Performance measure Indicator | Target | 2007/08 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Implementation of service delivery improvement programme | Proper utilization of movable physical resources | Purchase of 64 vehicles | 64 vehicles | R4 500 000 |  | Prepare and place purchase order for the acquisition of 64 vehicles. | Delivery of 32 vehicles and effect payment of R2 200 000 | Delivery of 32 Vehicles and effect payment of R2 300 000 |
|  |  | Maintenance of 301 vehicles | 301 vehicles | R6 500 000 | Payment of maintenance for 301 Vehicles R1 625 000 | Payment of maintenance for 301 Vehicles R1 625 000 | Payment of maintenance for 301 Vehicles R1 625 000 | Payment of maintenance for 301 Vehicles R1 625 000 |
|  |  | Lease and maintenance of 52 photocopiers | 52 photocopiers | R2 600 000 | Payment for leased photocopiers R650 000 | Payment for leased photocopiers R650 000 | Payment for leased photocopiers R650 000 | Payment for leased photocopiers R650 000 |
|  |  | Purchase of office equipment and office furniture | Spend R1.9 M on purchase of office furniture and office equipment | R1 900 000 | Purchase of office furniture and equipment R475 000 | Purchase of office furniture and equipment R475 000 | Purchase of office furniture and equipment R475 000 | Purchase of office furniture and equipment R475 000 |
|  |  | Stationery and printing | Spend R4.1 M on Stationery and printing | R4 100 000 | Payment of R1 025 000 for stationery purchased | Payment of R1 025 000 for stationery purchased | Payment of R1 025 000 for stationery purchased | Payment of R1 025 000 for stationery purchased |
|  |  | Management of telecommunication systems | Spend R6,5 M on the management of telecommunication systems | R6 500 000 | Payment for telecommunication expenses R1 625 000 | Payment for telecommunication expenses R1 625 000 | Payment for telecommunication expenses R1 625 000 | Payment for telecommunication expenses R1 625 000 |
|  | Provision of logistical facilities for Departmental functions | Preparation for Departmental events | Spend R8 M on Departmental events | R8 000 000 | Payment for hotel accommodation, car rental and flights R2 000 000 | Payment for hotel accommodation, car rental and flights R2 000 000 | Payment for hotel accommodation, car rental and flights R2 000 000 | Payment for hotel accommodation, car rental and flights R2 000 000 |
|  | Provision of clean, safe and secure environment | Provision of security and cleaning services | Provision of security and cleaning services | R13 000 000 | Payment of security and cleaning services | Payment of security and cleaning services | Payment of security and cleaning services | Payment of security and cleaning services |
|  |  | Installation of access control system and CCTV camera | Installation of access control system and CCTV camera |  | Installation of access control system and CCTV camera at Head Office | Maintenance of access control system and CCTV camera at Head Office | Maintenance of access control system and CCTV camera at Head Office | Maintenance of access control system and CCTV camera at Head Office |
|  |  | Installation of Guard Monitoring System | Installation of Guard Monitoring System |  | Installation of Guard Monitoring System | Maintenance of Guard Monitoring System at Head Office | Maintenance of Guard Monitoring System at Head Office | Maintenance of Guard Monitoring System at Head Office |
|  |  |  |  |  | R 4 000 000 | R 3 000 000 | R 3 000 000 | R 3 000 000 |
|  | Implementation of compliance measures to OHS Act | Adequate provision of protective clothing | Spend R1,3 M on purchase of protective clothing | R1 300 000 | Place purchase orders for protective clothing | Payment for protective clothing R650 000 | Payment for protective clothing R650 000 |  |

EXECUTIVE PROGRAMME: GOVERNMENT INFORMATION TECHNOLOGY SERVICES

| Strategic Goal | Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable objectives | Performance Measure Indicator | Target | Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Implementation of service delivery improvement programme | Implementation of MSP projects | Number of sites with functional network infrastructure | 8 sites with functional network infrastructure | R1 000 000 | Establish infrastructure in three sites R300 000 | Establish infrastructure in two sites R300 000 | Establish infrastructure in three sites R300 000 | Maintain and monitor network. R100 000 |
|  |  |  |  | R3 000 000 | Assessment and design of VPN | 50% Implementation of VPN 1 500 000 | 50% Implement VPN R1 500 000 | Monitor |
|  |  | % Implementation of DRP project | 100% implementation of DRP project | R800 000 | Design DRP site R250 000 | 50% Implementation of DRP R250 000 | 50% Implement DRP R300 000 | Review DRP |
|  |  | % implementation of GIS | 100% implementation of GIS project | R500 000 | 50% implementation of project R250 000 | 50% implementation of project R250 000 | Managing and updating of GIS datasets | Managing and updating of GIS datasets |
|  |  | % implementation of Website and Intranet | 100% development of website and intranet | R500 000 | Development website R250 000 | Development intranet R250 000 | Maintenance of Internet and Website | Maintenance of Internet and Website |
|  |  | Infrastructure management information Systems (Project, Fleet, Performance, Maintenance, Asset) | Acquisition of Infrastructure Management Information Systems | R2 000 000 | Develop user requirements and acquire system R500 000 | Implementation of IMIS R500 000 | Implementation of IMIS R500 000 | Implementation of IMIS R500 000 |
|  |  | Payment of software licenses | Payment of R1,7 m for software licences | R1 700 000 | - | - | Payment of licences R1 700 000 | - |
|  |  | Number of SLA maintained | Spend R2 m on the management of SLA | R2 000 000 | Management of SLA performance R500 000 | Management of SLA performance R500 000 | Management of SLA performance R500 000 | Management of SLA performance R500 000 |
|  | Provision of information and records management services | Implementation of IM strategy projects Information, records and knowledge management awareness | Holding of 5 awareness sessions | R300 000 | One Awareness session at Head Office and Capricorn R300 000 | Two Awareness sessions at Sekhukhune and Waterberg Districts | Two Awareness sessions at Mopani and Vhembe | Survey of impact of sessions in HO and districts |
|  |  | Functional Resource Centre | Acquisition of library materials | R150 000 | Acquisition of library materials R150 000 | Monitoring of library and information service. 60% usage | Monitoring of library and information service. 65% usage | Monitoring of library and information service. 75% usage |
|  |  | Implementation of Promotion to Access of Information Act | Translation and printing of the manual into Afrikaans and the production of Braille | R150 000 | Translate & print manual into Afrikaans and produce in Braille R150 000 | Management of all PAIA requests | Management of all PAIA requests | Submission of Section 15 and 32 PAIA reports |
|  |  | Effective and efficient messenger and postal services | Spend R150 000 on management of incoming and outgoing registers | R150 000 | Management of outgoing and incoming registers R50 000 | Management of outgoing and incoming registers R100 000 | Management of outgoing and incoming registers | Management of outgoing and incoming registers |
|  |  | Development of information architecture | Acquisition of information architecture and 100% implementation | R450 000 | Acquisition and 10% Implementation | 40% Implementation R250 000 | 40% Implementation R200 000 | 10% Implementation |
|  |  | Development of a records management system (centralization and digitisation) | Acquisition and 100% implementation of records management system | R1 500 000 | Acquisition and 20% Implementation R500 000 | 50% Implementation R500 000 | 20% Implementation R500 000 | 10% Implementation |
| Enhance and strengthen internal and external communications | Implement ion of the communication strategy | Implementation of corporate communication | Production of monthly and quarterly Departmental publications | R2 000 000 | Produce Departmental publications as per requirements (photography, advertising, monthly and quarterly newsletters) R500 000 | Produce Departmental publications as per requirements (annual report, citizen’s report, brochures, monthly and quarterly newsletters) R500 000 | Produce Departmental publications as per requirements (season’s greetings, newsletters, advertising, monthly and quarterly photography) R500 000 | Produce Departmental publications as per requirements (Diaries and calendars, monthly and quarterly newsletters) R500 000 |
|  |  | Implementation of corporate identity/ Marketing programme | Implementation of corporate identity / marketing programme | R2 500 000 | Manage campaigns and events, internal and external communication District visits, Candle lighting memorial service, EPWP Learners workshops | Manage campaigns and events, internal and external communication National Construction week, Women in construction, Departmental women’s day, Heritage month | Manage campaigns and events, internal and external communication. District visits, Disability day, 16 days of activism | Manage campaigns and events, internal and external communication. Budget speech, Excellence awards, Public participation on supply chain |
|  |  |  | Exhibitions in all Department activities |  | Exhibitions in all Departmental activities. | Exhibitions in all Departmental activities. Career exhibition | Exhibitions in all Departmental activities. Batho Pele Day | Exhibitions in all Departmental activities |
|  |  |  | Promotion of corporate identity and acquisition of corporate gifts |  | Promotion of corporate identity and acquisition of corporate gifts | Promotion of corporate identity and acquisition of corporate gifts | Promotion of corporate identity and acquisition of corporate gifts | Promotion of corporate identity and acquisition of corporate gifts |
|  |  |  |  |  | R500 000 | R500 000 | R1 000 000 | R500 000 |
|  |  | Media and Research | Media scans Media release Research Media briefings | R0 | Media scans Media release Research Media briefings | Media scans Media release Research Media briefings | Media scans Media release Research Media briefings | Media scans Media release Research Media briefings |
|  |  | Stakeholder management | Implement one public participation session, imbizo, EXCO meets the people, MEC meets the people, project launches, MEC’s consultative meetings with stakeholders | R0 | Implement one public participation session, imbizo, EXCO meets the people, MEC meets the people, project launches, MEC’s consultative meetings with stakeholders | Implement one public participation session, imbizo, EXCO meets the people, MEC meets the people, project launches | Implement one public participation session, imbizo, EXCO meets the people, MEC meets the people, project launches | Implement one public participation session, imbizo, EXCO meets the people, MEC meets the people, project launches |

EXECUTIVE PROGRAMME: STRATEGIC MANAGEMENT

| Strategic Goal | Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable Objectives | Performance Measure indicator | Target | 2007/2008 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Implementation of service delivery improvement programme | Implementation of service delivery improvement programme | Implementation of service delivery improvement programme | 4 quarterly reports on implementation of SDIP projects | R0 | Implement SDIP projects | Implement SDIP projects | Implement SDIP projects | Review of SDIP and draft SDIP for 2008/09 |
|  |  | Compilation of Annual Report on learning and sharing of information on innovative ways of performing tasks |  | R0 | Compilation of Annual Report on learning and sharing of information on innovative ways of performing tasks |  |  |  |
|  |  | Establishment of Service Delivery Improvement Unit to drive learning and innovation |  | R0 |  | Establishment of Service Delivery Improvement Unit to drive learning and innovation |  |  |
|  |  | Development and implementation of Departmental Awards | 4 quarterly reports on implementation of Departmental Awards | R150 000 | Develop and implement Departmental Awards | Implement Departmental Awards | Implement Departmental Awards R150 000 | Hold Departmental Awards Ceremony |
|  |  | Development and implementation of Contractor Awards | 4 quarterly reports on implementation of Contractor Awards | R300 000 | Develop and implement Contractor Awards | implement Contractor Awards | implement Contractor Awards R300 000 | Hold Contractor Awards Ceremony |
|  | Implementation of Special Programmes | Implementation of Special Programmes | Spend R400 000 on Special Programmes | R400 000 | Facilitate participation in the provincial and National activities. Take a girl child to work ceremony R25 000 | Facilitate participation in the provincial and National activities. Youth Day celebration R75 000 | Women in construction conference R150 000 | Review special programmes to empower youth, women and people with disability |
|  |  |  |  |  |  |  | Facilitate participation in the Provincial and National activities. Disability Day R150 000 | Develop a programme of action for 2008/09 |
|  | Implementation of Batho Pele | Implementation of Batho Pele Programmes | Spend R600 000 on the implementation of Batho Pele Programme | R600 000 | Conduct customer satisfaction survey at Head Office | Conduct customer satisfaction survey in Capricorn, Waterberg and Sekhukhune | Conduct customer satisfaction survey in Vhembe and Mopani | Evaluation Report on implementation of Batho Pele Programmes Prepare Batho Pele programme and projects for 2008/09 |
|  |  |  |  |  |  | Facilitate participation in the provincial and national activities. Public Service Week R300 00 | Batho Pele Day celebration Production of Citizens Report R300 000 |  |
|  | Implementation of coordinated strategic management | Strategic interventions to support core functions of the Department | Quarterly reports , 2008/09 revised plans and an established monitoring and evaluation framework | R200 000 | Develop a monitoring and evaluation framework to track performance and implementation of the strategic plan and the annual performance plan R50 000 |  | Convene mid-year strategic planning review session to incorporate mid-term priority reviews. | Finalise the revised strategic plan and annual performance plan for 2008/09 and publish it R150 000 |
|  |  |  |  |  | Prepare quarterly Departmental Performance Report | Prepare quarterly Departmental Performance Report | Prepare quarterly Departmental Performance Report | Prepare quarterly Departmental Performance Report |
|  | Implementation of the Inter-governmental Relations Framework (IGR) | Implementation of the Inter-governmental Relations Framework (IGR) | Alignment of Departmental plans with municipal IDPS | R0 | Verify plans for alignment to IDP’S | Participate in various municipal forums | Participate in various municipal forums | Coordinate submission of approved plans to District municipalities for 2008/09 |
|  | Coordination of regional integration programmes in line with PGDS objectives | Learning and information sharing with neighbouring states on Public Works functions | Learning and information sharing with neighbouring states on Public Works functions | R0 | Learning and information sharing with neighbouring states on Public Works functions | Learning and information sharing with neighbouring states on Public Works functions | Learning and information sharing with neighbouring states on Public Works functions | Learning and information sharing with neighbouring states on Public Works functions |

EXECUTIVE PROGRAMME: PROFESSIONAL SERVICES

| - Strategic Goal | Sustainable provincial building infrastructure to support service delivery |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Strategic Objectives | - Measurable Objectives | - Performance measure / Targets | - 2007 / 08 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| - Implementation of capital works projects within time lines, budget and quality in line with IDIP initiatives | - Development and implementation of a project planning implementation plan | - 100% implementation of Capital Works Projects | - R0 | - Develop a project planning implementation plan | - Implement project planning implementation plan | - Implement project planning implementation plan | - Implement project planning implementation plan |
|  | - Coordination of Provincial infrastructure delivery through the 2010 Soccer World Cup infrastructure | - Coordinated Provincial infrastructure delivery through the 2010 Soccer World Cup infrastructure | - R0 | - Quarterly report | - Quarterly report | - Quarterly report | - Quarterly report |
|  | - Updated norms and standards | - Research and development of norms and standards | - R0 | - Undertake research on norms and standards | - Develop norms and standards |  |  |

EXECUTIVE PROGRAMME: PROJECT MANAGEMENT

| - Strategic Goal | Sustainable provincial building infrastructure to support service delivery |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Strategic Objectives | - Measurable Objectives | - Performance indicators / Targets | - 2007 / 08 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| - Implementation of capital works projects within time lines, budget and quality in line with IDIP initiatives | - Implementation of capital works projects | - 100% implementation of Capital Works Projects |  | -Handover of project sites to contractors. Target 100% - -Supervision & monitoring of progress. expected average progress 35% target | Supervision and Monitoring of progress. 65% progress expected on projects handed over | Supervision and Monitoring of progress. 100% progress expected on projects handed over | Commissioning projects for Payment of retention monies. - Preparation of bid document for new projects Evaluation of bids for coming financial year. |
|  |  | Education Projects - Old Projects - 1. Completion of 95 Schools under Trees and in shacks | R31 270 000 | Completion of : 95 Schools under trees and in schacks-100% | Payment of retention and final accounts -Schools under trees and in shacks- |  |  |
|  |  | - 2. Completion of 239 Storm Damaged Schools | R117 515 000 | Completion of 239 Storm damaged Schools | Payment of retention and final accounts - Storm damaged Schools - |  |  |
|  |  | - New Projects - 1. Construction of 91 Condemned Schools Phase 1 | R96 000 000 | 91 Condemned Schools phase 1 On average 85% of the projects completed | 100% (91) schools completed | Payment of retention and final accounts |  |
|  |  | - 2. Construction of 88 Condemned Schools Phase 2 | R55 000 000 | 88 Condemned Schools Phase 2 On average 85% of the projects completed | 100% ( 88) schools completed | Payment of retention and final accounts |  |
|  |  | - 3. Construction of 4 Cross Boundary Schools | - R6 000 000 | - 4 Cross boundary Schools On average 85% of the projects completed | 100% (4) schools completed | Payment of retention and final accounts |  |
|  |  | - 4. Refurbishment of DoE Head Office | R9 000 000 | Refurbishment of DoE Head Office Site hand over , 35% of refurbishment complete | 65% of refurbishment of work complete | 100% of refurbishment of work complete | Payment of retention and final accounts |
|  |  | - 5. Refurbishment of 2 x Multipurpose Centres | R10 000 000 | Refurbishment of 2x Multipurpose Centers Site hand over. 85% of work done. | 60% of refurbishment of work complete | 100% of refurbishment of work complete | Payment of retention and final accounts |
|  |  | - Department of Health & Social Development - Multi-Year Projects - 1. Completion of 33 Clinics | R20 000 000 | Final inspection, release retention and close the project. 100% target. |  |  |  |
|  |  | 2. Completion of 20 Clinics | R36 000 000 | Final inspection, release retention and close the project. 100% target. |  |  |  |
|  |  | 3. Completion of 2 Health Centres | R25 100 000 | Continuation of monitoring and supervision. 20% progress target. | Continuation of monitoring and supervision. 50% progress target. | Continuation of monitoring and supervision. 70% progress target. | - Final inspection, release retention and close the project. 100% target |
|  |  | 4. Completion of 9 Mortuaries | R18 000 000 | Final inspection, release retention and close the project. 100% target |  |  |  |
|  |  | - 5. Completion of 5 Hospital Revitalization Projects | R33 600 000 | - Final inspection, release retention and close the project. 100% target |  |  |  |
|  |  | 6. Completion of staff accommodation for essential health workers | R26 782 000 | Final inspection, release retention and close the project. 100% target |  |  |  |
|  |  | 7. Continuation with two (2) Hospital Revitalization Projects | R95 500 000 | Continuation of monitoring and supervision of Thabamoopa and Letaba hospitals. 40% progress target. | Continuation of monitoring and supervision of Thabamoopa and Letaba hospitals. 60% progress target. | Thabamoopa and Letaba hospitals. 70% progress target. | Thabamoopa and Letaba hospitals. 80% progress target. |
|  |  | 8. Completion of EMS (5 Projects) | R15 000 000 | Continuation of monitoring and supervision. 90% progress target. | Continuation of monitoring and supervision. 100% progress target. | Final inspection, release retention and close the project. 100% target |  |
|  |  | 9. Completion of Whitoc | R6 450 000 | Continuation of monitoring and supervision. 40% progress target. | Continuation of monitoring and supervision. 70% progress target. | Final inspection, release retention and close the project. 100% target |  |
|  |  | 10. Completion of Social Development One Stop Centres (15) | R35 000 000 | Monitoring and supervision. 90% work complete | Final inspection, release retention and close the project. 100% work complete |  |  |
|  |  | New Projects 1. Staff Accommodation | R74 000 000 | Site Handover | Continuation of monitoring and supervision. 50% progress target. | Continuation of monitoring and supervision. 70% progress target. | Final inspection, release retention and close the project. 100% target |
|  |  | 2. Laundry Facilities (Upgrading of 4 existing Laundries) | R41 000 000 | Site Handover for Tshilidzini, Mokopane, Philadelphia and Pietersburg Hospitals | Continuation of monitoring and supervision. 50% progress target. | Continuation of monitoring and supervision. 70% progress target. | Final inspection, release retention and close the project. 100% target |
|  |  | 3. EMS (6 Projects) | R15 000 000 | Site Handover | Monitoring and supervision. 50% progress target. | Continuation of monitoring and supervision. 70% progress target. | Final inspection, release retention and close the project. 100% target |
|  |  | 4. Clinic Electrification (59) | R6 000 000 | Site Handover | Monitoring and supervision. 50% progress target. | Final inspection, release retention and close the project. 100% target |  |
|  |  | - 5. Community Based Rehabilitation Centres (CBRs) (3) | - R5 000 000 | Site Handover | Monitoring and supervision. 50% work complete | Continuation of monitoring and supervision. 70% work complete | Final inspection, release retention and close the project. 100% work complete |
|  |  | 6. Critical Life Saving Equipment at Targeted Hospitals (Boilers at George Masebe and W.F. Knobel) | - R10 000 000 | Site Handover | Monitoring and supervision. 50% progress target. | Final inspection, release retention and close the project. 100% target |  |
|  |  | Department of Transport and Roads 1. Construction of six (4 at Masia and 2 at Makuleke ) houses | R1 500 000 | Monitoring and supervision and 100% progress targeted. | - Final inspection, release retention and close the project. 100% target |  |  |
|  |  | 2. Convention of Warehouse to Offices | R5 800 000 | Continuation of monitoring and supervision and 100 % progress targeted. | - Final inspection, release retention and close the project. 100% target |  |  |
|  |  | Department of Agriculture 1. Vet Clinics and Processing Plants | R4 000 000 | - Final inspection, release retention and close the project. 100% target |  |  |  |
|  |  | - 2. Tompi Seleka College | R1 000 000 | - Continuation of monitoring and supervision. 60% progress target. | Monitoring and supervision and 80% progress targeted. | Monitoring and supervision and 100% progress targeted. | - Final inspection, release retention and close the project. 100% target |
|  |  | Department of Economic Development, Environment and Tourism 1. Environmental Affairs Offices (Suid Street, Polokwane) | R14 500 000 | - Final inspection, release retention and close the project. 100% target |  |  |  |
|  |  | 2. Marketing Stalls at -Mogalakwena -Senwarwana -Makhado -Modimolle | R2 400 000 | Continuation of monitoring and supervision and 100% progress targeted. | - Final inspection, release retention and close the project. 100% target |  |  |
|  |  | Office of the Premier 1. Construction of Offices of Traditional Leaders: -Mphephu -Tshikonelo -Marota -Marulaneng/Kutama | R9 400 000 | Continuation of monitoring and supervision and 60% progress targeted. | Continuation of monitoring and supervision and 100% progress targeted. | - Final inspection, release retention and close the project. 100% target |  |
|  |  | - Department of Sports Art & Culture - 1. Provincial Archives | - R29 435 000 | Supervision & monitoring and 50% targeted progress. | Supervision & monitoring and 100% targeted progress. |  |  |

EXECUTIVE PROGRAMME: REAL ESTATE

| Strategic Goal | Sustainable provincial building infrastructure to support service delivery |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable Objectives | Performance Measure indicator / Targets | 2007/2008 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Efficient management of immovable properties utilized for government service delivery | Disposal of redundant properties | Number of properties disposed 60 properties | R200 000 | 10 properties disposed R30 000 | 20 properties disposed R70 000 | 20 properties disposed R70 000 | 10 properties disposed R30 000 |
|  | Transfer of towns to municipalities | Number of R293 towns transferred to Municipalities 66 R293 towns | R80 000 | 30 R293 Towns transferred Towns R36 000 | 30 R293 Towns transferred R36 000 | 6 R293 Towns transferred R8 000 | - |
|  | Ownership of provincial properties | Number of provincial properties vested 30 properties | R 20 000 | 5 Properties vested R3 000 | 20 Properties vested R14 000 | 5 Properties vested R3 000 | - |
|  | Revenue optimazation | 70% reduction in arrear rentals | R0 | Recover 25% of arrear rentals | Recover 40% of arrear rentals | Recover 50% of arrear rentals | Recover 70% of arrear rentals |
|  | Integrated district office accommodation plan | Compilation of office space audit for the district offices | R4 000 000 | Bid award and compilation of implementation plan 20% work completed R800 000 | Monitor and supervise implementation plan 60% work completed R1,200 000.00 | Monitor and supervise implementation plan 100% work completed R2, 000 000.00 | - |
|  | Comprehensive reliable Provincial Asset Register | Updated asset register of all government owned immovable assets. Compilation of list of unutilized government properties | R10 000 000 | 25% updated Compile a list of unutilized properties, (land and buildings) R2 000 000 | 50% updated Finalize a list of unutilized properties R3 000 000 | 75% updated R2 000 000 | 100% completed R3 000 000 |
|  | Property investment | Commercialization of economically viable properties to be leased out to ensure economic development | R0 | Identify economically, viable properties to be leased out to derive economic benefit | Lease out 50% of identified properties | Lease out 100% of identified properties | - |
|  | Management of the prestige portfolio: Parliamentary Village, Premier’s Residence and Guest House | Development of policy and management structure | R0 | Develop policy Set up enabling management structure | Finalise, adopt policy and implement Implement | Implement | Review effectiveness of policy Review effectiveness |

EXECUTIVE PROGRAMME:  BUILDING AND MAINTENANCE

| Strategic Goal | Sustainable provincial building infrastructure to support service delivery |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable objectives | Performance measure Indicator/Target | 2007/08 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Maintenance of government buildings for safe and reliable use in accordance with norms and standards | Infrastructure maintenance plan in place and fully implemented | Maintenance of 155 residential houses in all districts completed | R2 415 000 | Completion of 35 houses R415 000 | Completion of 46 houses R700 000 | Completion of 46 houses R700 000 | Completion of 28 houses R600 000 |
|  |  | Maintenance of 5 blocks of flats | R3 399 000 | The Gables Flats, Ladanna Flats, Hillside Flats, Dewini Flats Activities: Paintwork Paving Landscaping Carpentry Electrical work R1 200 000 | The Gables Flats, Ladanna Flats, Hillside Flats, Dewini Flats Activities: Paintwork Paving Landscaping Carpentry Electrical work R1 399 000 | The Gables Flats, Ladanna Flats, Hillside Flats, Dewini Flats Activities: Paintwork Paving Landscaping Carpentry Electrical work R500 000 | The Gables Flats, Ladanna Flats, Hillside Flats, Dewini Flats Activities: Paintwork Paving Landscaping Carpentry Electrical work R300 000 |
|  |  | Renovation and upgrading 34 blocks of government offices in all districts in line with the audit report | R8 000 000 | Complete upgrading on 4 government offices. R1 880 000 | Complete upgrading on 5 government offices. R2 300 000 | Complete upgrading on 5 government offices R2 300 000 | Complete upgrading on 3 government offices R 1 520 000 |
|  |  | Renovation and upgrading of 3 government complexes at Giyani, Thohoyandou, and Sekhukhune | R 40 000 000 | Evaluation of bids and handover of project sites to contractors. 25% of upgrading work completed R8 000 000 | Monitoring and supervision of progress 50% of upgrading work completed R16 000 000 | Monitoring and supervision of progress 90% of upgrading work completed R14 000 000 | 100% of upgrading work completed R2 000 000 |
|  |  | Upgrading and refurbishment of Makwarela govt. complex 10 blocks of offices | R4 000 000 | Audit inspection planning 10% of upgrading work completed R1 000 000 | Structural repairs 60% of upgrading work completed R2 500 000 | Replacement of Asbestos roofs 100% of upgrading work completed R500 000 |  |
|  |  | Well maintained gardens, landscapes and grounds: government residential and office accommodation | R500 000 | Implementation of gardens, landscapes and grounds in line with the maintenance program. 25 % of work completed R100 000 | Implementation of gardens, landscapes and grounds in line with the maintenance program. 60 % of work completed R200 000 | Implementation of gardens, landscapes and grounds in line with the maintenance program. 90 % of work completed R100 000 | Implementation of gardens, landscapes and grounds in line with the maintenance program. 100 % of work completed R100 000 |
|  |  | Development of 57, 5 hectares of landscaping: Parliamentary Village and residential accommodation | R7 500 000 | Evaluation of bids and handover of project sites to contractors. 20% of work completed R1 500 000 | Monitoring and supervision of progress. 60% of planned work completed R3 000 000 | Monitoring and supervision of progress. 100% of planned work completed R3 000 000 |  |
|  |  | Upgrading of Premiers’ Residence | R3 500 000 | Site hand over and 20% of work completed R1 500 000 | 100% of work completed. R2 000 000 |  |  |
|  |  | Finalization of 11 MEC Houses. | R11 500 000 | Continue with work supervision 90% of work completed. R5 500 000 | Continue with work supervision 100% of work completed. R6 000 000 |  |  |

EXECUTIVE PROGRAMME 3:  EXPANDED PUBLIC WORKS PROGRAMME

| Strategic Goal | Job Creation, Skills Transfer and Poverty Alleviation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable Objectives | Performance Measure / Indicator | Target | 2007/2008 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Achievement of EPWP goals using Public Works capital and maintenance budgets | Implementation of Public Works EPWP Programme | Number of beneficiaries under the NYS skilled | 500 youths, 5% of which are absorbed into Departmental structure | R6 800 000 | Intake of youth into the Programme R1 700 000 for stipends | Monitoring of the Programme R1 700 000 for stipends | Monitoring of the Programme R1 700 000 for stipends | Evaluation of the Programme R1 700 000 for stipends |
| A well coordinated Provincial EPWP | Provincial EPWP Coordination | Coordinated intersectoral and departmental committees | Quarterly reports on intersectoral and departmental committees | R0 | Quarterly report | Quarterly report | Quarterly report | Evaluation report and Annual report |
|  | Implementation of EPWP support | Holding of 2 workshops and 5 district roadshows | 2 workshops and 5 district roadshows | R1 000 000 | Hold 2 workshops and 5 district road shows R1 000 000 | Implement outcome of workshops and road shows | Evaluate outcomes | Plan for next financial year |
|  | Development of sectoral norms and standards | Development of sectoral norms and standards | Developed sectoral norms and standards | R500 000 | Develop norms and standards R500 000 | Implement norms and standards | Monitor norms and standards | Evaluate implementation of norms and standards |
| Monitoring and evaluation of EPWP implementation | Monitoring of EPWP implementation | Compilation of Quarterly Reports on the 2007-08 EPWP Business Plan | Implementation of EPWP projects creating 57 391 jobs, transferring skills to 9 654 individuals and providing life skills to 50 156 individuals | R2 109 800 000 (Provincial and municipal budgets) | Jobs:14 353 Skills: 2412 Life Skills: 12 539 | Jobs:14 346 Skills: 2412 Life Skills: 12 539 | Jobs:14 346 Skills: 2414 Life Skills: 12 539 | Jobs:14 346 Skills: 2416 Life Skills: 12 539 |