## Sheet2
ACTIVITIES | PERFOMANCE 2004 |  | IMPACT ON TARGETED GROUPS | PLANS 2005
EDUCATION PROJECTS
Renovations and Rehabilitations | 151 schools at a budget of R153mil | All schools under construction. Expenditure = R24.8mil | Rehabilitated educational infrastructure for better access
| 8 schools at a budget of R3mil | 5 projects at tender stage
3 projects at pre-tender stage
New classroom blocks | 288 planned at a budget of R120.8mil | 112 Projects at tender stage | Additional and new educational infrastructure in the province
176 projects under-construction 50% of projects at completion stage
Total expenditure = R52mil
40% of carried-over projects reached completion stage
| Budget = R41mil | 22% of carried-over projects above 80% progress on site
38% of carried-over projects at 60% progress on site
Total Expenditure = R32.2mil
Ablution blocks | 141 Enviroloo Toilets implemented a budget of R13mil | 90% progress on construction. R6 mil expenditure. | Access to sanitation facilities
| 29 Waterborne toilets at a budget of R2.3mil | 95% progress on construction
R995 000 expenditure
Fencing Projects | 27 schools planned at a budget of R2.5mil | All 27 under-construction | Protected educational facilities
Multipurpose Centers | 13 projects at a budget of R3mil | 13 projects at tender stage
Special Schools | 2 projects at a budget of R5.8mil | Projects at tender stage | Accessable infrastructure for the disabled
Upgrading of technical colleges | Second phase of two technical colleges budget of R2. mil | Both first and second phases of the projects have reached 80%. The projects are ongoing.
Upgrading and Construction of Department of Education Offices (Voorwaarts) | 1 New office block at a budget of R2m | Project at planning phase | Availability of offices
HEALTH PROJECTS
Clinics | Electrification of 223 clinics planned at a budget of R9.5mil | All clinics at pre-tender stage. | Available primary health facilities
Hospital | New projects at 2 hospitals | R22 mil spent. Projects ongoing. | Available primary health facilities
Ongoing projects at 14 hospitals
Budget allocated =R56.3mil
| Electrification of 2 hospitals at a budget of R1.3mil | Projects at planning stage