Department of Public Works

Strategic Plan

--------------------------------

2005 – 2009

(DRAFT 1: 24/08/04)

Contents

Part A: Strategic overview

1.1	Statement of policy and commitment by the MEC	4

1.2	Overview by the accounting officer	5

1.3	Vision	6

1.4	Mission and strategic goals	6

1.5	Values	7

1.6	Legislative and other mandates	8

1.7	Description of status quo	10

1.7.1	Summary of service delivery environment and challenges	10

1.7.2	Summary of organisational environment and challenges	15

1.8	Description of strategic planning process	15

Part B: Programme and sub-programme plans

1.9	Strategic Objectives	17

1.10	Measurable objectives, performance measures and performance targets	20

1.11	Performance targets	54

1.12	Reconciliation of budget with plan by programme	56

1.13	Medium-term revenues	57

1.13.1	Summary of revenue	57

1.13.2	Departmental revenue collection	57

1.13.3	Conditional grants	Error! Bookmark not defined.

1.14	Co-ordination, co-operation and outsourcing plans	58

1.14.1	Interdepartmental linkages	58

1.14.2	Local government linkages	58

1.14.3	Public entities	58

1.14.4	Public, private partnerships, outsourcing etc	59

1.15	Financial Management:	59

1.15.1	Strategies to address audit queries	59

1.15.2	Implementation of PFMA	59

Part C: Background information

1.16	Appendix one: Analysis of service delivery environment	62

1.16.1	Policy changes and trends	63

1.16.2	Environmental factors and emerging challenges	64

1.16.2.1	Demographic profile of the province	Error! Bookmark not defined.

1.16.2.2	Employment, income and [other relevant information]	65

1.16.2.3	Profile of infrastructure in the province	35

1.16.3	Evaluation of current implementation performance	66

1.17	Appendix two: Organisational information and the institutional environment	66

1.17.1	Organisational design	69

1.17.2	Delegations	76

1.17.3	Capital investment, maintenance and asset management plan	76

1.17.4	Personnel	78

1.17.5	IT systems	79

1.17.6	Performance management system	81

1.17.7	Financial management	82

1.17.8	Audit queries	83

1.17.9	Implementation of PFMA	83

# Part A: Strategic overview

## Statement of policy and commitment by the MEC

The main challenges facing the department over the next few years relate to improving the  efficiency and effectiveness of service delivery. The department will encourage Broad Based Black Economic Empowerment (BBBEE) and small enterprise development by developing emerging contractors. The department is tasked with responsibility of coordinating EPWP and to develop a Provincial Infrastructure Plan

Another key challenge facing the department is the transformation of the provincial property portfolio. Non-core properties will be disposed of and the remaining properties must all be vested in the name of the province.

The RAL (Roads Agency Limpopo) is implementing a programme to reshape and regraveling rural roads, using labour-intensive construction methods. The aims of the programme are to provide temporary employment to the long-term unemployed youth and women in rural areas, and to build good quality roads cost-effectively.

I, O.C. Chabane, MEC for Public Works (Limpopo), hereby commit myself to the implementation of the strategic plan contained herein.

O.C. Chabane

## Overview by the accounting officer

The Limpopo Department of Public Works faces immense challenges. The strategic plans described here have been formulated with the aim of addressing these challenges by adopting strategies which will release resources for service delivery and improve service delivery. The department will implement strategic plans such as the labour intensive roads programme, commercialisation and outsourcing programmes, disposing of redundant properties, continually improving efficiency and effectiveness, best practice financial management, improved information management systems and recruitment of additional skilled personnel. In the coming financial year, the department will also focus on programmes such as improving gender representivity at middle management level. More work will be done in the coming year to further improve compliance with generic service delivery standards.

| KEY FOCUS AREAS FOR 2005/06 | ALIGNMENT WITH IDPs | BUDGET INPUTS FOR 2005/06 |
| --- | --- | --- |
| Service delivery improvement of road maintenance, building maintenance, cleaning, gardening and security | n/a | Not applicable – IPSP funded |
| Implementation of labour-intensive road regravelling programme (Gundo Lashu). | All roads projects are done in consultation with municipalities and the roads programme participates in IDP planning forums |  |
| Routine and preventative maintenance and rehabilitation of roads | Ditto |  |
| Disposal of redundant properties | n/a | On course for 100% by end of year |
| Tarring of roads | All roads projects are done in consultation with municipalities and the roads programme participates in IDP planning forums |  |
| Obtain title deeds for all provincial properties and valuing all provincial properties | n/a |  |
| Implementation of Emerging Contractor Development Programme (Limpopo Sakhasonke) | n/a |  |
| Improve maintenance systems for Health and Education facilities, together with Departments of Health and Education | n/a | - |

## Vision

Adequate and Reliable Integrated Public Infrastructure for growth, development and a prosperous Provincial Economy

## Mission and strategic goals

## MISSION

## To facilitate the management of sustainable integrated Provincial Infrastructure by providing leadership in the planning, management and implementation of programmes through optimal utilization of resources for accountable and customer - oriented service delivery for a united, non - racial, non-sexist, democratic South Africa.

STRATEGIC GOALS OF THE DEPARTMENT

- Establishment and maintenance of a sound and safe provincial road network.

- Management of government properties

- Offering a building construction management, project management, contract management and building maintenance service to other provincial government departments.

- Contribute towards poverty alleviation and promotion of job creation in the Province.

## Values

The Limpopo Department of Public Works prides itself on the following core values;

- Consultation

- Service Standards

- Access

- Courtesy

- Information

- Openness and Transparency

- Redress

- Value for money

- Hard working

- Customer-orientation

- Willingness to improve

- Progressiveness

- Professionalism

- Compliance

- Accountability

- Humility

- Reliability

- Prudence

- Integrity

- Zero tolerance to misconduct

- Respect

- Customer citizen focus

- Punctuality

- Impartiality

- Continuous improvement

## Legislative and other mandates

The Constitution states that provincial governments are only responsible for Public Works functions which relate to provincial functions and provincial state property. Hence, National Public Works directly undertakes Public Works functions which relate to national functions in the Province, such as the construction and maintenance of facilities and properties which are a national competence.

The Premier has assigned Provincial Public Works functions to the Department of Public Works. The Premier has included provincial roads in the provincial Public Works functions.

The operations of the Department are governed by the legislation governing the built environment professions, such as the Acts governing the Engineering, Quantity Surveying and Architecture professions. The Department has a large workforce engaged in road and building maintenance activities and therefore needs to take cognisance of the Occupational Health and Safety Act. Road and building construction activities are also governed by the relevant environmental legislation.

There is no legislation specific to Public Works, but there is a national White Paper on Public Works (Public Works Towards the 21st Century, 1997), and the Department endeavours to work within the policy framework set by the White Paper. In this regard, the Department endeavours to stimulate economic activity through job creation and empowerment of emerging entrepreneurs with particular bias towards previously disadvantaged individuals. In addition, the Department has adopted a matrix type of organisational structure, rather than a divisional organisational structure, in order to enable the adoption of project management techniques for the management of projects.

Like other departments, the Department is also guided by national policies aimed at transforming the public service, such as Batho Pele and the White Paper on Transformation of the Public Service. In addition, the Department is bound to work within the prevailing regulatory framework, including (inter alia) the Public Service Act and the new Public Service Regulations, Public Finance Management Act, New Treasury Regulations, and the Preferential Procurement Policy Framework Act. The Department is also bound by nationally negotiated agreements regarding conditions of service for its employees. It would be useful to have a brief description of these mandates, instead of the simple listing that of them that most departments currently present.  Other mandates that relates to coordination of EPWP and development of Provincial Infrastructure Plan are now added to Provincial Public Works.

## Description of status quo

This section contains broad information on the programmes in the Department.

### Summary of service delivery environment and challenges

Backlogs of Infrastructure

The recurring annual backlogs in budgeting for the maintenance of all provincial government infrastructure and the roads maintenance backlogs are provided in Table 2 and Table 3 below respectively.  There is also an estimated backlog of R2.5 billion worth of provincial government-funded new infrastructure which needs to be built to service communities in the Limpopo. In addition, R4.9 billion is required for preventative maintenance and rehabilitation of existing provincial infrastructure and R8.3 billion is required to upgrade existing facilities. (see Table 4 – Pg.13)

Table 1: Estimated flood damage to public infrastructure in the Limpopo.

| - SECTOR | - ESTIMATED QUANTIFICATION OF DAMAGE |
| --- | --- |
| - Provincial roads, bridges and drainage structures | - R 1 300 million |
| - Local roads, bridges and drainage structures | - R 400 million |
| - Water supply systems | - R 147 million |
| - Housing | - R 407 million (20 000 homeless families) |
| - Schools | - R 84 million |
| - Public facilities - - Provincial game reserves and farms - - Border posts | - R 44 million - R 5 million |
| - TOTAL | - Approximately R2.35 billion |

Source: Plan for Reconstructing Flood-Damaged Public Infrastructure in the Limpopo, Limpopo Government, July 2000. (Updated February 2001).

- Table 2 Status of the funding of provincial infrastructure maintenance

| - Type of infrastructure | - Department responsible for Budgeting Maintenance | - Amount Required For Annual Maintenance To Prevent Further Deterioration | - Amount Required To Execute Back-log of Maintenance Work - (To Restore To Good Condition) | - Amount Budgeted For Maintenance For The Year | - Shortfall On Annual Maintenance |
| --- | --- | --- | --- | --- | --- |
|  | - 1 | - 2 | - 3 | - 4 | - 5 = 2 – 4 |
| - ROADS | - PUBLIC WORKS | - R318, 000,000 | - R1 155, 000, 00 | - R111, 000,000 | - R207, 000,000 |
| - GOVERNMENT OFFICES | - PUBLIC WORKS | - R36, 900,000 | - R149, 500, 000 | - R16 000, 000 | - R 20,900,000 |
| - HOSPITAL AND CLINICS | - HEALTH & WELFARE | - R67, 162,157 | - R1, 296,002,873 | - R29, 719,873 | - R37, 442,984 |
| - SCHOOLS AND COLLEGES | - EDUCATION | - R55,701, 875 | - R1, 950,128, 000 | - 0 | - R55, 701, 875 |
| - SPORTS, ARTS, & RECREATION | - SPORTS, ARTS AND RECREATION | - R4, 600, 000 | - R82, 221,090 | - 0 | - R4, 600, 000 |
| - TRAFFIC STATIONS & WORKSHOPS | - PUBLIC TRANSPORT | - R4, 858,575 | - R38, 950,000 | - 0 | - R4, 858,575 |
| - STATE FARMS AND IRRIGATION SCHEMES | - AGRICULTURE | - R2, 140, 833 | - R115, 348, 550 | - 0 | - R2, 140, 833 |
| - TOTALS |  | - R 489,363,440 | - R 4,783,150,513 | - R 156,719,173 | - R 332,644,267 |

Table 3 : ROAD MAINTENANCE BACKLOGS

| - Type of maintenance | - Implications of not carrying out maintenance | - Current backlogs of maintenance | - Annual requirement to prevent further deterioration | - Amount budgeted |
| --- | --- | --- | --- | --- |
| - Fog spray tar roads (R10 000 per km) Repair and Reseal tar roads (R300 000 per km) | - Tar roads will rapidly fall apart and require rehabilitation | - R124 million | - R40 million | - R41 million |
| - Rehabilitate collapsed tar roads (R1 million per km) | - Tar roads will become more dangerous and turn into gravel roads | - R743 million | - R196 million | - R57 million |
| - Regravel gravel roads (R100 000 per km) | - Gravel roads will become impassable | - R3264 million | - R72 million | - R52.256 million |
| - Repair bridges | - Bridges may collapse | - R24 million | - R10 million | - R3.6 million |
| - TOTALS |  | - R1 155 million | - R318 million | - R153.856 million |

1.  The allocation figures for the  financial year exclude the flood damage reconstruction grant

Table 4 : ROAD MAINTENANCE BACKLOGS

Roads and Bridges

Roads Agency Limpopo (RAL), a company owned by the Government, is in terms of the Northern Province Roads Agency Act 11 of 1998 responsible for the provincial road network and related structures in terms of planning, design, construction and maintenance. The Board of the RAL is appointed by, and reports to the MEC for Public Works. The provincial network consists of over 21 218 km of road of which 6 020 km are surfaced and over 15 198 km are gravel. This includes all major roads (surfaced and unsurfaced) linking towns, villages and settlements in the Province. However, it does not include streets in towns and villages, which are the responsibility of the local sphere of government.

Property Management and Building

The Department is responsible for providing the provincial government with its property requirements. This involves renting of private properties and construction and maintenance of government-owned properties. The provincial property portfolio which is managed by the Department of Public Works consists of 744 residential houses, 12 blocks of flats, three large former homeland government complexes with 21 office blocks, 34 other office blocks and 44 other smaller regional office complexes, health and education buildings, museums, cultural centres, buildings in game parks and youth camps.

### Summary of organisational environment and challenges

In order to facilitate the implementation of the roads, building and property functions, the Department maintains four support directorates in the areas of human resource management, information management, financial management and corporate services.

Human Resource Management

The directorate is responsible for the provisioning of personnel within the framework of the new Public Service Act and Regulations, as well as the Batho Pele strategy.

GITO (Information Management)

The department also entered into service level agreements with the State Information Technology Agency (SITA) in terms of which the Departments’ entire information technology function is managed by the SITA. The Department has established a GITO structure in order to manage the service level agreements with the SITA. The Department’s information management and communications functions have also been absorbed into the GITO component.

Financial Management

The main functions of this Directorate is to render support services to the Department in terms of co-ordination of the budget, control over stores, expenditure control, and control over procurement of goods and services

Corporate Services

This programme seeks to render support to the Department through the following services:

- Maintaining proper records for the Department.

- Auxiliary services, including transport and office services

- Customer care

- Manage Shared Service Centres (SSC’s) in districts

- Management of tender office

Challenges facing the department include the recruitment of professional staff especially in the field of architecture, engineers, etc.

At present, most of the work is being done by low-level, unskilled staff.  This can be overcome by using the Public Service Regulations

to do job enrichment and by creating professional posts at the relevant levels to attract the right people.

A further challenge is to promote a productive culture of effectiveness and efficiency in the department. This is being accomplished through the

Service Delivery Improvement programme which aims to introduces quality management systems into the various programmes.

Adherence to the PFMA and Treasury Regulations poses a further challenge. A programme for creating awareness around the scourge of

HIV-Aids is already underway in the department, especially in our road and building camps.

## Description of strategic planning process

Strategic Planning is an on-going process. Each programme conducts individual strategic planning sessions during which programme-specific strategic plans are developed. These individual plans are consolidated into a single Departmental Strategic Plan during the Departmental Strategic Planning Workshop which is usually held at the end of May each year for planning for the following financial year.

# Part B: Programme and sub-programme plans

## Strategic Objectives

Strategic goal 1

Establishment and maintenance of a sound and safe provincial road network.

Strategic objectives

- To maintain safe and rideable roads for public use.

- Outsourcing the road construction unit.

- Tarring of roads.

- The implementation of a labour-intensive roads regraveling programme (Gundo Lashu).

- To introduce a Service Delivery Improvement programme (SDI) for road maintenance.

Strategic goal 2

Management of government properties

Strategic objectives

- To dispose of redundant government property.

- Improving revenue collections from tenants.

- To introduce a Service Delivery Improvement programme (SDI) for cleaning, gardening and security.

- To improve management of the provincial property portfolio.

- Transferring of properties to municipalities.

- Updating of a comprehensive provincial property register.

- Optimal utilisation of office space.

Strategic goal 3

Offering a building construction management, project management, contract management and building maintenance service to other provincial government departments.

Strategic objectives

- To render effective routine building maintenance services internally.

- To provide effective routine building maintenance services to other departments.

- To implement and manage an Emerging Contractor Development Programme (ECDP) – Sakhasonke.

- The consolidation and strengthening of project management procedures and systems.

- The management of provisioning and construction of facilities for other departments.

Strategic goal 4

Contribute towards poverty alleviation and promotion of job creation in the Province.

Strategic objectives

- Implementation of a labour intensive roads regravelling programme (Gundo Lashu)

- Development of an Emerging Contractor Development Programme (ECDP) - Sakhasonke

## Measurable objectives, performance measures and performance targets

| 1 | 2 | 3 |  | 4 | 5 | 6 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Programme structure Measurable objectives | Output | Performance Measures |  |  |  |  |  |
|  |  | Cost Measure |  | Quantity Measure | Quality Measure | Timeliness Measure |  |
| Programme 1 (Administration) | To provide support services to the core programmes (Roads, Building, Property) of the department |  |  |  |  |  | Budget R186,454 |
| 1.1. Human Resource Management | To render policy analysis functions, staff advisory and staff management services |  |  |  |  | R32,158 |  |
| 1. Leadership Provide meaningful leadership in the area of strategic human resources management, training and development, workplace relations and occupational health during the fiscal year 2005/2006 | - Innovative human resource practices - Innovative recruitment techniques - Business focused HR Planning - Succession and retention plans - Career orientated skills development plan - Broad HR knowledge base - An intergrated Adult Basic Education Programme - Sound labour relation practices - A functional workplace health - A wellness programme in place |  |  | High Persal literacy level 500 bursaries 6000 training interventions 1000 ABET intake 28 workplace consultative forums 100 HIV AIDS awareness workshops | Competent workforce Compliance to standards Consistency Accredited training Fairness ISO 14000 compliance | March 2005 Quarterly up March |  |
| 2. Policy and Strategy Align human resources policies and strategy towards service delivery in line with the vision and mission of the department. | - Extensive employee communication strategy - Conceptual framework to implement HRM - Strategically aligned policies - HR risk management strategy and - Plan - Programme strategic plan signed off by - HOD - Sub programmes business plan being - In place - Policy manual being widely - Distributed |  |  | Hold HR Review meetings Quarterly risk management reviews Finalise outstanding policies | Compliance With legislation And relevant Review Existing policies | Monthly upto 03 2005 Quarterly |  |
| 3. Stakeholder Focus # Customer and stakeholder needs relating to strategic human resource management are quantified and prioritized according to service delivery standards. | Efficient and effecive staff benenefits office An established PMS office Effective compalints handling office Revised HR service delivery standards Revised work methods for task environment |  |  | Reduction in number of complaints Number of complantts recorded Conduct quartely customer survey | Customer and stake holder feedback | Quarterly up to March 2005 |  |
| 4. People Management Manage staff and personnel within the legal administrative framework | Relevant policies to manage staff Involvement of staff in decision making. A democratic work environment Motivated workforce Functional employee wellness programme | R28 753 m |  | Increased staff satisfaction Staff turnover Reduction in employees taking sick leave related to workplace stress | Level of staff involvement in decision making Reduction in sick leave utilised | Monthly reviews |  |
| 5. Resource and Information Management Optimise all human resource management supporting activities to improve deployment of capital, human and material resources for service delivery. | Best EAP practices Fair labour practises Best hr practices Workplace skills plan Competent staff Reliable information Proper documentaion Human resource management knowlegde resource centre |  |  | Number of professionals Intergrity of Staff records Correct staff placement Placing staff correctly on Persal system | Integrity Consistency Staff proficiency | Up to March 2005 |  |
| 6. Processes Continuous identification, review, management and improvement of all process to attain best human resource management services | Transformation and restructuring of the workplace. Redesigned hr systems and processes Service delivery improvement Programme Redesigned organisational structure Process review action plans Implementation of the public service regulations Documented hr process and Procedures |  |  | Constant review of processes and systems Efficient and effective organisational structure | Improved workflow Improved Results Synergy of processes Quality work and reports | March 2005 |  |
| 7. Impact on society Meaningful contribution to the realization of departmental social responsibility programme in line with government policy | Implementation of employment equity Implementation of learnerships Provision of eap services to family members of serving emloyees. |  |  | Number of people employed from designated groups. Number of learnerships implemented Number of bursary reciepients Number of families assisted under the EAP | Feedback from From Stakeholders | March2005 |  |
| 8. Customer and Stakeholder Satisfaction Provision of reliable HR solutions to all users and beneficiaries of human resource management services. | Established HR call center Up to date HR records Well trained and professional staff Friendly staff Simplified documents |  |  | Reduced number of dissatisfied customers | Fair and courteous service, honesty and intergity , responsiveness, simplicity | March 2005 |  |
| 9. People Satisfaction Continuously strive to understand, predict and improve the satisfaction and involvement of staff n pursuit of a healthy working environment. | Employee wellness Motivated staff Functional consultative forums Democratic work place environment SHERQ compliant work environment |  |  | Reduced number of dissatisfied staff Reduced staff turnover Reduction in misconduct cases and grievances Number of performance related awards | Motivated workforce Responsive administration Absence of work related injuries | March 2005 |  |
| 10. Supplier and Partnership Performance Consolidation of frameworks utilized in managing performance of suppliers and service providers. | Service provders database Affiliation to professional bodies and association Hr call center |  |  | Number of service providers in database | Preferred suppliers on database | March 2005 |  |
| 11. Organisational Results Contribution of HRM in the realization of the overall vision and mission by streamlining all value adding process. | Improved reliablity of personnel records Compliance with the Public Service Regulation And all other legislation Batho Pele Reduction in the number of Audit Queries |  |  | Up to date personnel records Reduction in the number of formal audit queries | Compliance to standards Improved Organizational performance Improved image of the Department Unqualified audit report | March 2005 |  |
| 1.2. GITO Information Management | To focus on management control systems development and implementation in the areas of telecommunication infrastructure systems development for all components of the department; information management and communications |  |  |  |  | Budget R24,082 |  |
| To provide stable and efficient ICT infrastructure | Provician of ICT infrastructure Stable Network connectivity SLA established with service provider |  |  | Number of cost centres with ICT infrastructure 95% of Network conectivity in all regions, cost centres and Head office. Systems functioning optimally | Reliable and sufficient IT infrastructure Reliable network system and network points . Reduction of user complaints. | 2005/2006 |  |
| Coordination of provincial ICT infrastructure | Plan for Provincial ICT infrastructure |  |  | Conseptual ICT document developed. | Broder conectivity in rural areas. | 2005/2006 |  |
| Develop & Implement Master Systems Plan (MSP) | Coordinated Departmental IT activities |  |  | Planning in line with MSP guidelines | Optimised and Reliable IT infrastructure | July 2004 |  |
| Provision Of Telecommunication Infrastructure (Lan & Wan) | Network Cabling And Switches Network Maintenance Contract |  |  | Network All District Offices And Cost Centres With Head Office And Districts Ensure That Network Is Always Operational Through Maintenance Service Contracts | Improvement Of Internal And External Communication And Support To Provincial Database For Coordination Of Infrastructure Provisioning Reliability And Availability Of Information In Support Of Improved Decision-Making | On-going |  |
| Hardware & Software Provision | Acquisition of hardware and software |  |  | 90% Of Hardware And software as well as related Accessories Provided For department. | Acquire Adequate And Reliable Hardware & software aswell as related Accessories For The Department, | 2005/2006 |  |
| Software Licensing | Ensure all software in the department are Legal. |  |  | Adequate Software And Support Services Are Provided All Software Currently Used In The Department Is Licenced | Improved Communication And Service Delivery | 2005/2006 |  |
| Provisioning of Information Management Services | Compilation & Publication Of quality departmental reports Fully functional information management resource centre. Functional Intranet |  |  | Publish quality Annual Reports Quarterly Reports,Strategic Plan and Departmental Newsletter Develop A Docu-Ment Cataloguing System. Develop intergrated document management system Improve, Update And Maintain A Departmental Intranet | Improved Communication Improved Access To Documentation Improved Information Sharing User Feedback, easy access to information. | 2005/2006 |  |
| Communication Services | Communication Strategy Development Implementation of Communication Strategy Departmental Events and campaigns management |  |  | Build positive relations with media, clients and stakeholders Customer staisfaction Informative Stakeholder and public | Positive public image Reduce customer complaints Well informed public and stakholders | 2005/2006 |  |
| 1.3. Corporate Services | To render support through maintaining proper records for the department, Auxiliary services, customer care, management of shared service centres (SSC’s) in districts and management of the tender office. |  |  |  |  | Budget R66,266 |  |
| To develop and manage internal communications for the Department in terms of telecommunications infrastructure and to develop customer relationship management in the Department | To do a needs analysis of telecommunication infra-structure in the regions and ensure that backlogs are addressed at the Cost Centres Recruit and train customer relations officers Conduct surveys with all customers to ensure proper internal communications Develop proper internal communications with the project centres to ensure that all policy documents and circulars are timeously received |  |  | Better internal communications Improved customer relations Improved commu-nication and report-ing procedures. Speedy resolution of customer complaints and minimise complaints | Support the department to realize its overall objectives and strategies by providing effective and efficient administrative support services. | 31/Mar/2005 31/Mar/2005 31/Mar/2005 |  |
| To maintain proper records for the Department | To constantly review all work methods and proce-dures to identify and note all weakness in the current work methods and implement improve-ments Implementation and monitoring of the filing procedures at head office and all project centers. Re-organize the layout of registry. |  |  | Easily, readily accessible and consistent information. Systematic filing of records. Proper records management system. | Assist the department to reach its overall objective and strategies by providing effective efficient administrative support services. | 31 Mar 2005 30 Mar 2005 |  |
| To perform excellent office services functions such as travel and accommodation arrangements, providing stationery, managing fax and photocopier services, as well as processing the payment of accounts | To constantly review all work methods. To do a needs analysis of labour savings devices and institute resource plan to address backlogs in all regions Put in place processes and systems to ensure the timeous payments of accounts Constantly check the stock at the stationery to ensure that there is enough stock and place orders if stock on hand drops to 50% To develop fault-reporting strategies for labour-saving devices and reduce the time taken to effect repairs to labour saving devices Timeously process payments to service providers |  |  | Effective and efficient office services (travel, accommodation arrangements, stationary, labour-saving devices, etc) to all officials in the department. Improved service delivery. Effective payment methods and customer satisfaction | Assist the department to reach its overall objective and strategies by providing effective and efficient administrative support services | 31 Mar 2005 31 Mar 2005 30 Apr 2005 31 Mar 2005 |  |
| To manage the government motor fleet as well as subsidised vehicles to ensure proper utilization of government vehicles to enable departmental officials to execute their functions effectively | Do needs analysis of subsidised motor vehicles as well as government cars and put in place resource plan to address shortfalls. Smooth transition of the devolution of transport function from the Department of Transport to the Department of Public Works To constantly review all work methods and procedures to identify and note all weakness in the current work methods and implement improvements. Constantly review the under utilization of vehicles on a monthly basis Inspect all government vehicles and monitor expenditure and set up database for all subsidized cars as well as claims. Update and Complete assets register of all Government vehicles |  |  | Improved control of vehicle manage-ment resulting in reduced expen-diture, eradication of irregularities and receiving value for money. Cost reduction Updated and reliable inventory of all vehicles in the department. |  | 31 Mar 2005 31 Mar 2005 31 Mar 2005 |  |
| Ensure that all work methods and procedures in the Departmental Tender Office are reviewed to ensure that there is proper internal control measures in place to deal with the increased delegations from the Provincial Tender Board | To do an analysis of procurement procedures to ensure that there is adherence to the PPPF Act Put in place year long quotation process to ensure acquisition of goods and services in cases of emergency To constantly review all work methods and proce-dures to identify and note all weakness in the current work methods and implement improve-ments. |  |  | Proper and efficient adjudication of Tenders. Efficient support services to the Departmental Tender committee and core business directorates of the Department. Transparent and accountable adjudication of Tenders. | Assist the department to reach its overall objective and strategies by providing effective and efficient administrative support services | 30 November 2005 |  |
| Ensure that the Shared Service Centers provide a prompt service to the core directorates in terms of procuring goods and services and attending to their request timeously. | Put in place monitoring systems such as registers to measure the time the request is received by the Shared Service Centers to the moment the request is finalised. Undertake monitoring and evaluations of these systems on quarterly basis. Get reports on bi-monthly basis from shared service centre managers. |  |  | Improved service delivery to core directorates | Support the department to realize its overall objectives and strategies by providing effective efficient administrative support services. | 1 Mar 2005 |  |
| 1.4. Financial Management | To render support services to the department in terms of co-ordination of the budget, control over stores, expenditure control and control over the procurement of goods and services |  |  |  |  | Budget R45,654,000 |  |
| Budget Planning & Control | Activity-based budget Constant budget plan Timeous capturing and activating of budget Monitoring of budgets Compliance with regulations Compliance with sec40 (4) b-c monthly reports to the EA and Treasury Monthly reconciliation Cancellation and re-print of cheques |  |  | Compilation of activity segmented budget framework Informed and accurate input from directorates Budgets to be finalized before the end of the financial year, and any changes to the structure should be finalized before the end of January Programme Managers’ availability for report discussion MTEF budgets are compiled in the new format and other guidelines Monthly closure of books and no exceptions | Confirmed budget allocations from Treasury. Reduction of virements and transfer of funds throughout the year. Expenditure commences at the beginning of the financial year. Reduction of budget cuts; fiscal dumping & unauthorized expenditure. Areas of under and over expenditure are identified during the early stages Programme Managers’ availability for report discussion Systems running efficiently. No down time on server. | March of every fiscal period December every year 31st March of every year Monthly Monthly Monthly |  |
| Revenue Management |  |  |  | Not Applicable | Comparison of percentage in previous periods Information management- credible asset registers Efficient financial systems Capable officials Credible assets register Complete information from systems | Monthly Weekly payments On-going Daily Daily Monthly |  |
| Expenditure Management | Expenditure control Accurate, timely and responsive reports Reduced payment cycle Safe custody of vouchers & face value documents Payroll Management |  |  | Spending within voted period. User-friendly reports for non-financial managers. Reconciled systems reports Age analysis details on 6 months cycle Fewer or no audit queries; Reduction in fraud & corruption; All vouchers stored in relevant districts Statutory compliance; Accurate management of third party obligations on payroll | Timeous availability of budget and systems Capable staff; Efficient financial systems Information flow, contracts management by line officials Assistance from Compliance with regular district audits Information from 3rd parties; Rapport with clientele- HRM | Monthly 7th day of every month Monthly Monthly Within obligated period |  |
| Asset & Inventory Management | Restructuring of stores management Stock provision Disposal of obsolete and redundant moveable assets Stores inspection and annual stock-taking Asset management Purchases and acquisitions |  |  | Submission of requisitions, quotations and authorities Relevant systems in place Boards of survey nominated; Directorates maintain asset registers Compliance unit and provisioning officers working together. Appoint stock-taking teams Co-operation from all programmes on their assets. Rele-vant systems in place for automa-tion. Dedicated personnel Submission of requisitions, quotations and authorities | Effective inventory management. Reduction of audit queries. Automation of the inventory management process Economic order quantities Auction sale programme; Inventory management asset registers Loss reduction; Adherence to stores management systems Asset registers for the department and financial asset accounting. Optimal utilisation of resources Process orders and invoices | Quarterly and annually Monthly review Monthly & Annually Quarterly reconciliation of assets and rand value Daily Daily |  |
| Systems Management | Administering systems – PERSAL, BAS, FINEST |  |  | Computers in workstations; Software packages loaded for users as per request; Training sessions available | Systems availability, Performance Reliable data | Daily |  |
| Management of Purchases | Administer contracts Monitor purchases of goods and services in line with procurement procedures, PFMA and Treasury Regulations Capacity Building Render Support to Directorates and Districts by monitoring procurement and expenditure patterns Monitoring procurement policies & regulations Implement internal controls for procurement Set up and communicate procurement process |  |  | Check the validation period of contracts Age analysis of outstanding orders Relevant training courses Analyse expenditure and consolidation of expenditure reports Systems and procedures in place Conduct risk assessment annually Establish consultation and communication for users; Provision of procedure manuals for the process | Valid contracts in place Elimination of procurement backlog Identification of suitable skills development programmes Elimination of unauthorised, wasteful and fruitless expenditure Complete compliance with policies Elimination of audit queries and potential fraud, negligence & corrupt activities Analyse returns on purchases | Daily Monthly Quarterly Monthly Monthly Review Monthly On-going |  |
| Risk Management | Risk assessment Communication of Risk strategy Implementation of Phase III of the risk management system Appoint a manager to run the program Fraud Prevention |  |  | Human and financial resources Management support & understanding of the concept Availability of human resources. Support from all programmes Availability of candidates for interviews Programme Managers’ availability for report discussion Audit plans to be driven by the assessments. Skilled personnel. Audit being carried, human & financial resources Financial & human resources | Compilation of risks identified in department, actions to combat the potential risks Incorporation of risk controls in all business processes All programmes have risk champions Incumbent in post Identification and prioritisation of controls in high risk areas Compliance audits & internal audit to focus on high risk areas. Reports on progress Workshops for communicating the plan | Every 5 years – Reviewed annually March 2004/05 March 2004/05 March 2004/05 Quarterly Reviews Quarterly Annually September 2005 |  |
| Programme 2 Public Works | To manage the property requirements for all provincial departments and to manage the provincial property portfolio |  |  |  |  | Budget R373,644 |  |
| 2.1 PROPERTY |  |  |  |  |  | R113,088,000 |  |
| Disposal of redundant state properties | Disposal of provincial land and properties in accordance with the “disposal land for provincial state owned redundant properties” Sale of flats |  |  | Sale of all remaining redundant State fixed properties Sale of 7 blocks of flats | Revenue raising. Release govern-ment from non-core functions. Release resour-ces for service delivery. Black economic empowerment. | On-going September 2005 |  |
| Optimal utilisation of office space | To proceed with the space audit in the remaining buildings |  |  | Follow-up report will be made availa-ble on an ad-hoc basis | Current vacant /under-utilised space can serve as a potential source of revenue | On-going |  |
| Lease management | Continuous updating and management of lease management |  |  | On-going | Eliminate unauthorised and illegitimate rental payments | On-going |  |
| Improved management of residential properties | Rental Collection Improved management of tenants and leases |  |  | Aim to achieve 95% rental collect-ion by March 2004 To appoint housing inspectors who will be responsible for lease and tenant management | Increase in revenue collection Timeous pay-ments and renewal of leases. | On-going |  |
| Updating of a comprehensive provincial property register | Vest all the properties in the name of Limpopo Province, which involves identification of properties in consultation with other departments to confirm ownership; obtaining Item 28 (1) certificates from the national Minister of Land Affairs before registration with the Deeds Office |  |  | Develop a data storage facility for storing documents Continued liaision with the Gauteng provincial government to acquire title deeds of properties which are situated in Limpopo Continue with the vesting program-me. | Successful vesting of all identified properties in the name of the province. Completion of comprehensive provincial property register | On-going |  |
| Transfer of properties to municipalities | Briefing of districts Municipalities Signing of Deed of Transfer Registration and transfer of properties |  |  | There are 197 R293 townships in the programme for transfer to various municipalities | Improved gover-nance and inter-governmental cooperation. | March 2006 |  |
| Cleaning services | Daily cleaning and upkeep of common state buildings and grounds |  |  | Workplans put in place. Improvement in cleanliness and presentability of grounds of government buildings | Good government image. | On-going |  |
| Gardening services | Maintenance of gardens at common government offices |  |  | Workplans put in place. Improvement in cleanliness and presentability of grounds of government buildings | Good government image. Efficient and effective administration | On-going |  |
| Security services | Protection of State Assets |  |  | Workplans put in place. Improved management of private security contracts | Good government image. Efficient and effective administration | On-going |  |
| - Government Buildings (OTHER Infrastructure) | To offer building construction management, project management, contract management and building maintenance services to the department and other provincial government departments |  |  |  |  | Budget R260,556,000 |  |
| Improved work output of construction teams | Effective and efficient teams that execute projects based on private sector standards and timeframes | Construction of 200 new dwelling units at road construction camps – R8.4m |  | Completion of 200 new dwelling units at road construction camps – R8.4m | Execution of projects according to specification | Completion of projects within schedule |  |
| Official residential accommodation for MPL’s and MEC’s | Alleviate shortage of Official residential accommodation for political office bearers | Ten additional housing units at the Parliamentary village – R10.86m |  | Completion of the ten additional housing units at the Parliamentary village by 31 March 2005 | SABS and National Building Regulations | Construction and work schedules |  |
| Render effective routine building maintenance and rehabilitation services for all Government offices | Offices that are compliant with the occupational health and safety act and national building regulations. | R24.263million |  | Completion by 31 March 2005 | SABS standards and National Building Regulations | Construction and work schedules |  |
| Equipment maintenance and special structural repairs | Offices that are atmospherically and environmentally comfortable to work from | R13.10million |  | Completion by 31 March 2005 | SABS standards and National Building Regulations | Specifications and work schedules |  |
| New offices | Adequate office accommodation for staff and MEC at Department of Public Works | R0.96million |  | Completion of roll-over project by 30 June 2004 | SABS standards and National Building Regulations | Construction and work schedules |  |
| Implementation of an Emerging Contractor Development Programme (ECDP) – Sakhasonke | Ensure training of emerging contractors to obtain National Certificate in Construction Contracting | Personnel budget |  | 80 contractors | Successfully completed 2 building site projects Successfully obtained 193 points credits | Maximum four months theoretical training Maximum eight months on site training |  |
| Programme 3 Roads & Bridges | Establishment and maintenance of a sound and safe provincial road network |  |  |  |  | Budget R1,012,980 |  |
| 4.1 Departmental maintenance | To maintain safe and rideable roads for public use |  |  |  |  | Budget R312, 730 |  |
| - Gravel Maintenance | - Blading (blade-km) - Re-shape, Formation, narrow & drains (km) - Re-gravelling (km) - Gravel shoulders – re-shape (km) | R 46.22 / bl-km R 1,691.50 R 55 / km R 1,464.05 / km From Business Plans of districts |  | 500,000 bl-km 550 km 400 km 1000 km From Business Plans of districts | - Quality Management System - Road Maintenance Manual Jan. 2003 - SDI Monitoring | - Business Plans of Districts |  |
| - Drainage Maintenance | - Cleaning of drainage structures - each - Install new 600 & 900 mm dia. Culvert - each - Head/Wingwall – each | R 325.03 each R 8,655.88 each R 3,488.77 each From Business Plans of districts |  | 26,000 150 700 From Business Plans of districts | - Quality Management System - Road Maintenance Manual Jan. 2003 SDI Monitoring | - Business Plans of Districts |  |
| - Reserve Maintenance | - Bush-clearing & rubbish removal – light (m2) - Bush-clearing & rubbish removal – medium (m2) - Bush-clearing & rubbish removal – heavy (m2) - Bush-clearing & rubbish removal – machine (m2) - Grass cutting (m2) | R0.20 / m2 R0.30 / m2 R0.79 / m2 R 4.78 / m2 R 0.10 / km From Business Plans of districts |  | 80,000,000 m2 20,000,000 m2 12,000,000 m2 370 m2 17,000,000 (m2) From Business Plans of districts | - Quality Management System - Road Maintenance Manual Jan. 2003 - SDI Monitoring | - Business Plans of Districts |  |
| - Road signs | - Replace chevron W401 & W402 each - Replace single pole sign – each - Replace double pole sign – each - Fence repair / km - Painting poles - each | R 326.66 / each R676.46 / each R2,540.63 / each R 3,205.44 / km R 33.70 / each From Business Plans of districts |  | 10,000 no 10,000 no 11,929 no 1,500 km 1,200 no From Business Plans of districts | - Quality Management System - Road Maintenance Manual Jan. 2003 - SDI Monitoring | - Business Plans of Districts |  |
| - Surface repair | - Pothole repair: - Edge-break - Crack-seal: | R275.74 / sq.m R1,380.19 /sq.m R8.54 / metre From Business Plans of districts |  | - 33,000 sq.m - :3,000 sq.m - 644,000 metre. - From Business Plans of districts | - Quality Management System - Road Maintenance Manual Jan. 2003 SDI Monitoring | - Business Plans of Districts |  |
| 6. Other (plant) | The condition of plant used by the Department is regularly checked in order to establish whether it can still be gainfully employed | - According to industry norms - Service level agreements between the Mechanical Sub-directorate and the district maintenance teams are in place |  | - According to industry norms - Service level agreements between the Mechanical Sub-directorate and the district maintenance teams are in place | - According to industry norms - Service level agreements between the Mechanical Sub-directorate and the district maintenance teams are in place | - According to industry norms - Service level agreements between the Mechanical Sub-directorate and the district maintenance teams are in place |  |
| 4.2 Roads Agency Limpopo (RAL) | To establish and manage the provincial road network effectively and efficiently (planning, designing and construction) |  |  |  |  | Budget R700,250,000 |  |
| To effectively and efficiently manage the Provincial Road Network (planning, designing and constructing) to its optimum potential | Oversee and manage works projects Implement adequate road and other asset maintenance and cleaning programs |  |  | Strategic routes to be kept operational Routine and periodic maintenance to be timeous and cost efficient Technical standards to be maintained. | All high priority projects will be in line with the Provincial Development Strategy plan considering the Ivory Routes, the Spatial Development Rationale and the Spatial Development Initiative including the Dilokong sub-corridor. | 2005/06 financial year |  |
| Strategic planning, design, construction, operation, rehabilitation and maintenance of the Limpopo Province road network. | Demarcate provincial roads Establish an appropriate land and asset register for the entire provincial road network |  |  | All provincial roads declared Asset register to be developed once provincial network has been defined Development of Provincial Road Network Strategy | Provincial road network defined Provincial road network defined Provincial road network strategy aligned with Provincial Growth and Development Strategy | March 2006 March 2006 March 2006 |  |
| To generate revenue from the development and management of its assets | Tolling of Provincial Roads Charging of levies, fees or rentals for advertising, access, rentals, leasing, within road reserves |  |  | Revenue Generation Plan developed | Revenues raised will be invested in the provincial road network | May 2006 |  |
| To develop technical expertise that will render services to other institutions | World class human resource development. Benchmark the RAL’s Technology and communication strategy |  |  | Human Resource policies and proce-dures developed To offer RAL's technical services to other organisa-tions Technology and Communication strategy developed and in operation | Improve efficiency of provincial road network management World-class infrastructure provision in the province. | March 2006 March 2006 March 2006 |  |
| To implement an aggressive (strategic) funding programme | Exploit opportunities to access funds from donors, government departments and other sources |  |  | Obtain Funds from other sources | Co-ordinated effort in the development of Provincial infrastructure | March 2006 |  |
| Socio-economic development | Developing emerging contractors Employment creation and poverty alleviation through implementing Labour Intensive Programmes Redressing historical imbalances |  |  | Develop and implement guide-lines to promote emerging contract-ors Successfully implement the Labour Intensive Rural Roads Maintenance Programme Implementation of Affirmative Action policies to re-dress historical imbalances | Contribution to job creation Job creation, poverty alleviation and SMME development Human Resource development and economic empowerment | On-going On-going May 2005 |  |

## Performance targets and monitoring mechanisms

| 1: Administration |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Output | Performance Measure | Monitoring Mechanism | 2004/05 target | 2005/06 target | 2006/07 target | 2007/08 | 2008/09 | % change over MTEF |
| To provide support services to the core programmes (Roads, Building, Property ) of the department | See 1.10 |  |  | 173,766 | 186,454 | 157,175 | 165,034 |  |  |

| 2: Property |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Output | Performance Measure | Monitoring Mechanism | 2004/05 | 2005/06 | 2006/07 | 2007/08 | 2008/09 | % change over MTEF |
| To manage the property requirements for all provincial departments and to manage the provincial property Portfolio | See 1.10 |  |  | 105,194 | 113,088 | 107,028 | 112,379 |  |  |

| 2.2: Building other Infrastructure |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Output | Performance Measure | Monitoring Mechanism | 2004/05 | 2005/06 | 2006/07 | 2007/08 | 2008/09 | % change over MTEF |
| To offer building construction management, project management, contract management and building mainte-nance services to the department and other provincial government departments | See 1.10 |  |  | 252,333 | 260,556 | 331,679 | 348,263 |  |  |

| 3: Roads |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Output | Performance Measure | Monitoring Mechanism | 2004/05 target | 2005/06 | 2006/07 | 2007/08 | 2008/09 | % change over MTEF |
| Establishment and maintenance of a sound and safe Provincial road network | See 1.10 |  |  | 802,449 | 1,012,980 | 1,106,646 | 1,161,978 |  |  |

## Reconciliation of budget with plan by programme

The changes of expenditure (if possible in nominal and real terms) by overall budget programme and sub-programme should be shown and the rate of change in spending of past years compared with that projected for the MTEF period (see table on next page). An account should be given of how spending trends have transpired in previous years and how MTEF projections correspond to strategic plan objectives.

Table 1: Evolution of expenditure by budget programme and sub-programme (R million)

| Sub-programme | Year – 1 2002/03 (actual) | Year - 2 2003/04 (actual) | Base year 2004/05 (estimate) | Average annual change (%)2 | Year 1 2005/06 (budget) | Year 2 2006/07 (MTEF projection) | Year 3 2007/08 (MTEF projection) | Average annual change (%)3 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Administration | 110,710 | 150,283 | 173,766 |  | 186,454 | 157,175 | 165,034 | 6 |
| 2. Public Works |  |  |  |  |  |  |  |  |
| 2.1. Govt. Building Maintenance (other infrastructure) | 266,764 | 233,028 | 252,333 |  | 260,556 | 331,679 | 348,263 | 6 |
| 2.2. Properties | 89,973 | 96,445 | 105,194 |  | 113,088 | 107,028 | 112,379 | 6 |
| Total for programme 2 | 356,737 | 329,473 | 357,527 |  | 373,644 | 438,707 | 460,642 |  |
| 3. Roads & Bridges | 659,132 | 834,334 | 802,449 |  | 1,012,980 | 1.106,646 | 1,161,978 | 6 |
| 4. CBPWP | 10,000 | 5,000 | - |  |  |  |  |  |
| Total programme | 1,136,579 | 1,319,090 | 1,333,742 |  | 1,573,708 | 1,702,528 | 1,787,654 | 6 |

*The CBPWP has been incorporated into the Building division under the Sakhasonke Emerging Contractor Development Programme as from 2004/05.

## Medium-term revenues.

### Summary of revenue

The following sources of funding are used for the Vote:

Table 2: Summary of revenue: (Department of Public Works)

| R 000 | 2002/03 Actual | 2003/04 Actual | 2004/05 Estimate | 2005/06 MTEF | 2006/07 MTEF | 2007/08 MTEF |
| --- | --- | --- | --- | --- | --- | --- |
| Voted by legislature | 886,858 | 1,085,637 | 1,096,412 | 1,308,719 | 1,410,742 | 1,304,563 |
| Conditional grants | 249,728 | 283,453 | 237,331 | 264,359 | 291,786 | 290,348 |
| Other (specify) | 0 | 0 | 0 | 0 | 0 | 0 |
| Total revenue | 1,136,586 | 1,369,590 | 1,334,143 | 1,573,412 | 1,504,633 | 1,594,911 |

### Departmental revenue collection

Table 3: Departmental revenue collection: (Department of Public Works)

| R 000 | 2003/04 Actual | 2004/05 Actual | 2005/06 Estimate | 2006/07 MTEF | 2007/08 MTEF | 2008/09 MTEF |
| --- | --- | --- | --- | --- | --- | --- |
| Current revenue |  |  |  |  |  |  |
| Tax revenue | 0 | 0 | 0 | 0 | 0 | 0 |
| Non-tax revenue | 28,314,168 | 10,791,654 | 5,024,795 | 4,835,280 | 0 | 0 |
| Capital revenue |  |  |  |  |  |  |
| Rental | 10,171,314 | 3,459,971 | 7,264,124 | 3,113,974 | 0 | 0 |
| Sale of buildings | 15 | 10,002 | 8,121 | 7,035 | 0 | 0 |
| Departmental revenue | 10,171,314 | 3,459,986 | 7,274,126 | 3,122,095 | 0 | 0 |

## Co-ordination, co-operation and outsourcing plans

### Interdepartmental linkages

The Limpopo Department of Public Works has entered into Service Level Agreements (SLA’s) with the Department of Education and

the Department of Health and Welfare for the construction of schools, clinics and hospitals.

### Local government linkages

The department participates in Integrated Development Planning (IDP) forums with local and district municipalities and other

stakeholders with regard to roads projects.

### Public entities

Table 4: Details of public entities

| Name of public entity | Main purpose of public entity | Transfers from the departmental budget |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 2003 MTEF | 2004 MTEF | 2005 MTEF | 2006 MTEF | 2007 MTEF |
| 1. Roads Agency Limpopo (RAL) | Responsible for the planning, design, construction and maintenance of roads and bridges | 539,056,000 | 500,252 | 700,250 | 742,755 | 77,893 |

### Public, private partnerships, outsourcing etc

The Department currently does not have any public-private-partnerships.

## Financial Management:

### Strategies to address audit queries

The Premier’s Office has established an internal audit component and audit committees to service the whole province including this department. The compliance component within the departments also conducts risk assessment workshops and regular inspections to identify critical risk areas and shortcomings and recommends appropriate corrective measures on deviations. The component is also responsible for making follow-ups on audit findings by the office of the Auditor General and ensures that corrective measures are implemented by the department.

### Implementation of PFMA

| PFMA IMPLEMENTATION | STATUS |
| --- | --- |
| Clause 42 1(a) (2) and (3) of PFMA re : drawing up inventories of assets and liabilities to be transferred, both us and transferee to sign inventory; | Inventory transferred to RAL (Roads Agency Limpopo) was signed off by both institutions |
| Clause 43 (3) of PFMA re submit details of virements within 7 days to Treasury and MEC; | This is not happening yet, but we keep a schedule of all virements made in the year. |
| Part 2 section 3.2.1: says we must do risk assessment annually - this seems very onerous to me. It is a massive exercise and are we really going to do it annually? Can we not just do an annual brief update on our initial one, and maybe do a major exercise every three years? | We are currently attempting to finalise the first one and we can indicate that it is actually not feasible to do one annually as we would never implement the controls and review in the same year of the assessment to establish effectiveness. Therefore, the exercise would be futile. |
| Part 2 section 3.21: says that the AO must provide a certificate to treasury by 30 June 2001 indicating that the risk assessment has been completed and that the fraud plan is completely operational. Did we comply? | The risk assessment also has a reviewed fraud prevention plan to be unveiled after a few changes. |
| Part 2 section 4.2.1: says that the AO must advise the EA, treasury and the AG of an criminal charges it has laid against any person in terms of section 86 of the Act (financial misconduct). Are we complying? We do have some such criminal cases, relating to the tender frauds in building. | The information is captured in the Annual Report. There is a section for charges of all kinds including, financial misconduct. Sect 86, is more specific to AO's and specific kinds of breach and negligence, which has not occurred. |
| Part 2 section 4.3.1: says that the AO must report to the EA, DPSA and PSC regarding the outcome of disciplinary procedures for financial misconduct. Are we complying? | This item is covered in the Annual report. The labour relations section submits a report to the Office of the Premier & DPSA |
| Part 2 section 4.3.3 and 4.3.4: says that the AO must annually- submit to treasury and the AG a schedule of info relating to disciplinary proceedings for financial misconduct. Are we complying? | This item is covered in the Annual Report |
| Part 3 section 5.1.1 says that the EA must approve our strategic plan. Are we getting the MEC to approve the strategic plan in writing? | Yes, the MEC is approving the strategic plan in writing |
| Part 3 section 5.2.1 says the we must submit our strategic plan to the legislature at least 7 days prior to the discussion on the dept's vote. Did we comply- Part 2 section 4.21? | The legislature, Treasury& Premiers office have been served with our strategic plan as and when they request it. |
| Part 3 section 5.2.2 details things which must be in the strategic plan. Are we complying? | We are complying with basic requirements. |
| Part 3 section 5.3.1 says that we must submit written quarterly reports to the EA. Are we complying? Not as far as I know | No. We do quarterly reports to treasury and the Premier’s office. |
| Part 4 section 7.3.1 and Part 5 section 10.2.4 say that we must revise all fees charges and rates at least annually. I don't think we are complying. The market-related rentals were last revised more than a year ago, as far as I know. | The rates that have been revised are for all other things except properties. |
| Part 4 section 7.3.2 says that information on the tariff structure must be included in the annual report. Did we comply? | The section on the financial management report on Tariff policy was filled in. |
| Part 4 section 8.3.5 says that the payroll report must be returned to the CFO after being certified, and the AO must ensure that all paypoint certificates have been received on a monthly basis. | The paypoint managers have been delegated to perform the task of certificates and there is a monthly reconciliation between Finance & HR for payments |
| Part 5 section 11.4.3 says that all debts written off must be disclosed in the annual financial statements, indicating the policy in terms of which the debt was written off. Are we complying? | The policy was attached to the financial statements and all debts written off were reported. |
| Part 5 section 11.5.1 says that interest must be charged on debts to the state. Are we complying? What about interest on the rental arrears? | We are complying in most cases, Treasury issues out interest to be used monthly on all arrear accounts |
| Part 7 section 18.3.1 and section 18.4.1 give details of things which must appear in the annual report - did we comply in full with both sections? | Yes, we have complied. |
| Part 8 section 19.8.1 says that the AO of a department controlling a trading entity must provide monthly info on the trading entity in the monthly report of the dept. Are we complying? | The early warning has information on the transfers and expenditure against the dept. The required detail is not clear. |
| Part 8 section 21.2.4 says that all gifts, donations and sponsorships received must be declared as a note to our annual financial statements. Did we comply? | Yes, we have complied. |

# Part C: Background information

## Appendix one: Analysis of service delivery environment

Roads and Bridges

Roads Agency Limpopo (RAL), a company owned by the Government, is in terms of the Northern Province Roads Agency Act 11 of 1998 responsible for the provincial road network and related structures in terms of planning, design, construction and maintenance. The Board of the RAL is appointed by, and reports to the MEC for Public Works. The provincial network consists of over 21 218 km of road of which 6 020 km are surfaced and over 15 198 km are gravel. This includes all major roads (surfaced and unsurfaced) linking towns, villages and settlements in the Province. However, it does not include streets in towns and villages, which are the responsibility of the local sphere of government.

The Department has produced plans for redefining national, provincial, district and local roads in the province. These plans have been sent to the National Road Agency and to District Municipalities for comment. If implemented, the plans will result in the redefinition of a number of provincial roads as national and district roads, and a reduction in the size of the provincial road network to approximately 9 000 km.

The Department still retains approximately 4 000 personnel in the routine roads maintenance function. The Department and the RAL entered into an agreement whereby the Department will continue to carry out routine maintenance on the roads using its internal staff and equipment until such time as the routine road maintenance may be outsourced. The Department is engaged in negotiations with the personnel of the small remaining construction unit and unions as part of the process of outsourcing the construction unit.

Property Management and Building

The Department is responsible for providing the provincial government with its property requirements. This involves renting of private properties and construction and maintenance of government-owned properties. The provincial property portfolio which is managed by the Department of Public Works consists of 900 residential houses, 12 blocks of flats, three large former homeland government complexes with 21 office blocks, 34 other office blocks and 44 other smaller regional office complexes, health and education buildings, museums, cultural centres, buildings in game parks and youth camps.

Activities related to the property management function include managing lease agreements; appointing values; managing land matters; managing accommodation arrangements for politicians; managing the processes of disposal of property and transfer of property to local government; collecting rent revenues; management of the provincial property asset register; inspecting properties and reporting required maintenance work to landlords or to the Department’s Building section, and managing gardening, cleaning and security as well as leasing out under-utilised facilities at market related rentals.

All of the above functions are carried out internally, apart from the security function, which is partially outsourced. Security on most buildings is outsourced. The Department carries out the cleaning and gardening functions internally.

Activities related to the building function include: provision and maintenance of mechanical and electrical installations in provincial buildings; routine, periodic and preventative maintenance of buildings; rehabilitation of buildings, construction of new buildings; and design of new buildings. All design and major contractual work has been outsourced for some time. At present, the Department carries out most routine building maintenance and some preventative maintenance internally.

### Policy changes and trends

The Department of Public Works still has a long way to go in order to achieve its goal of consistently high standards of service. The Department started from a low base in 1994, having inherited a multitude of problems from the previous administration, including huge backlogs of infrastructure in previously disadvantaged areas, over-staffing in some areas, and human resources which had been disastrously underdeveloped.  The core function of the Department of Public Works is to provide and maintain infrastructure. Increasing personnel expenditure due to rising employment costs has led to the crowding-out of other expenditure, making it increasingly difficult for the Department to fulfill its mandate of providing and maintaining infrastructure.  This situation informs the plans described in this document to restructure the Department with the aim of releasing and generating resources for service delivery. Training of personnel and affirmative action (particularly with regard to gender) are also key strategic priorities of the Department. In the 2004/2005 year, the Department will focus on Service Delivery Improvement (SDI) Programmes in the areas of Roads and Bridges, Properties and Facilities Management and Building. These programmes will assist the Department with regard to efficient business processes, service and workflows, transparency, accountability and effective reporting. Five-year strategic plans (incorporating service delivery improvement programmes). Service delivery is further enhanced through the implementation of the following policies and plans:

- Human Resource Plan

- Information Plan

- Affirmative Action Plan

- Structural Plan

- Service Delivery Improvement Plan

- Facilities Plan

- Service Delivery Standards

### Environmental factors and emerging challenges

Roads and Bridges

We allocated R539 million to the Roads Agency Limpopo. This budget included the last trance of the conditional grant from National Treasury of R91 million, which was allocated for flood damage repairs of 224 km of roads. The rest of the budget was spent on tarring 124 km of roads; repairing, resealing, and rehabilitating 225km. Four (4) bridges were constructed and three (3) were upgraded and repaired. A total of 225km of roads were regravelled. All of these projects were successfully completed on time and within budget.

Property and Facilities Management

An amount of R94,3 million was allocated to the Property and Facilities Management programme. The department made good progress in terms of developing and maintaining an improved Provincial property asset register. The major portion of the register is now complete with all known properties listed. As part of our disposal of redundant properties, 117 residential properties valued at R12.7 million were sold. All the properties were sold to previously disadvantaged individuals, and 51% of these individuals were women.

Government Buildings

We managed 819 projects worth R277 million for the Department of Education. These projects were allocated to private sector construction companies through the preferential procurement process. This resulted in the construction of 2108 new classrooms; renovations to 61 schools; repairs to 10 flood-damaged schools; repairs to 4 storm-damaged schools; maintenance of kitchen equipment, electrical connections and other repairs to colleges of education in all six districts; repairs to 11 marking centres; upgrading of a special school; upgraded two technical education colleges; upgraded one teacher’s training college and constructed additional offices for the Department of Education Head Office.

PGDS – Now known as the LDGS

According to the Limpopo Growth and Development Strategy (LDGS) document, the provincial profile is as follows:

- The Province covers an area of 123 910 square km which is 10.2 % of national.

- The Province has a population of 4.9m, which is 12.1 % of national.

- The Province is 89 % rural in nature.

- A relative high proportion of the population is younger than 15 years of age.

- The Public Sector is the highest provider of employment opportunities.

- The unemployment rate in the Province is presently 46 % (Census 1996).

- HIV and AIDS infection in estimated at 17 persons per 100 with a potential to affect our young people most.

#### Employment, income and occupational categories of staff in the department

Table 5: Occupational categories

| Types of Occupation | Number | Percent of total |
| --- | --- | --- |
| Managers | 267 | 4,81 |
| Professionals | 6 | 0,06 |
| Technical | 39 | 0,54 |
| Clerical | 799 | 11,11 |
| Sales and services | - | - |
| Skilled agriculture | - | - |
| Artisan | 768 | 10,68 |
| Operators | 248 | 3,45 |
| Elementary occupations | 4719 | 69,22 |
| Government Information & Technologies Office | 6 | 0,14 |
| Unemployed | - | - |

Table 6: Income distribution

| Income per month | Percent of total |
| --- | --- |
| None | - |
| R1 - R500 | - |
| R501 - R1000 | - |
| R1001 - R2500 | 0,88 |
| R2501 - R6000 | 85,18 |
| R6001 -R11000 | 12,11 |
| > R11001 | 1,83 |
| Unspecified | - |
| Total | 100 |

#### The provincial infrastructure for which the Department is responsible is deteriorating due to inadequate funding for maintenance, and the rate of addressing the backlogs of infrastructure in previously disadvantaged areas is too slow. The February 2000 floods caused further extensive damage to infrastructure.

### Evaluation of current implementation performance

We anticipate spending all money on behalf of client departments; namely, the Department of Education and the Department of Health and Welfare and other client departments.

## Appendix two: Organisational information and the institutional environment

In order to facilitate the implementation of the roads, building and property functions, the Department maintains four support directorates in the areas of human resource management, information management, financial management and corporate services

Human Resource Management

The mission of this directorate is to render policy analysis functions, staff advisory and staff management services. The directorate is responsible for the provisioning of personnel within the framework of the new Public Service Act and Regulations, as well as the Batho Pele strategy. This includes human resource planning; interfacing with the job market to gain appropriate skills for the Department; and staff advisory services is for internal HR functions. The Department’s Human Resource Plan and the Department’s Affirmative Action Plan are contained in this document.

The Workplace Relations component of this directorate is responsible for the development and maintenance of sound labour practices as well as the democratisation of the work place. The Management Services sub-directorate is responsible for conducting job analyses and evaluations, monitoring and advising on productivity as well as structural analysis. The Community Development section is responsible for the community based public works programme.

GITO

The Information Management Program will act as an enabler in the improvement of delivery of services to stakeholders which aims at putting the Department to a competitive advantage. The Program will focus on management control system development and implementation in the areas of telecommunications infrastructure systems development for all components of the department; information management and business continuity plans.

The aims of these programmes are:

- To enable the Department to maintain reliable databases

- To enable the Department to maintain assets registers

- To enable the Department to plan maintenance programmes better

- To enable the Department to control projects better

- To improve communications and information management within the Department.

Financial Management

The main functions of this Directorate is to render support services to the Department in terms of co-ordination of the budget, control over stores, expenditure control, and control over procurement of goods and services. The Directorate is engaged in the following internal financial management programmes:

Programme scope of objectives:

- Budget planning and control

- Procurement Services

- Assets and Inventory management

- Render Financial Advice

- Expenditure control/management

- Regulate Financial Norms and Standards

- Development of Financial Managers

- Risk Management

- Supply chain management

Measures to meet objectives:

- Aligned strategic planning and processing

- Providing resources

- Adherence to guidelines

- Monitoring and reporting

- Internal control systems development

- Training, coaching and mentoring

- Culture reform

Compliance and inspectorate (responsible for investigation and reporting on irregularities, co-ordination of response to the Auditor General, ensuring the application of laid down financial procedures and also ensuring the economic utilisation of government resources)

Corporate Services

This programme seeks to render support to the Department through the following services:

- Maintaining proper records for the Department.

- Auxiliary services, including transport and office services

- Customer care

- Manage Shared Service Centres (SSC’s) in districts

- Management of tender office

### Organisational design

- Organogram

- Reporting lines of senior managers down to deputy-director level (with names)

| NAME | JOB TITLE | LEVEL |
| --- | --- | --- |
| MAVUSO EV | SNR MANAGER | 13 |
| RALULIMI RT | PROJECT MANAGER | 11 |
| MACHETHE MS | MANAGER TECH SERVICES | 11 |
| MCHAVI ND | PROJECT MANAGER | 11 |
| SEKHU MJ | CONTROL LAND DEVELOPER | 11 |
| MUBVA-CHABALALA BT | MANAGER FINANCIAL MAN | 11 |
| FLATELA TT | MANAGER ADMIN | 11 |
| MASHELE RM | MANAGER ADMIN | 11 |
| MPE I | MANAGER COMMUNICATION | 11 |
| MAANDA TP | MANAGER IM | 11 |
| MALOMANE MO | MANAGER IT | 11 |
| TSHIKONELO NJ | PROJECT MANAGER | 11 |
| KEKAE WL | PROJECT MANAGER | 11 |
| MOJAPELO S | PRINC ARTISAN SUP | 11 |
| NDLOVU SA | PROJECT MANAGER | 11 |
| MUVHANGO TE | PROJECT MANAGER | 11 |
| KEKANA NM | PROJECT MANAGER | 11 |
| TSHIVHENGWA NF | PROJECT MANAGER | 11 |
| MADALA NB | MANAGER TECH SERVICES | 11 |
| BOTHA JJC | PROJECT MANAGER | 11 |
| MASHAMBA TC | PROJECT MANAGER | 11 |
| MAGUWADA NR | PROJECT MANAGER | 11 |
| MATHONSI HA | PROJECT MANAGER | 11 |
| RAMASWIELA F | MANAGER ADMIN | 11 |
| MUNZHEDZI MD | PROJECT MANAGER | 11 |
| RAMBAU RE | MANAGER TECH SERVICES | 11 |
| NKWINIKA ME | MANAGER ADMIN | 11 |
| THEMBO SB | PROJECT MANAGER | 11 |
| MOGAKANE S | MANAGER ADMIN | 11 |
| MANAMELA MP | CHIEF TRAINING OFFICER | 12 |
| MAPHALLA MS | MANAGER ADMIN | 12 |
| JOHN V | MANAGER ADMIN | 12 |
| NKOSANA GA | PROJECT MANAGER | 12 |
| MIYENI TN | PROJECT MANAGER | 12 |
| MEHALE NR | SNR PROJECT MANAGER | 12 |
| MOTHAPO MC | MANAGER ADMIN | 12 |
| RIKHOTSO KW | PROJECT MANAGER | 12 |
| NTHABALALA HR | PROJECT MANAGER | 12 |
| MOGANO MR | PROJECT MANAGER | 12 |
| CHOSHANE PD | PROJECT MANAGER | 12 |
| BRAUNS BG | PROJECT MANAGER | 12 |
| MAVUNDA NF | MANAGER ADMIN | 12 |
| NEPFUMBADA JN | MANAGER ADMIN | 12 |
| MALAN SS | MANAGER PERS MANAGEM | 12 |
| KASEKE LL | MANAGER PERS MANAGEM | 12 |
| LEKGAU RM | MANAGER PERS MANAGEM | 12 |
| RAPATSA MI | CHIEF TRAINING OFFICER | 12 |
| SHIVAMBU JJ | MANAGER FINANCIAL MAN | 12 |
| MPHETSO TW | MANAGER FINANCIAL MAN | 12 |
| MAKHANI NJ | MANAGER FINANCIAL MAN | 12 |
| MORIBANE MW | MANAGER ADMIN | 12 |
| NKUNA ME | MANAGER ADMIN | 12 |
| CHIMANZI J | MANAGER IT | 12 |
| KRIEL IJG | SNR PROJECT ROADS | 12 |
| MAUPA EM | MANAGER ADMIN | 12 |
| MAKOMENE MP | MANAGER ADMIN | 12 |
| PIENAAR AJ | SNR PROJECT MANAGER | 12 |
| MABOTJA NM | MANAGER TECH SERVICES | 12 |
| NDWALANE FFF | SNR PROJECT MANAGER | 12 |
| MASHEGO SE | MANAGER ADMIN | 12 |
| PHEEHA RP | MANAGER TECH SERVICES | 12 |
| SEROTE NE | SNR PROJECT MANAGER | 12 |
| KRUGER JL | MANAGER ADMIN | 12 |
| MOLONGWANA BM | MANAGER ADMIN | 12 |
| MUNERI ME | SNR PROJECT MANAGER | 12 |
| MASUPA NK | SNR PROJECT MANAGER | 12 |
| TSHIVHINDA MM | MANAGER ADMIN | 12 |
| NEMAULUMA MD | MANAGER ADMIN | 12 |
| BALOYI SB | MANAGER ADMIN | 12 |
| MTHOMBENI QM | SNR PROJECT MANAGER | 12 |
| HLUNGWANE D | MANAGER TECH SERVICES | 12 |
| MANYELO DM | MANAGER ADMIN | 12 |
| MATHABATHA RR | SNR PROJECT MANAGER | 12 |
| SETWABA MM | MANAGER TECH SERVICES | 12 |
| SITHOLE GM | MANAGER ADMIN | 12 |
| RATAU DS | SNR PROJECT MANAGER | 12 |
| NGOBENI NZ | SNR PROJECT MANAGER | 12 |
| CHILOANE DD | MANAGER TECH SERVICES | 12 |
| KEKANA PW | SNR MANAGER | 13 |
| RAMANYIMI T | SNR MANAGER | 13 |
| MATOME SM | SNR MANAGER | 13 |
| DLAMINI LG | SNR PROJECT MANAGER | 13 |
| BAIKIE TU | SNR PROFESSIONAL | 13 |
| PHIRI H | SNR PROFESSIONAL | 13 |
| MASWANGANYI TB | SNR PROJECT MANAGER | 13 |
| MASHALA MS | SNR PROFESSIONAL | 13 |
| KASEKE A | SNR PROJECT MANAGER | 13 |
| MASHA SCB | SNR PROJECT MANAGER | 13 |
| NENGUKE AK | SNR PROJECT MANAGER | 13 |
| GHOOD F | SNR PROFESSIONAL | 13 |
| HLONGWANE MS | SNR MANAGER | 13 |
| MOTHIBI JB | SNR MANAGER | 13 |
| BELL NJ | SNR PROFESSIONAL | 13 |
| MADALE CT | SNR MANAGER | 13 |
| NEPHAWE NF | SNR MANAGER | 13 |
| KUTAMA MD | SNR MANAGER | 13 |
| SEBOKO MM | SNR MANAGER | 13 |
| GHOOR EI | SNR MANAGER | 13 |
| MALELE T | GENERAL MANAGER | 14 |
| MKHUMANE NH | CHIEF FIN OFFICER | 14 |
| MSWELI PP | GENERAL MANAGER | 14 |
| NAIDOO R | GENERAL MANAGER | 14 |
| KHUNOU EM | GENERAL MANAGER | 14 |
| SHINGANGE R | SNR GENERAL MANAGER | 15 |

- Map showing districts and maintenance camps

### Delegations

The MEC has issued adequate delegations to the Head Of Department (HOD) and to the General Manager : Human Resources Management

in terms of the Public Service Regulations (PSR). The HOD has issued financial delegations to all relevant managers in terms of the PFMA.

### Capital investment, maintenance and asset management plan

Building

On-going building projects

The building services programme is presently managing a total 22 on-going projects worth R16.6million 4 will carried forward to the 2005/06 financial year.

Planned projects

For the 2004/05 financial year, the programme has planned for the construction of housing units at roads camps and two new office blocks

at a total sum of R27.3million. An amount of R9.3million also been budgeted for major refurbishment of government offices.

Capital Stock

The directorate has inherited a capital stock of buildings that were previously managed by three administrations and which had not been maintained for a long period. There has therefore been a backlog, which has been steadily growing since 1994, due to inadequate funding of maintenance. As a result, only 30% of the existing capital stock is in a good condition, 20% is in a fair condition and 40% in bad condition. Clearly, the current funding levels are hugely inadequate and the maintenance backlogs have now led to immense refurbishment work. In terms of the directorate’s infrastructure backlog redress strategy; an annual budget of R53.9million is required for this purpose. For the 2004/05 financial year the directorate’s total budget for new office needs, day-to-day routine maintenance and planned maintenance activities that will prevent further deterioration is R55million. In spite of all these competing needs a sum of R9.3million has nonetheless been set aside to address part of the refurbishment work, which is prioritized on the basis of compliance with relevant statutes.

Roads (departmental maintenance)

25% of departmental capital equipment (graders, bulldozers, frontend loaders, trucks, ldv’s) is in good order. 30% is in a

medium condition, and 45% are in need of major repairs. Each year the department spend money to repair them to a serviceable level.

This year, the programme will be spending 30,5million for this purpose. This amount however, still falls far short of the total we would

require to bring all the equipment to  working order.

Roads (Road Network – Roads Agency Limpopo)

The RAL is responsible for the provision and maintenance of provincial roads. The total provincial road network consists of 22560km’s,

of which 6500 is tarred and 16060 is gravel. There are approximately 850 bridges. The tarred or surface road network’s conditions is

as follows:

6% very poor, 12% poor, 32% fair, 34% good and 16% very good.

The un-surfaced networks condition is as follows:

10% very poor, 20% poor, 39% fair, 27% good, 4% very good  according to gravel quantity.

This year (04-05), the Road Agency will spend R48.5m on rehabilitation of roads, R80m on repair, re-seal and fogspray and R96m on regravelling

projects through the Gundo Lashu (labour-intensive) programme. In addition to this, R24.6m will be spent on bridge repair.

The strategy for yearly projects is that all projects should be approved by July of the preceding year, designs should be ready by December, and

advertisements and tendering should be completed by the end of March. This will ensure that projects can begin as early in the financial

year as possible.

Some of the current projects are:

- Makonde-Masisi road, and

- Burgersdorp bridge

### Personnel

The table below outlines the total staff establishment of 6852 broken down on a per region basis.

Staff establishment breakdown

| cENTRE | Total staff |
| --- | --- |
| Head Office | 337 |
| Capricorn | 967 |
| Vhembe | 1768 |
| Mopani | 1512 |
| Sekhukhune | 772 |
| Waterberg | 1029 |
| Bohlabela | 467 |
| TOTAL | 6852 |

### IT systems

| Program | Information required | Resource from which to obtain | Method of obtaining information | Budget |
| --- | --- | --- | --- | --- |
| Rationalisation of departmental information and development of management plans, quarterly reports, newsletter, annual reports to citizens in terms of PFMA, New Public Service Regulations, New Treasury Regulation and other relevant policy and regulation documents. | All relevant policy documents such as PFMA, New Public Service Regulations, New Treasury Regulation. All activities of the department including programmes, business plans, priorities, budget, reports and any relevant information | Departmental resources and Internet access for Government policy documents | E-mails, Internet, Faxes, telephones, circulars | 100 000.00 |
| Development of electronic messaging software, departmental Web Site (linked to the Office of the Premier), security and disaster recovery management system. | Provincial information on infrastructure and socio-economic data. | Departmental Resources | Meetings, fax, telephone | In-house |
| Development of knowledge-based provincial database which is linked to a Geographic Information Management System | Data from Public, stakeholders, Provincial departments and Parastatals. Infrastructure backlogs and socio-economic data | DFID assist in the form of grant or donation. Stakeholders and other provincial departments. | Appointment of consultants to collect and collate required information. Meetings, databases and Internet facilities. | Office of the Premier co-ordinate the funding of the project. |
| Deployment of telecommunication Infrastructure and integrated electronic messaging in seven regional offices. | Regional offices of the department, Eskom and Telkom. | Consultants, contractors and internal staff. | Internet, databases, faxes and other media. | R2 million |
| First annual review of SLA’s with SITA | Business needs analysis requirement for IT/IS business assessment for the Department and Development of outsourcing plan | Department and SITA | Business Agreement, incorporation agreement, service level agreement, value propositions, mail, faxes, telephone, meetings and memoranda | In-house |
| Information Resource Management | User needs and requirements | Government Institutions, private sector, academic institutions | Library book purchases, subscriptions, research and internet |  |
| Administration | Finance, personnel, equipment purchases and maintenance, stores, correspondence and records, assets, tenders and contracts, suppliers, etc. | FINEST database, BAS, PERSAL, MS OFFICE Applications | Rollout of the integrated electronic messaging infrastructure; Database interrogation. |  |

Information Systems for Monitoring of Progress

- BAFMIS

- Roads Production and Planning Information System

Training

Training on the use of IT systems is provided as and when required.

### Performance management system

The Performance Management System tool was implemented in the department in April 2002. The first annual final evaluation was successfully completed in April 2003. Currently busy implementing the 2004 final evaluation.

### Financial management

Systems that are in place to ensure sound financial management

Electronic Systems in place

- BAS, FINEST, PERSAL

- Treasury to introduce inventory management systems.

Internal Control Systems in place

- Purchase Sub-directorate

- Expenditure Control

- Budget Control

- Inventory and Asset management

- Revenue and Systems

- Compliance

Training which will be undertaken in the coming year to improve financial management capacity in the department

- Three officials undergoing CIMA COURSE

- Officials to attend the SALGA Courses

PFMA Foundation

REAL

GRAP

FINANCIAL STATEMENTS

INTERNAL CONTROL & RISK MANAGEMENT

PUBLIC SECTOR ASSET MANAGEMENT

### Audit queries

See attached annexure 1

### Implementation of PFMA

In order to ensure the successful implementation of the PFMA, the department has identified objectives and actions which are

reflected in the table below:

| Objective | Action |
| --- | --- |
| BUDGET PLANNING | Activity-based budget |
|  | Constant budget plan |
|  | Timeous capturing and activating of budgets |
|  | Monitoring of budgets |
|  | Compliance with regulations |
|  | Compliance with sec40 (4) b-c monthly reports to the EA and Treasury. Monthly reconciliation |
| REVENUE PLANNING | Increased collection of revenue |
|  | All moneys collected payable to the Provincial Revenue |
|  | Strategic revenue planning |
|  | Timeous capturing of receipts |
|  | Efficient bookkeeping |
|  | Effective Debt Management |
| EXPENDITURE MANAGEMENT | Expenditure control |
|  | Accurate, timely and responsive reports |
|  | Reduced payment cycle |
|  | Safe custody of vouchers & face value documents |
|  | Payroll management |
| ASSET AND INVENTORY MANAGEMENT | Restructuring of stores management |
|  | Stock provision |
|  | Disposal of obsolete and redundant moveable assets |
|  | Stores inspection |
|  | Asset management |
|  | Purchases and acquisitions |
| SYSTEMS MANAGEMENT | Administering systems – PERSAL, BAS, FINEST |
| MANAGEMENT OF PURCHASES | Monitoring procurement policies & regulations |
|  | Implement internal controls for procurement |
|  | Set up and communicate procurement process |
| RISK MANAGEMENT | Risk assessment |
|  | Communication of Risk strategy |
|  | Implementation of Phase III of the risk management system Appoint a manager to run the program |
|  | Fraud Prevention |

GLOSSARY