FOREWORD BY THE MEC

The Department of Public Works remain with a challenge to contribute to economic growth and socio-economic transformation through the provision of strategic leadership in sustainable provincial government infrastructure development. In terms of this challenge, the department therefore aims to give effect to the Inter- Governmental Relations Framework whose main objective is good co-operative governance to ensure a better life for all through: -

- The provision of sustainable provincial government infrastructure;

- Management of provincial land and buildings

- Job creation, poverty alleviation and skills transfer.

The signing of the Construction and Property Charter in March this year seeks to reposition the construction industry such that it responds to the critical issues such as empowerment, particularly women and the youth. To this end, the Department will position itself to relate directly to the Provincial Growth and Development Strategy in terms of planning, development and management of provincial government infrastructure.

In an endeavor to alleviate poverty, create jobs and transfer skills, the department will put emphasis and resources towards the effective implementation of the Expanded Public Works Programme. This will require a more concerted effort towards ensuring that Labour Intensive methods are applied across all EPWP projects.  The development of the five year business plan will enable us to vigorously roll out EPWP to provincial departments and municipalities to ensure that its implementation is in compliance with the Division of Revenue Act.

The department will continue using its property portfolio and the Expanded Public Works Programme for training, job creation as well as the provision and maintenance of infrastructure to contribute towards the reduction of unemployment in the Province. A maintenance plan for the provincial property portfolio has been developed to address both maintenance backlogs as well as future maintenance programmes.

During the coming years, the department, in pursuit of its vision, mission and strategic goals, will increase its flexibility in rendering effective services, embark on waste elimination and minimise lead times in responding to the needs of institutions and the people we serve.

HON. M. SEMENYA

MEMBER OF THE EXECUTIVE COUNCIL (MEC)

TABLE OF CONTENTS

Page

PART A: STRATEGIC OVERVIEW

- Overview by the Accounting Officer							3

- Vision											4

- Mission										4

- Values											5

- Sectoral situational analysis								5

- Legislative and other mandates							6

- Broad policies, priorities and strategic goals						7

- Information systems to monitor progress						7

- Description of strategic planning process						8

PART B: PROGRAMME AND SUB-PROGRAMME PLANS

- Overall programme structure								9

- Programme 1: 	Administration							9

- Programme 2: 	Infrastructure development

- Programme 3		EPWP								17

- Plans per Executive Programme							25

PART C: APPENDIX

14.	Appendix 1: Departmental Budget  							48

PART A

STRATEGIC OVERVIEW

OVERVIEW BY THE ACCOUNTING OFFICER

The continued focus of the Department of Public works is to provide leadership in the delivery of provincial government buildings infrastructure and the management of immovable assets. This is a challenge that requires continuous business re-engineering in order to fast track infrastructure delivery. It is against this background that the Department went on an organizational development process resulting in the crafting of new core mandate, vision and mission. Consequently the organizational structure was reviewed in line with the new mandate.

In the financial year 2007/08, a concerted effort will be made to ensure that the pace at which the Expanded Public Works Programme is accelerated. This will be realized through the implementation of the Five Year Business Plan and the four sectoral strategies. Key to the implementation of these plans is to continue assisting government departments and municipalities in developing EPWP aligned programmes, which so far has been a real problem.

Commencing this financial year, my Department will roll out a five year maintenance plan for government buildings to ensure that they meet the Occupational Health and Safety Standards.

We have commenced a process to conduct space audit which is aimed at determining the office accommodation needs of the provincial government. This audit will indicate clearly, what the office accommodation needs for government departments are and once the audit is completed, all government departments will be housed in an Institutional Zone, making government services more accessible.

The process to compile a reliable asset register for the provincial government is underway and will be completed soon, indicating all known and unknown immovable assets.

I therefore commit myself and the entire staff of the Department to effectively render efficient service delivery to the people of our Province.

Mr Johannes Rantete

Head of Department

VISION, MISSION AND VALUE STATEMENTS

In 2006, the department formulated the following vision, mission and strategic goals informed by a revision of the core mandates of the department. The revised core mandates are: -

- Facilitate and coordinate the provision of provincial government building infrastructure

- Management of provincial land and buildings

- Coordination of the implementation of Expanded Public Works Programme

Vision

A leader in the provision and management of provincial government land and buildings

Mission

Optimal utilization of resources in the provision and management of provincial land and buildings and the coordination of the implementation of Expanded Public Works Programme.

Strategic goals

- Sustainable provincial building infrastructure to support service delivery

- Proper maintenance of government buildings to attain functional and economic  benefit, through the development and implementation of comprehensive maintenance plan

- Implementation of capital works projects within time lines, budgets and quality in line with IDIP initiatives

- Efficient Management of immovable property utilized for government service delivery

- Poverty alleviation, skills transfer and job creation

- Achieve EPWP goals using DPW capital and maintenance budgets

- A well coordinated Provincial EPWP

- Promotion of Broad Based Black Economic Empowerment

- Intensify implementation of preferential procurement policies in compliance with relevant Government procurement prescript.

- Good corporate governance

- Compliance with relevant legislative prescripts

- Improve overall performance

- Intensify implementation of Service Delivery Improvement programme

- Implement Human Resource development Programme

Values

The Limpopo Department of Public Works prides itself on the following core values:

- Professionalism

- Humility

- Adherence to the Batho Pele principles

SECTORAL SITUATIONAL ANALYSIS

Service Delivery Environment

PROGRAMME 1 : INFRASTRUCTURE

Professional Services

The department is responsible for the provision and management of professional services in accordance with professional norms and standards, the coordination and development of infrastructure planning and design objectives in line with the Provincial Infrastructure Development Plan. Most of the specialized design and contractual works are outsourced. In the future, the planning of provincial infrastructure will be conducted in an integrated approach through the Provincial Infrastructure Coordinating Unit in which departments such as Education, Health & Social Development, Local Government & Housing and Roads & Transport will serve. It is expected that District Municipalities will participate in this Unit once it is fully and properly functioning.

Project Management

The successful execution of the Provincial Infrastructure Development Plan is much dependant on the competency and professionalism of this programme. The programme is responsible for the management of contracts on behalf of client departments. A social facilitation role is also played by this programme to ensure participation of the community in decision making process of government funded projects.

Real Estate

The department manages and also provides land and accommodation to provincial departments. This involves leasing of private properties for use by provincial departments; appointment of valuers for valuation of immovable properties government intends renting or buying; management of the process of disposal of immovable properties, the transfer of property to local municipalities; provision of accommodation to politicians and finally, the safe keeping of an up to date provincial property asset register.

Maintenance

The department is currently responsible for the maintenance of provincial owned properties, both offices and residential houses and flats, which are for exclusive use by the departments as well as those which are used by more than one department such as the three Government Complexes in Giyani, Lebowakgomo and Thohoyandou. Maintenance of other provincial owned properties such as health facilities and schools is the responsibility of the respective departments under whose custody the facilities fall. The buildings under the management of this department require serious repairs since they have not had sufficient planned and preventative maintenance for sometime now. This poses occupational health and safety challenges, especially because of insufficient budget to carry out the required maintenance work as well as managing increased volumes of day-to-day repairs.

PROGRAMME: 3

Expanded Public Works Programme

The levels of unemployment and poverty compelled Government to introduce the Expanded Public Works Programme as one of the range programmes aimed at addressing this problem. This is an infrastructure driven programme which is aimed at the promotion of skills development and labour intensive methods.

Governance Environment

The core service delivery drivers of the department are programmes that are underpinned by a conducive governance environment. The department attempts to improve work efficiency, skilling of personnel, sound financial management, proper utilization of resources and Information and Communication Technology (ICT) Services.

LEGISLATIVE AND OTHER MANDATES

The Constitution states that provincial governments are only responsible for Public Works functions, which relate to provincial functions and provincial state property. Hence, National Public Works directly undertakes functions, which relate to national functions in the Province, such as the construction and maintenance of facilities and properties, which are of national competence. The Premier has assigned Provincial Public Works functions to the Department of Public Works. The operations of the Department are governed by the legislation governing the built environment professions, such as the Acts governing the Engineering, Quantity Surveying and Architecture professions. The Department has a large workforce engaged in building maintenance and property facility activities and therefore needs to take cognisance of the Occupational Health and Safety Act. Building construction activities are also governed by the same environmental legislation.

The White Paper on Public Works (Public Works Towards the 21st Century, 1997) provides a framework which the Department adopted in endeavouring to stimulate economic activity through job creation and empowerment of emerging entrepreneurs with particular bias towards previously disadvantaged individuals. In addition, the Department has adopted a matrix type of organisational structure, rather than a divisional organisational structure, in order to enable the adoption of project management techniques for the management of projects.

Like other departments, the Department is also guided by national policies aimed at transforming the public service, such as Batho Pele and the White Paper on Transformation of the Public Service. In addition, the Department is bound to work within the prevailing regulatory framework, including  (inter alias) the Public Service Act, the Public Service Regulations, Public Finance Management Act, Treasury Regulations, and the Preferential Procurement Policy Framework Act. The Department is also bound by nationally negotiated agreements regarding conditions of service for its employees. Other mandates that relates to coordination of EPWP and development of Provincial Infrastructure Plan are now added to Provincial Public Works.

BROAD POLICIES, PRIORITIES AND STRATEGIC GOALS

Departmental Broader Policies

- P.F.M.A.

- Treasury Regulations, 2002

- Public Service Regulations, 2001

- Labour Relations Act, 2002

- Skills Development Act, 1998

- Skills Development Levies Act, 1999

- Employment Equity Act 1998

- Basic Conditions of Employment Act 1997

- White Paper on Transformation of Public Service

- Promotion of Access to Information Act

- Construction Industry Development Board Act

- Preferential Procurement Policy Framework Act

- Occupational Health and Safety Act

INFORMATION SYSTEMS AND TO MONITOR PROGRESS

The department’s GITO endeavours to provide and maintain robust inter - operable and integrated systems; implement and align IT programmes and projects with the department’s strategic goals and objectives; acquire and maintain a functional network infrastructure that supports Information Communication Technology (ICT) as well as Information Technology security. GITO considers the following key imperatives as part of the IS strategy:

- Alignment to the Business Strategy

- Alignment with the e-Government Strategy

- Integration of business systems

DESCRIPTION OF THE STRATEGIC PLANNING PROCESS

The Strategic Planning process is informed by the following broad government agenda:

- State of the nation address

- State of the Province address

- Provincial Growth and Development Strategy

- MEC’s Budget Speech

- Municipal Integrated Development Plans (IDPs)

- Clusters Programmes of Action

The departmental strategic planning process commenced in June 2006 wherein Senior Management went on a two day strategic planning workshop to review the core mandates, the vision and mission. This process of redefining ourselves was critical in order to understand the strategic direction the department had to take in lieu of the massive infrastructure delivery challenges facing the department. It was also critical to develop concise and implementable plans linked to the budget.

The various executive programmes then reviewed, developed and submitted their inputs on the situational analysis, strategic objectives, constraints, measures to overcome them and quality improvement measures, which then informed the Annual Performance Plan for 2007 – 08.

PART B: PROGRAMME AND SUB-PROGRAMME PLANS

BUDGET PROGRAMME AND SUB-PROGRAMME PLANS

Overall programme Structure

| Programme | Sub-Programme |
| --- | --- |
| PROGRAMME 1 Administration | - Office of the MEC - Strategic Human Resource Management - Strategic Financing - Corporate Services - GITO - Strategic Management |
| PROGRAMME: 2 Provincial Infrastructure Development | - Professional Services - Project Management - Real Estate - Building Maintenance - Expanded Public Works Programme |
| PROGRAMME: 3 EPWP |  |

PROGRAMME 1: 	ADMINISTRATION

Objective

The main objective for this programme is to provide support to line functions through the executive support services, strategic management, financial management, human resources, and information and communication technology services and promote the corporate image of the department for improved service delivery

Situational Analysis

The programme consists of the Office of the MEC, Strategic Financing, Strategic Human Resource Management, Corporate Services, Government Information and Technology Office and Strategic Management.

POLICIES, PRIORITIES AND STRATEGIC OBJECTIVES

Policies

The Department is guided by National policies aimed at transforming the public service, such as Batho Pele and the White Paper on Transformation of the Public Service. In addition, the Department is bound to work within the prevailing regulatory framework, including (inter alias) the Public Service Act, the Public Service Regulations, Skills Levels Act, Basic Conditions of Employment Act, Labour Relations Act, Public Finance Management Act, Treasury Regulations, the Preferential Procurement Policy Framework Act, and the Access to Information Act.  The Department is also bound by centrally negotiated agreements regarding conditions of service for its employees.

Priorities

- Improving revenue collection.

- Implementation of Risk Management strategy.

- Skills Development and Training of staff.

- Complete personnel audit and recapturing personnel on PERSAL.

- Improve the implementation of the Performance Management System.

- Implementation of Communication Strategy.

- Implementation Supply Chain Management (SCM) Framework.

- Implementation of Learnerships and Internships.

- Continue with the process of Transformation in the Department.

- Strengthening corporate governance.

- Broad Based Black Economic Empowerment (BBBEE).

- Alignment of the organizational structure with the strategy.

- Reduce personnel expenditure by 2% as required by National Treasury.

Analysis of constraints and measures planned to overcome them

The major challenge for this programme is to enhance skills among employees, improve work efficiency, attraction and retention of competent staff, organisational performance improvement and promote the corporate image of the department

Description of planned quality improvement measures

The Department will embark on a project to optimise its business processes and workflows across all units to enable it to effectively support the core functions of the department. In addition, this department will strengthen its performance management system in order to ensure organisational performance improvement.

SUB-PROGRAMME 1: OFFICE OF THE MEC

Situational Analysis

The office of the MEC is responsible for the provision of a well coordinated executive service that is aimed at achieving the vision of the department.

Policies, priorities and strategic objectives

In pursuit of its vision, the office is guided by both national and provincial policies which are pronounced from time to time. Key to the successful realisation of its vision is the vigorous implementation of transformation programmes embodied in the White Paper on Transformation of the Public Service as well as Batho Pele policy framework.

Analysis of constraints and measures planned to overcome them

The major challenge of this sub-programme is staff inadequacy to be able to render an effective executive service. Posts and their levels are determined by the Ministry of Public Service and Administration without due consideration to the size as well as the nature of the work of the department. However plans are afoot to adequately capacitate the sub-programme with skilled staff.

Description of planned quality improvement measures

The sub-programme will continue with the consultation programme with the public through Imbizo’s which are aimed at service delivery improvement.

SUB-PROGRAMME 2:  STRATEGIC HUMAN RESOURCE MANAGEMENT

Situational Analysis

The sub-programme is responsible for the attraction and provision of competent human resources, human resource development, performance management system and Employee Assistance Programme. Structural problems, capacity and inadequate funds have to a larger extent reduced the ability of this sub-programme to respond to challenges and service delivery requirements posed by external environment, new policy mandates and additional core functions within the department in the past. However, these challenges have been addressed by the adoption of a new organisation structure to enable support for implementation of strategic plans.

Policies, priorities and strategic objectives

The sub-programme does not have comprehensive Human Resource plans supporting business and departmental imperatives. To this end, the sub-programme intends implementing the following priorities:

- Quicker process of filling key positions in the department;

- Special development programme to assist and promote performance excellence in the department; and

- Institutionalisation of modern recruitment and retention of high calibre staff.

Analysis of constraints and measures planned to overcome them

There is a lack of a clearly defined human resource development strategy in the Province with regard to the identification of sector-specific skills requirements. For instance, there is a lack of skilled professionals in the Province in the built-environment. The Department has adopted the Provincial Performance Management System which is based on the Balanced Scorecard (BSC) methodology. There are, however, still challenges with regard to the implementation of the system.

The Department will introduce a Learnership and Internship programme to address skills shortage in the built-environment. A consolidated human resource plan has been developed and comprises of a workplace skills plan, employment equity plan, affirmative action plan, redundancy plan, succession plan, retention and recruitment plans. The updating of personnel information on the Persal system has improved to 98% and the implementation of the performance management system has been successful. Personnel expenditure came within budget, and all planned skills development interventions were executed. A workplace health programme has also been successfully implemented. All planned labour forum meetings were held and as such labour matters were satisfactorily resolved. The organizational structure was aligned to the strategy of the department

Description of planned quality improvement measures

- Workplace Health will start on the improvement of staff health and thus  reduce staff turn over due to ill health by utilizing the EAP Services.

- Occupational Health and Safety (OHS) aims to reduce accidents at the                workplace by 99%.

- HIV & AIDS management aims to increase awareness of HIV & AIDS by 100%, by means of more effective Roads Shows, peer educational sessions and distribution of awareness products.

- Proper staff placement and increase staff skills for customer satisfaction.

- Contribute towards poverty alleviation

- Improve and coordinate the HR functions in districts.

SUB-PROGRAMME 3:  STRATEGIC FINANCING

Situational Analysis

The sub-programme is responsible for implementing internal control measures and ensuring compliance to legislation governing financial management and corporate governance. The sub-programme further coordinates responses to the Auditor General’s audit queries, and the implementation of corrective measures in response to these queries.

Staffing

Non-corporation from programs and non-compliance to legislations

Creation of two Bid Adjudication Committee and 1 specification committee

Submission of business plans and annual cash flow projections

Under spending of the budget

Rewarding of performing contractors

Service Level Agreement

Debt Management

None performance by service providers

Determination of the minimum stock level

Maximisation with regard to revenue and arrear rentals collection

Develop monitoring tool for site visits

Develop annual procument plan

Streamline procument processes

Fronting

Vetting of contractors

Implement CIDB standards for conformity

Implementation of electronic procument databse

Slowness in awarding tenders for clients departments

BBBEE

Misperception by contractors – projects awarded to one contractor

Risk	Implementation of Risk Management Assessment Plan

Implementation of fraud, corruption and prevention strategy and awareness campaign

Develop minimum Information system – unauthorized access to information

Policies, priorities and strategic objectives

The sub-programme is guided by the Supply Chain Management Policy Framework, BBBEEA and PPPFA in addressing the imbalances of the past and encouraging HDI’s to participate in the procurement system funded by government. Treasury Regulations are a pillar to ensuring a sound financial management.

In pursuit of good corporate governance, the sub-programme will ensure:

- Unqualified and clean audit report; and

- Improved efficiency in the use of financial resources

Analysis of constraints and measures planned to overcome them

To introduce materials resource planning (MRP) and Just-in-Time (JIT) in the Department to improve inventory management. Through activity based budgeting, the finance section has managed to foster a stronger role of accountability to all programme managers in their financial management activities. The next step is to introduce a system of Activity Based Costing (ABC). As part of the process of procurement reform, Government promulgated the Supply Chain Management Framework Act, which led to the establishment of a supply chain management (SCM) unit within the department. The unit’s core function is to create an appropriate environment for procurement and provisioning systems, which are fair, equitable, transparent, competitive and cost effective as required by the PFMA.

The Department has a Risk Management Strategy and a Fraud Prevention Plan in place. Through the implementation of the plans, there has been a reduction in the number of fraud and corruption incidents. The Department has attained an acceptable level of awareness and culture change in the area of risk, at both strategic and operational levels. The challenge is to continue to manage risk to an acceptable level.

The Department has been meeting most of the deadlines for compliance with the PFMA, Treasury Regulations and other financial transcripts. The Department has furthermore improved on its Activity Based Budgeting and Costing and ensuring that all expenditures are allocated to the correct budgets. A major impediment to certain efficiencies on the financial activities was due to the poor functioning of the transversal financial systems, namely BAS and Finest.

The Department has improved its planning and alignment to the Medium Term Expenditure Framework (MTEF) for strategic plans and infrastructure projects. This approach was essential for the proper planning of projects, which resulted in the introduction of Materials Resource Planning (MRP) for the core functions. Through activity based budgeting, the finance section has managed to foster a stronger role of accountability all programme managers in their financial management activities.

Description of planned quality improvement measures

- The component of Risk and Security management has established a programme of action to mitigate and address audit queries arising from the same course of action and process. An action plan has been drawn up for each of the financial year and expressions as pronounced by the Auditor General, and quarterly reviews are made as a means of addressing all issues raised in the Audit process, and this measure has yet not adequately been attended to.

- In financial management, a strong focus has been in building capacity and increasing resources to attend to debt management and revenue collection. Training sessions and personnel have been recruited to meet the new requirements of clearing debt in the department, especially internal staff debt. Although, the implementation of the financial system is slow, the department has prepared to fully utilise the training sessions of rolling out the modules by exposing as many people as can be allowed in the sessions as a back up for the high turnover.

- The supply chain management unit is currently fraught with challenges of conceptualisation of the principles of supply chain management as a value and rather than an encumbrance to the existing procurement process. Due to the lack of adequate managerial capacity in the area of supply chain, the department is looking into the idea of a strategic partnership with expertise,  who will provide a drive for the process in line with principles of business re-engineering and entrenching efficiency in the process as a norm rather than the anomaly.

- The project mentioned above is essentially initial delicate for service delivery improvement, efficiency and achievement of value for money through an economical system, this of course pursued with enabling legislation such as the PFMA, PPPFA and the Supply Chain Management Framework Act and Practice Notes

SUB-PROGRAMME 4:  CORPORATE SERVICES

Situational Analysis

A strong Corporate Services that is aligned to the functional strategies of the department and also supporting the overall strategy of the department is a pre-requisite for the attainment of the vision of the department. The main responsibility of this sub-programme in relation to the vision and mission of the department is to strengthen the dynamism of the department for continuous improvement and also provide management and administrative support function which inter alias includes facilities and fleet management.

Policies, priorities and strategic objectives

In order to realise its policy mandates, the sub-programme will develop an Enterprise Resource Plan for effective management of corporate affairs as well as good corporate governance.

Analysis of constraints and measures planned to overcome them

The department embarked on a project to improve records management in line with regulatory frame works and industry best practice. This will enable the Department to comply with provisions of promotion of Access to Information Act, the National Archives Act and other relevant legislation. The budget has been decentralised to the district offices to procure in terms of the needs analysis made, monitor and evaluate all procurements in terms of the PPPFA Act and BBBEE. In order to manage the Department’s administrative support functions at District level more effectively, shared service centre managers coordinate these functions. This has resulted in the effective implementation of procurement reforms, improved fleet and logistics management and effective customer relationship management.  The provision of tele-communication equipment, which was greatly lacking in the District Offices has improved during the past financial year and is continuing to improve. The sub-programme has also begun the process of integrating the department’s records in line with legislation.

Description of planned quality improvement measures

- Improve telephone connectivity at Cost Centres

- Improve the filing system and methods used for risk free and user friendly system

- Ensuring of safe, secure storage and handling of documentation.

- Disposal of redundant files using the National Archives Act as a guide.

- Improve service delivery, internal and external, by ensuring fast and accurate

payments of services rendered.

- Quick cancellation and processing of orders.

- Decentralise budget to Districts in order to procure according to needs

- Reduce fleet abuse and vehicle misuse

- Promote effective and wise vehicle usage

- Monitor and evaluate all procurement processes

SUB-PROGRAMME 5:  GOVERNMENT INFORMATION TECHNOLOGY SERVICES

Situational Analysis

The GITO component is divided into three units namely ICT, Communication and Information and Records Management. The ICT is responsible for applications and systems development as well as provision and maintenance of ICT infrastructure. The maintenance and support of ICT infrastructure is outsourced to various service providers including SITA. Communication unit is responsible for both internal and external communication through use of both the print and electronic media. It also undertakes research on stakeholder needs in order to ensure that the Departmental activities are aligned to stakeholders. The Information and Record Management unit focuses on record management as well as management and provision of timely and accurate information for improved decision making.

Policies, priorities and strategic objectives

The programme is guided by Minimum Information Security standards, National Archives Act, Provincial Archives Act, Promotion of Access to Information Act, Public Service Act, Minimum Interoperability Standards, COBIT, ITIL, ICT Charter, ECTA and SITA act among others. The programme will focus on the following priorities:

- The development and implementation of applications for the Department. e.g GIS, Maintenance and Real Estate System, Call centre management system, Repositories/Data warehouse, Portal Development and Asset Management Systems;

- Ensure Provision of reliable ICT infrastructure in all Departmental office locations.

- Ensure good corporate Governance;

- Promotion of PAIA;

- Improve communication with Departmental Stakeholders (both internal and external);

- Ensure informed decisions through effective information management systems;

- Encourage regional integration – knowledge sharing;

- To make departmental information, knowledge, information systems and information and communications technology improve the efficiency of the department.

Analysis of constraints and measures planned to overcome them

The identified challenges are:

- Lack of ICT skills among users;

- Lack of adequate systems and applications to support the business;

- Lack of information repositories/Data warehouse;

- Absence of re-engineered processes;

- Lack of integrated supporting systems;

- Delays in installation of Data lines in cost centres;

- Shortage of staff;

- Continuous development/training of staff; and

- Compliance with policies and regulations, for example, use of filing plan, MISS classification, PAIA.

Description of planned quality improvement measures

In order to address the constraints a number of initiatives have been instituted namely:-

- Establishment of ICT training centers in four Districts;

- Implementation of key initiatives highlighted in the MSP and IM strategic documents in particular focusing on business applications;

- Investigate alternative means to provide connectivity in the outline cost centers;

- Continue to outsource some of the functions or activities;

- Completion of workplace skills plans with clear indication of developmental areas required;

- Filling of all vacant posts and

- Monitoring and creating awareness of policies and legislations.

SUB-PROGRAMME 6:  STRATEGIC MANAGEMENT

Situational Analysis

The Strategic Management division plays a central role in taking a lead in the strategic planning process of the department. It is tasked with the responsibility to coordinate the development of strategic plans and monitor the implementation thereof. The unit is also responsibility for the coordination of service delivery initiatives, Batho Pele as well as special programmes with particular focus on women, youth and persons with disability. Fostering Inter-Governmental Relations and the alignment of municipal IDPs is also the responsibility of this unit.

Policies, priorities and strategic objectives

The primary focus of this sub-programme is to ensure that the strategic planning process and the strategic goals thereof are informed by the government Programme of Action, Cluster Priorities and alignment to the Limpopo Growth and Development Strategy and IDPs.

Analysis of constraints and measures planned to overcome them

The strategic planning directorate is a newly established unit within the Department of Public Works. The directorate is being capacitated through the appointment of personnel.

Description of planned quality improvement measures

On going strategic planning process and quarterly performance reviews will be conducted to monitor the implementation of the strategic goals. The Batho Pele Change Engagement programme will be rolled out to the district offices. The challenge that remains is to review the departmental service standards. The implementation of special programmes needs to be fast tracked to meet national imperatives.

PROGRAMME 2:	PROVINCIAL INFRASTRUCTURE DEVELOPMENT

Situational Analysis

The department manages a diverse portfolio which includes leased and owned office and residential buildings. The toughest challenge therefore, in the execution of this mandate is the upgrading and maintenance of all of these assets to the minimum acceptable levels.

The department is currently auditing the three government owned office complexes with a view to developing a master maintenance plan that will provide medium to long term maintenance programmes to ensure compliance with the Occupational Health and Safety Act.

The department’s specific purpose in relation to provincial immovable assets is to ensure that immovable property owned or utilised for delivering various services yields functional, economic and social benefits to the government.

Although EPWP has been launched in the Province and an implementation framework developed, there appears to be lack of commitment to the programme by departments and municipalities in that most of them have not yet appointed EPWP Coordinators and also that very few have been able to identify projects with job creation and poverty alleviation potential. It appears that the department will have to consider intensifying its involvement in departments and municipalities where implementation problems are being experienced.

Policies, priorities and strategic objectives

- EPWP will use skills development and labour based technology to promote employment opportunities;

- Achieve EPWP goals using DPW capital and maintenance budget;

- Develop a reliable assets management register;

- Develop a master maintenance plan;

- Develop an integrated office accommodation plan; and

- Coordination of integrated provincial infrastructure planning and development

Analysis of constraints and measures planned to overcome them

Pivotal to comprehensive asset management is an accurate and fully populated Immovable Asset Register. The department inherited asset registers from the erstwhile administrations with incomplete data. As a first step, the department managed to register immovable assets which were identified then. As a second step, the department is in the process of procuring the services of a service provider who will identify other immovable assets for purposes of updating the Provincial Immovable Asset Register.

The departmental space and cost norms are currently being reviewed in order to improve service delivery, promote efficiency and eliminate operational barriers. The department has already invited bids for the provision of an integrated office accommodation plan which will assist in the development of performance enhancement strategies for maximum utilisation of office space.

As implementing agent for other departments, Public Works has experienced various challenges of proceeding with infrastructure development in the manner that it is currently being practiced. At present the province does not have a document or database, which is a consolidation of its total infrastructure needs for provincial departments and municipalities. This has sometimes resulted in instances where priorities of the provincial departments clash with those of municipalities.

The infrastructure planning process should therefore take into account all provincial and local government infrastructure needs as well as the provincial development plans of institutions such as Road Agency Limpopo, Department of Water Affairs, Eskom and Telkom.

To achieve this, there is therefore a need for an integrated approach in infrastructure planning and development that can best be accomplished through the establishment of a Provincial Co-ordinating Infrastructure Unit.

One of the most important constraints for the EPWP is the human resource capacity to manage the execution of the large amount of labour intensive work properly. Therefore training of consultants has become mandatory to ensure that bid documents captures the EPWP elements of LIC. An on-going challenge to the EPWP is to mobilise support among departments and municipalities for the successful implementation of the programme. Since EPWP is implemented within line budgets of departments and municipalities, there is a need therefore to develop an increasing understanding of the importance of this programme.

Description of planned quality improvement measures

The following quality improvement measures will be implemented to ensure achievement of strategic goals and thereby realise economic growth though sustainable job creation and relevant skills transfer:

- Coordination of provincial infrastructure departments;

- Implementation of the Just In Time principle to commission capital works projects within the specified timeframes;

- Management and maintenance of a reliable Provincial Asset Register;

- Skills transfer, job creation and poverty alleviation through vigorous implementation of EPWP; and

- Implementation of the Provincial Maintenance Plan.

SUB-PROGRAMME 1:  PROFESSIONAL SERVICES

Situational Analysis

The Professional Services programme is responsible for the provision and management of professional services in respect of professional norms. It co-ordinates and develop infrastructure planning and design objectives in line with the provincial development plan.

Policies, priorities and strategic objectives

The operations of the programme are guided by legislation governing the built environment professions such as acts governing the Engineering, Quantity Surveying, Architecture professions. The programme is also guided by the Occupational Health and Safety Act, Environmental legislation, National Building Regulations and other built environment regulations.

The programme will focus on the following priorities:

- Integrated Provincial Infrastructure Planning

- Management of Consultants

- Research and Development

- Strengthening corporate governance

Analysis of constraints and measures planned to overcome them

Lack of joint planning with client departments with regard to infrastructure provision is a major challenge. In order to address this challenge, the programme intends to launch the Provincial Infrastructure Coordinating Unit. EXCO approval has been sought in this regard. The programme will endeavour to enter into Service Level Agreements with client departments in order to address issues of planning. Another major challenge facing the programme is the lack of skilled and experienced personnel in certain professional disciplines.

Description of planned quality improvement measures

Interaction with various professional bodies will take place to clarify grey areas pertaining to the registration of professionals. To capacitate the programme in terms of both skill and staff, the programme will absorb professionals who are in training and eligible to undertake the test of professional competency.

SUB-PROGRAMME 2:  PROJECT MANAGEMENT

Situational Analysis

The restructuring of the department and the creation of the Project Management Executive programme has presented an opportunity for increased development and improvement of service delivery in the provision of building construction management and project management to other provincial government departments. Setting up this unit will strengthen institutional and operational efficiency through improved systems, structures and processes.

Policies, priorities and strategic objectives

The programme is guided by the National Building Regulations (NBR), Construction Industry Development Board (CIDB), Occupational Health & Safety Act (OHS), Environmental Legislation and other Built-Environment regulations. The programme will focus on the following priorities:

- The consolidation and strengthening of project management procedures and systems. This will include capacity building in the districts to ensure visible project management services.

- Focusing attention on specific outcomes and directing resources appropriately.

- Improving control and accountability mechanisms.

- Ensuring good corporate governance.

Analysis of constraints and measures planned to overcome them

The identification and formulation of challenges derive from the probing of the maturity of our project management practices as well as pertinent observations made by stakeholders. An illustration of challenges experienced at various levels of the project management structures as we struggle at times to excute the work on behalf of our clients include but are not limited to:

- Delays in appointment of contractors.

- Delays in payments to contractors.

- Complaints of poor workmanship

- Endless post delivery snag lists.

- Inability on the part of contractors to deliver timeously the facilities.

- Interference by local authorities and communities in  the operations of appointed contractors.

- Inadequate monitoring of workmaship and quality due to the geographic spread of the projects.

- Inadequate management control systems

Description of planned quality improvement measures

The interventions guided by the need to improve project implementation and monitoring will be through strengthening of existing project management organisational structures and clarifying roles/functions of various units both at head office and district level. The programme has already started assigning project managers to projects in a manner that matches their individual level of competence to the magnitude and level of complexity. A structure is in place which enables technical personnel in the built environment to focus on specific aspects of a project cycle. The programme will maintain a critical mass of personnel at head office, whose functions will include general project management activities and it will also form part of capacity building teams for our project management structures at district level. The CIDB register of contractors has now been established with a comprehensive system of tracking contractors’ track record and verifying their levels of competence. It is envisaged that contractors appointed using this system will execute projects better.

SUB-PROGRAMME 3:  REAL ESTATE

Situational Analysis Services Rendered

The sub-programme is responsible for the provision and management of immovable property, which serves as the platform for  efficient service delivery of various government departments. This involves land management and the provision of office accommodation to all provincial departments. This embraces the leasing of private properties for use by provincial departments; valuation of immovable properties that the department intends renting or buying; management of the process of disposal of immovable properties, the transfer of property to local municipalities, vesting of provincial properties to ensure proper ownership and provision of residential accommodation to politicians.  There has been a growing need for more residential accommodation for political office bearers in the Province.  This requirement has become eminent in light of the results from the latest population census that has determined that this Province will have about 52 MPLs in the future.

Policies, priorities and strategic objectives

The Department has developed a policy in line with the White paper on Government-wide Immovable Asset Management to guide the management of the Provincial Property Portfolio including the acquisition and disposal of properties. In addition, the Department conducts activities in terms of the various legislation governing property matters, including: The National State Land Disposal Act, The Northern Province Land Administration Act, The Municipal Systems Act, PFMA, Treasury Regulations. The Property programme will focus on improving revenue collection and the overall management and transformation of the property portfolio. The strategic objectives will  be to focus on:

- The improvement and maintainenance of good management of the provincial property portfolio.

- The disposal of government property classified as redundant.

- Ensuring the ownership of provincial property through the process of vesting

- Improving rental collection from tenants.

- The continued transfer of townships (R293) to municipalities.

- Updating and maintaining a comprehensive provincial property asset register

- Administration of provincial office and residential accommodation

- Acquisition of land for socio-economic development

- Payment of municipal rates and taxes

- Development of policies with respect to the efficient utilisation of government immovable assets

Analysis of constraints and measures planned to overcome them

The property programme is responsible for providing the provincial government with its property requirements and ensuring the effective, efficient and economic management of the property portfolio for service delivery. This involves the renting, acquisition and disposal of properties, lease management of Government properties, registering of State-owned properties in the name of the Province, transfer of Provincial properties to Municipalities, as well as the provision of residential accommodation for political office bearers.

The program faces huge challenges in the area of rental collection both in terms of rent-defaulters and a lack of capacity in rental collection management within the Department. The disposal programme is being hampered by the inability of preferred buyers to access finance as well as long-drawn-out legal process to evict existing tenants. There is a serious lack of capacity within client Departments to manage their own respective leases with landlords. There is also a  lack of skilled human resource capacity within the Department to monitor leases on behalf of client Departments. The programme also faces a challenge with regard to the updating of all the fields in Provincial property asset register. A further challenge facing the Department is the provision of office space for the provincial government. The Department is faced with critical challenges in contributing to the transformation of the patterns of property ownership as stated in the Property Charter. A key issue in managing  the provincial immovable assets is unlocking the economic potential of land owned by the  government to address poverty alleviation and social development needs of the Province.

The programme will attempt to improve the collection of arrear rentals by dedicating staff to manage the rental collection. The programme will explore alternative ways of property disposal to preferred buyers and will ensure transformation of property ownership as reflected in the Property Charter. In addition, the programme will improve capacity within the Department to monitor the management of leases by client departments. The programme continues to address the gaps in the Provincial property asset register. The programme will continue to fast track the acquisition of land for solicit economic development.

Description of planned quality improvement measures

To effectively manage government immovable assets, the department must give due consideration to develop policies for more efficient and economic use of immovable assets. This places an obligation on the Department to prepare immovable asset management plans to ensure that prudent management of such assets take place.  The policy must distinguish users and custodians of immovable assets. It is also critical that the department finalises the comprehensive assets register, which will reflect all provincial immovable assets.  There is also a need to acquire asset management system to ensure proper management of immovable assets.

The department will conduct space audit in all districts to establish whether provincial departments are properly accommodated and that office space is optimally utilized.  Furthermore, the Department must engage the municipalities to provide strategic land for the government needs. As custodian of immovable assets the department is required to pay municipal rates and taxes.  The National Department of Public Works has devolved this function to the province.  The Department must create human resource capacity to undertake this function.

The obligation of the department in acquiring and disposing of property must take into consideration the broader socio-economic objectives of the Province.  To this end the aims and objectives as reflected in the Property Charter to unlock obstacles to property ownership and transforming the property sector must be taken into consideration.

SUB-PROGRAMME 4:  BUILDING AND MAINTENANCE

Situational Analysis

The sub-programme is responsible for the maintenance of provincial owned properties, inclusive of both office and residential accommodation.

Policies, priorities and strategic objectives

The programme is guided by the Occupational Health & Safety Act (OHS), Environmental Legislation, National Building Regulations (NBR), Construction Industry Development Board (CIDB) and other built-environment regulations. The programme will focus on the following priorities:

- Using in-house building staff to construct and maintain road camps and for maintaining the residential property portfolio.

- Routine and preventative maintenance of buildings and facilities.

- To render effective routine building maintenance services.

Analysis of constraints and measures planned to overcome them

One of the major challenges facing the Building programme over the previous years has been the lack of effective management control systems for internal building and maintenance teams. The lack of sufficient funding to address maintenance backlogs is a further challenge.

In order to address the lack of management control systems, the Department embarked on a programme of service delivery improvement during the financial year. This has led to the development of systems and processes that has resulted in a marked improvement in the output of the teams.

Description of planned quality improvement measures

A larger part of the government buildings have not had a sufficient planned and preventative maintenance for time now. To address this challenge, this sub-programme will conduct comprehensive repairs in order to comply with OHS standards.

PROGRAMME 3:  EXPANDED PUBLIC WORKS PROGRAMME

Situational Analysis

The objective of Programme 3 is to ensure the realization of mandates of the Expanded Public Works Programme (EPWP). Through a National Cabinet decision and the subsequent Provincial Executive Council’s decision, the Department of Public Works was mandated to coordinate the implementation of the programme in the Province.

This involves evaluating business plans, monitoring implementation, facilitating training and reporting progress for all EPWP programmes in the province.

Policies, priorities and strategic objectives

The objectives of the programme are to:

- Promote job creation

- Poverty alleviation

- Facilitate skills development

The priority of the programme is to ensure the achievement of objectives and successful implementation of the business plans developed for the programme.  To ensure compliance to legislations that underpins the EPWP, ensure collaborative problem solving and intervention.

Analysis of constraints and measures planned to overcome them

Government implementing agencies and bodies must identify EPWP projects that will be funded through the Municipal Infrastructure Grant (MIG 40% of the allocation), while provincial departments have to identify funds from within their existing budgets that must be channelled towards EPWP.  The Department of Public Works must set aside 30% of its infrastructure projects budgets for the implementation of EPWP, more emphasis must be placed on Labour Intensive projects.

Guidelines for the economic, social and environmental sectors have been developed by the relevant sector departments.  A provincial EPWP steering committee has been established. Consultative meetings and workshops with Municipalities and Provincial departments have taken place.  Business plans have been developed and are in the process of implementation.  At present, consolidations of sector plans have taken place.

Description of planned quality improvement measures

The main action this year is to put more emphasis on shared goals for government and society, the development of outstanding sector plans needs to be finalised and development of MTEF based operational plan linked to the five-year business plan. There is a need to develop communication plan to raise awareness around the EPWP, and to build capacity within the Province with regard to the implementation of the programme.  The introduction of monitoring and reporting mechanisms to measure the progress and impact becomes critical.   The establishment of formal links with implementing Agencies and the signing of service level agreement be introduced to ensure success and accountability.

Concrete targets will only be developed once baseline audit has been done, and targets will be negotiated in line with broader provincial growth and development objectives and targets. The programme will influence the Department of Labour to keep a data base of people who went through the programme and other related programmes.  Partnerships with other organs of civil society will be developed along the achievement of the millennium goals.

A service delivery improvement program will be put in place to enable the programme to monitor and evaluate impact and measure progress in terms of objectives.  Evidence Based Decision Support be utilised for impact assessment.  The intersectoral / interdepartmental coordinating committee will be a key player in guiding and evaluating the effectiveness of strategies and plans.

ANNUAL PERFORMANCE PLAN 2007 -2008

EXECUTIVE PROGRAMME: STRATEGIC HUMAN RESOURCES MANAGEMENT

| Sub Programme Human Resource Management | Strategic Goal: Improved Service Delivery and Good Corporate Governance |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Stragic Objectives | Measurable objectives | Performance Measure Indicator | 2007/08 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Skills Development for improved service delivery Skills Development to meet objectives of Provincial Growth and Development Strategy | Implementation of workplace skills plan Implementation of HRD Strategy | Integrate Abet into skills programme Number of skills development programme implemented Number of educational grants for serving employees maintained Facilitate Implementation of (18. 2) learnership programmes for infrastructure related skills Number of interns recruited Number of education and training grants awarded to non-serving employees | R 1.5 m R2. m R800 000 R 1.3 m R700 000 | Facilitate implementation of registered Learnership programmes Monitor registered Learnership programmes Facilitate implementation of identified skills development programmes - Conduct quarterly monitoring and evaluation of bursary contracts Facilitate implementation of registered Learnership programmes Implement identified internship programs Conduct quarterly monitoring and evaluation of bursary contracts | Monitor registered Learnership programmes - Monitor identified skills development programmes - Conduct quarterly monitoring and evaluation of bursary contracts Monitor registered implemented Learnership programmes Monitor Implementation of identified internship programs Conduct quarterly monitoring and evaluation of bursary contracts | Review implemented learnership programmes - Monitor identified skills development programmes Review and evaluate identified skills development programmes Allocate bursaries to serving personnel Conduct quarterly monitoring and evaluation of bursary contracts Review implemented Registered Learnership programmes Review Implementation of identified internship programs Conduct quarterly monitoring and evaluation of bursary contracts | Registration of learnership programme Placement of learners Evaluate implemented registered Learnership programmes Develop skills development programme for next cycle Review bursary awards scheme Conduct quarterly monitoring and evaluation of bursary contracts Registration of learnership programmes Placement of 50 learners Evaluate implemented registered Learnership programmes Evaluate Implementation of identified internship programs Conduct quarterly monitoring and evaluation of bursary contracts |
|  |  | Number of emerging contractors trained(Sakhasonke) Number of supervisors trained Number of mentors trained Integration of EPWP College with FET’S Cc-ordinated Business partnership with financial institutions facilitated | R5,4 M | Procure service provider Identify and facilitate registration of 40 supervisors Identify and facilitate registration of 90 mentors Liaison with Dept of Education for integration Faciliate liaison with financial partnership for 40 contactors | Training commences Training commences Training of 90 mentors Finalise Integration - | Training continues Monitor and Evaluate the impact of training Monitor and Evaluate the impact of training - - | Training continues Monitor and Evaluate the impact of training Monitor and Evaluate the impact of training - - |
| Improved work efficiency | Aligned organizational structure to strategy of the department | Approved Organizational Structure | R500,000 | Appoint OD Service Provider | Submit Structure to DPSA for approval | Follow up with DPSA for finalization. | Evaluate affected and new posts and advertise vacant posts |
|  | Implementation of the integrated Human Resource Plan | Reviewed and approved HR plan | N/A | Update statistical data in the HR Plan | Update statistical data in the HR Plan | Update statistical data in the HR Plan | Revise HR plan based on new Organogram |
|  | Attraction and retention of proficient staff | Implement recruitment plan | R 19 m | Advertise and fill post | Advertise and fill post | Advertise and fill post | Advertise and fill post |

| Performance Improvement | Manage implementation of performance management policy | Implemented Performance Management policy | R 3.8 M | Implement Performance Management policy | Monitor implementation of Performance Management policy | Monitor implementation of Performance Management policy | Evaluate personnel I.TO Performance Management policy and draw plans for next financial year |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Improve Human Resource Information Management (Persal Admin) | % of fields completed and updated on Persal |  | 99% of fields completed and maintained | 100% of fields completed and maintained | 100% completed and maintained | 100% completed and maintained |
|  | Deliver Employee Benefits and allowances | Benefits and allowances paid within timelines and according to policy | R346M | Not more than 2% exceptions on HRM Review Report | Not more than 2% exceptions on HRM Review Report | Not more than 2% exceptions on HRM Review Report | Not more than 2% exceptions on HRM Review Report |
| Improved work environment | Implementation of an integrated Employee Wellness program | HIV & AIDS prevention & care program implemented Occupational, health and safety prevention and care program implemented Employee Assistance Program implemented Social Wellness program implemeted | R2m | Procure HIV & AIDS prevention projects Procure special OHS interventions Procure Special EAP interventions Provide solution focused therapy for distressed employees Invite participants for various sporting and cultural activities and elect district committees & teams - | Implement Peer Education Training, VCT Campaigns Implement medical testing of high risk categories Implement EAP interventions according to the health calendar and needs Provide solution focused therapy for distressed employees Practice sports and cultural activities on a weekly basis. Play and host matches as outlined in the SW policy | Implement Peer Education Training, VCT Campaigns Implement First Aid, Fire Fighting, Disaster management interventions. Implement EAP interventions according to the health calendar and needs Provide solution focused therapy for distressed employees Practice sports and cultural activities on a weekly basis Play and host matches as outlined in the SW policy | Review & Evaluate & Needs Assessment for Employee Wellness projects for next FY. Risk assessment of sites and job categories Implement EAP interventions according to the health calendar and needs Provide solution focused therapy for distressed employees Review policy and plan activities for next FY - |
| Improved work environment | Manage implementation of employment relations | Grievance and Disciplinary Cases finalized within timelines | R34.000 | Reduce backlog on Disciplinary and Grievance cases by 30% | Reduce backlog on Disciplinary and Grievance cases by 30% | Reduce backlog on Disciplinary and Grievance cases by 20% | Reduce backlog on Disciplinary and Grievance cases by 20% |

EXECUTIVE PROGRAMME: STRATEGIC MANAGEMENT

| Sub Programme: Strategic Management | Strategic Goal: Improved Service Delivery |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable objectives | Performance measure Indicator | 2007/08 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Enhance public service delivery | Service Delivery Excellence | Service delivery improvement programme developed and implemented |  | Report on monitoring and implementation of SDIP |  | Report on monitoring and implementation of SDIP | Review of SDIP and drafting of SDIP for 2008/09 |
| . |  | Special programmes implemeted | R500 000 | Facilitate participation in the provincial and National activities. Take a girl child to work ceremony | Facilitate participation in the provincial and National activities. Youth day celebration | Women in construction conference Facilitate participation in the Provincial and National activities. Disability day | Review special programmes to empower youth, women and people with disability Develop a programme of action for 2008/09 |
|  |  | Batho Pele programmes implemented | R500 000 |  | Report on customer satisfaction survey Facilitate participation in the provincial and National activities. Public service week | Facilitate participation in the provincial and National activities. Batho Pele day celebration Production of Citizens report | Report on customer satisfaction survey Progress review and next plan of action for 2008/09 |
|  |  | Business process reengineering. |  | Business analysis and process mapping of Executive Programs and district offices | Business analysis and process mapping of Executive Programs and district offices | Business analysis and process mapping of Executive Programs and district offices | Review progress and develop plan of action for 2008/09 |
|  |  | Implement strategic interventions to support core functions of the department |  | Convene strategic planning session to review the strategic plan and Annual Performance Plan for 2007/08 Coordinate the implementation of EXCO resolutions and Clusters’ Programmes of Action | Develop a monitoring and evaluation framework to track performance and implementation of the strategic plan Coordinate the implementation of EXCO resolutions and Clusters’ Programmes of Action | Convene mid-year strategic planning review session to incorporate mid-term priority reviews. Coordinate the implementation of EXCO resolutions and Clusters’ Programmes of Action | Finalise the revised strategic plan and annual performance plan for 2008/09 Coordinate the implementation of EXCO resolutions and Clusters’ Programmes of Action |
|  |  | Monitoring and Evaluation |  | - | Coordinate and facilitate Departmental quarterly Performancxe reviews for 1st quarter Coordinate consolidation of 1st quarter performance report | Coordinate and facilitate Departmental quarterly Performance reviews for 2nd quarter Coordinate consolidation of 2nd quarter performance report | Coordinate and facilitate Departmental quarterly Performance reviews for 3rd quarter Coordinate consolidation of 3rd quarter performance report |
|  |  | Implementation of the IGR Framework |  | Verify plans for alignment to IDP’S Coordinate regional integration programmes in line with PDGS objectives | Participate in various municipal forums Coordinate regional integration programmes in line with PDGS objectives | Participate in various municipal forums Coordinate regional integration programmes in line with PDGS objectives | Coordinate submission of approved plans to District municipalities for 2008/09 Coordinate regional integration programmes in line with PDGS objectives |

EXECUTIVE PROGRAMME:  CORPORATE SERVICES

| Sub Programme: |  | Strategic Goal: Improved service delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives |  | Measurable objectives | Performance measure Indicator |  | 2007/08 Budget |  | Quarter 1 |  | Quarter 2 |  | Quarter 3 |  | Quarter 4 |  |
| Proper utilization of moveable physical resources |  | Provision of a conducive work environment | Purchase of 64 vehicles |  | R3,500,000 |  |  |  | Placement of orders for acquisition of 64 vehicles |  | Take delivery of vehicles and effect payment Needs analysis for 2008/9 |  | Take delivery of vehicles and effect payment Registration and allocation of vehicles |  |
|  |  |  | Provision of labour-saving device and office equipment |  | R6M |  | Conduct needs analysis and produce action plan for 2008/9 |  | Procurement and management of contracts |  | Procurement and management of contracts |  | Procurement and management of contracts |  |
|  |  |  |  |  | R9 M R3M |  | Management of telecommunication systems |  | Management of telecommunication systems Bid adjudication and appointment of a service |  | Management of telecommunication systems Install new telephone system |  | Management of telecommunication systems |  |
|  |  | Provision of logistical facilities for Departmental functions | Preparation for Departmental events |  | R10 M |  | Ad-hoc arrangements |  | Ad-hoc arrangements |  | Ad-hoc arrangements |  | Ad-hoc arrangements |  |
|  |  |  | Provision of security and cleaning services |  | R11M |  | Management of 30 security contracts |  | Management of 30 security contracts |  | Management of 30 security contracts |  | Management of 30 security contracts |  |
|  |  |  |  |  | R3,7 M |  | Develop specifications for the installation access control system incl. CCTVs at the districts |  | Bid adjudication and appointment of a service provider |  | Installation of system |  | Installation of system |  |
|  |  | Compliance with OHS Act | Adequate provision of protective clothing |  | R2,5M |  | Needs analysis for 2008/9 |  | Placement of orders |  | Delivery and allocation of goods |  | Delivery and allocation of goods |  |
| Sub Programme: Corporate Services | Strategic Goal: Improved Service delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Objectives | Measurable Objectives |  |  | Performance measure Indicator |  | 2007/08 Budget |  | Quarter 1 |  | Quarter 2 |  | Quarter 3 |  | Quarter 4 |
| Proper utilization of moveable physical resources | Implementation of enterprise resource plan |  |  | Purchase of 64 vehicles |  | R3,500,000 |  | Needs analysis for 2008/9 |  | Placement of orders for acquisition of 64 vehicles |  | Take delivery of vehicles and effect payment Needs analysis for 2008/9 |  | Take delivery of vehicles and effect payment Registration and allocation of vehicles |
|  |  |  |  | Management of subsidized vehicles Provision of labour-saving device and office equipment |  | R2,800,000 |  | Conduct needs analysis and produce action plan for 2008/9 |  | Evaluation of applications based on RT57 contract Procurement and management of contracts |  | Take delivery of vehicles. Needs analysis for 2008/9 Procurement and management of contracts |  | Take delivery of vehicles Procurement and management of contracts |
|  |  |  |  |  |  | R7,900,000 |  | Management of telecommunication systems |  | Management of telecommunication systems |  | Management of telecommunication systems |  | Management of telecommunication systems |
|  | Provision of logistical facilities for Departmental functions |  |  | Preparation for Departmental events |  | R9,000,000 |  | Ad-hoc arrangements |  | Ad-hoc arrangements |  | Ad-hoc arrangements |  | Ad-hoc arrangements |
|  |  |  |  | Compliance with OHS Act |  | R3,000,000 |  | Await issue of new contract |  | Procurement of protective clothing |  | Procurement of protective clothing |  | Conduct needs analysis for 2008/09 |
|  |  |  |  | Provision of Security services |  | R9,000,000 |  | Management of 34 security contracts |  | Management of 34 security contracts |  | Management of 34 security contracts |  | Management of 34 security contracts |
|  |  |  |  |  |  | R1,500,000 |  | Review Specifications for CCTV installation |  | Bid adjustment and appointment of a service provider |  | Installation of system |  | Installation of system |
|  |  |  |  | Provision of cleaning services |  | R2,000,000 |  | Prepare bid documentation |  | Bid adjudication and appointment of a service provider |  | Delivery and allocation of equipment |  | Delivery and allocation of equipment |
|  |  |  |  | Development of a security policy |  |  |  |  |  |  |  |  |  |  |

EXECUTIVE PROGRAMME: STRATEGIC FINANCE

| Sub programme: Strategic Finance | Strategic Goal: Good corporate governance |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable objectives | Performance Measure Indicator | 2007/08 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Maintenance of an appropriate procurement and provisioning system which is fair, equitable, transparent, competitive and cost effective | Implementation of Supply Chain Management Framework | The number of officials trained Number of awareness campaign conducted (both internal & external ) Number of Bid Committees established Percentage of SLA’s signed with programs Percentage of awarded contractors submitted for vetting |  | 10 officials trained Enforcement of SCM policy Develop standards and map processes Appointment of Departmental and infrastructure Bid Adjudication committee 95% 50% of contractors submitted for vetting | 10 officials trained Conduct 6 workshops on SCM – Internal clients Popularize the SCM standards and map processes in Head Office and 5 Districts. - 100% 60% of contractors submitted for vetting | 10 officials trained Conduct 5 workshops on SCM – External clients Popularize the SCM standards and map processes in Head Office and 5 Districts. Develop annual procurement plan - 100% 75% of contractors submitted for vetting | 10 officials trained Compile 6 reports on workshops conducted. Assess the impact and compile 6 reports Develop annual procurement plan - 100% 90% of contractors submitted for vetting |
| Maintenance of effective, efficient and transparent systems of financial and risk management and internal control | Optimization of revenue collection Optimal budget management Compliance with applicable legislations Provide Risk management support and advice | Percentage of Revenue collected against the target Percentage of budget spent against the budget Percentage of payments processed within 30 days Number of audit queries received Number of Risk and Fraud awareness campaigns and workshops conducted Number of risk management progress reports Number of evaluation reports of internal controls Number of security assessment and audits reports Percentage of the budget of claims against the department Number of fraud & corruption cases investigated | R23,693m R601598m R 1,5M | R5,923m 25% budget spent 90% Number of audit queries received Number of workshops and campaign conducted One Quarterly progress Report on implementation of Risk Management plan One evaluation report of internal controls One security assessment and audit report 25% of the budget Number of cases the cases received | R5,923m 25% budget spent 95% Number of audit queries received Number of workshops and campaign conducted One Quarterly progress Risk Management Report One evaluation report of internal controls One security assessment and audit report 50% of the budget Number of cases the cases received | R5,923m 25% budget spent 100% Number of audit queries received Number of workshops and campaign conducted One Quarterly Risk Management progress Report One evaluation report of internal controls One security assessment and audit report 75% of the budget Number of cases the cases received | R5,923m 25% Budget spent 100% Number of audit queries received Number of workshops and campaign conducted One Quarterly Risk progress Management Report One evaluation report of internal controls One security assessment and audit report 100% of the budget Number of cases the cases received |

EXECUTIVE PROGRAMME: GOVERNMENT INFORMATION TECHNOLOGY SERVICES

| Sub Programme: GITO | Strategic Goal: Improve service delivery |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable objectives | Performance Measure Indicator | Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Improve work efficiency | Implementation of MSP projects Hardware procured Software licenses procured Management of SLA Best practice in ICT implemented | Number of sites with functional network infrastructure % Implementation of DRP project % Implementation of ECM % implementation of GIS % implementation of Portal % implementation of Mintirho (core functions) system % implementation of Project Management system % Implementation of Performance Management system % Implementation of Back office system % Hardware procured % of software licenses procured Number of SLA ITIL and Cobit implemented | R 1 000 000 R2 200 000 R 700 000 R 2 200 000 R 2 000 000 R 750 000 R 500 000 R 1 500 000 R0 R 3 000 000 R 2000 000 R 3 2m R2 m | Establish infrastructure in three sites ( Bohlablela, Arconhoek and Cental) Assessment of VPN Assess DRP requirements 25% implementation of project User requirements of project User requirements of project User requirements of project Assessment of needs 50% 50 % of Hardware procured 100% of software licenses procured Management of SLA performance Assessment | Establish infrastructure in two sites ( Sekgosese, Mutale) Design VPN Design DRP project 50% implementation of project 50% implementation of project System development System development System development Assessment of needs 50% 50% of Hardware procured Management of SLA performance Assessment | Establish infrastructure in three sites ( Thoyonndou 1) Implement VPN Implement DRP Implementation of ECM 25% Managing and updating of GIS datasets 25% implementation of project System Development System development System development Design of system Hardware & maintenance Management of SLA performance Implementation | Maintain and monitor network. Review VPN Performance Implement DRP Implementation of ECM 25% Managing and updating of GIS datasets Maintain Portal Implementation of system Implementation of system Implementation of system Design of system Hardware & maintenance Management of SLA performance Implementation |
| Improve work efficiency | Provision of information and records management services in the Department | Implementation of IM strategy projects - Development of policy, standards and procedures - Functional repository - Information, records and knowledge management awareness Functional Resource Centre and Information kiosks in districts, cost centers and MPCC Effective departmental intranet and website Effective learning environment (knowledge management) Business continuity plan (BCP) Functional records management service Implementation of Promotion to Access of Information Act Effective and efficient messenger and postal services | R0 R1,5 mil R300 000 R300 000 R0 R300 000 R2 mil R0 R300 000 R250 000 R350 000 | Develop information lifecycles and management actions Fifty percent consolidation of information and data architecture Awareness sessions at Head Office and Capricorn Acquire resource centre accommodation Revamping the departmental intranet and website Determine components of a holistic knowledge management and develop an implementation plan Develop a business continuity plan Implement Best Practice for records management Develop record disposal programme for all registries Review departmental manual. Develop request database Develop collection and distribution methods | Finalisation and implementation of Information management policy, standards and procedures Fifty consolidation of information and data architecture Awareness sessions at Sekhukhune and Waterberg Districts Installation of PALS library system in resource centers Populating the departmental intranet and website Establish approved governance structures Develop a business continuity plan Amendments and additions to approved file plan Implementation of disposal programme Translate manual into Afrikaans and produce in Braille Review outgoing and incoming registers | Implementation of IM policy, standards and procedures User requirements Awareness sessions at Mopani and Vhembe Districts Acquisition of library materials Maintain the departmental intranet and website Implementation of knowledge management projects Implementation of a BCP Development of digitization plan Implementation of disposal programme Manage information request processes Refurbish postal offices | Implementation of IM policy, standards and procedures Design the repository - Plan the establishment of resource centers in districts Maintain the departmental intranet and website Implementation of knowledge management projects Implementation of BCP Implement a digitization plan Implementation of disposal programme Submission of Section 15 and 32 reports Review outgoing and incoming registers |
| Enhance and strengthen internal and external communications (Good corporate governance) | Implement ion of the communication strategy | Implementation of corporate communication Implementation of corporate identity/ Marketing programme Media and Research Stakeholder management | R2,5 mil R2,5 mil R1,2 mil R0 | Produce Departmental publications as per requirements (photography, advertising, three monthly and one quarterly newsletters) Manage campaigns and events, internal and external communication. District visits, Candle lighting memorial service, EPWP Learners workshops Exhibitions in all Departmental activities. Promotion of corporate identity and acquisition of corporate gifts Media scans Media release Research Media briefings Implement one public participation session, imbizo, EXCO meets the people, MEC meets the people, project launches | Produce Departmental publications as per requirements (annual report, citizen’s report, brochures, three monthly and one quarterly newsletters) Manage campaigns and events, internal and external communication. National Construction week, Women in construction, Departmental women’s day, Heritage month Exhibitions in all Departmental activities. Career exhibition Promotion of corporate identity and acquisition of corporate gifts Media scans Media release Research Media briefings Implement one public participation session, imbizo, EXCO meets the people, MEC meets the people, project launches | Produce Departmental publications as per requirements (season’s greetings, newsletters, advertising, three monthly and one quarterly photography) Manage campaigns and events, internal and external communication. District visits, Disability day, 16 days of activism Exhibitions in all Departmental activities. Batho Pele day, Promotion of corporate identity and acquisition of corporate gifts Media scans Media release Research Media briefings Implement one public participation session, imbizo, EXCO meets the people, MEC meets the people, project launches | Produce Departmental publications as per requirements (Diaries and calendars, three monthly and one quarterly newsletters) Manage campaigns and events, internal and external communication. Budget speech, Excellence awards, Public participation on supply chain Exhibitions in all Departmental activities Promotion of corporate identity and acquisition of corporate gifts Media scans Media release Research Media briefings Implement one public participation session, imbizo, EXCO meets the people, MEC meets the people, project launches |

EXECUTIVE PROGRAMME: PROJECT MANAGEMENT

| - Sub-Programme - Project Management | Strategic Goal: Providing leadership in sustainable integrated provincial development |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Strategic Objectives | - Measurable Objectives | - Performance Objective | - 2007 / 08 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| - Successful execution of Capital Works Projects | - Implementation of capital works projects | - % of successfully completed Capital Works Projects |  | -Handover of project sites to contractors. Target 100% - -Supervision & monitoring of progress. expected average progress 35% target | Supervision and Monitoring of progress. 65% progress expected on projects handed over | Supervision and Monitoring of progress. 100% progress expected on projects handed over | Commissioning of projects. Payment of retention - Preparation of bid document for new projects |
|  |  |  |  |  |  | Commissioning of projects. | Evaluation of bids for coming financial year. |
|  |  | Education Projects | R85m | Completion of : 95 Schools under trees and in schacks-100% | Payment of retention and final accounts -Schools under trees and in shacks- |  |  |
|  |  |  | R272m | Completion of 239 Storm damaged Schools | Payment of retention and final accounts - Storm damaged Schools - |  |  |
|  |  |  | R96m | 91 Condemned Schools phase 1 On average 85% of the projects completed | 100% (91) schools completed | Payment of retention and final accounts |  |
|  |  |  | R55m | 88 Condemned Schools Phase 2 On average 85% of the projects completed | 100% ( 88) schools completed | Payment of retention and final accounts |  |
|  |  |  | - R6m | - 4 Cross boundary Schools On average 85% of the projects completed | 100% (4) schools completed | Payment of retention and final accounts |  |
|  |  |  | R9m | Refurbishment of DoE Site hand over | 65% of refurbishment of work complete | 100% of refurbishment of work complete | Payment of retention and final accounts |
|  |  |  | R10m | Refurbishment of Multipurpose Centers Site hand over | 60% of refurbishment of work complete | 100% of refurbishment of work complete | Payment of retention and final accounts |
|  |  |  | R6m | Renovation of DoE Warehouses | 100% of Renovation work complete | Payment of retention and final accounts |  |
|  |  | Health Projects - 33 Clinics | - R 115m | Final inspection, release retention and close the project. 100% target. |  |  |  |
|  |  | -20 clinics | R70m | Final inspection, release retention and close the project. 100% target. |  |  |  |
|  |  | - 2 health centres | R 16m | Continuation of monitoring and supervision. 20% progress target. | Continuation of monitoring and supervision. 50% progress target. | Continuation of monitoring and supervision. 70% progress target. | - Final inspection, release retention and close the project. 100% target |
|  |  | - 9 Mortuaries | R 49m | Final inspection, release retention and close the project. 100% target |  |  |  |
|  |  | - 7 Hospitals | R 210m | - Final inspection, release retention and close the project. 100% target |  |  |  |
|  |  | Construction of staff housing for essential health workers | R120m | Final inspection, release retention and close the project. 100% target |  |  |  |
|  |  | 2 Hospitals | R145m | Continuation of monitoring and supervision of Thabamoopa and Letaba hospitals. 40% progress target. | Continuation of monitoring and supervision of Thabamoopa and Letaba hospitals. 60% progress target. | Thabamoopa and Letaba hospitals. 70% progress target. | Thabamoopa and Letaba hospitals. 80% progress target. |
|  |  | EMS (5 Projects) | R23. 5m | Continuation of monitoring and supervision. 90% progress target. | Continuation of monitoring and supervision. 100% progress target. | Final inspection, release retention and close the project. 100% target |  |
|  |  | Laundry Facilities (5 Projects) |  | Site Handover for Tshilidzini, Donald Frazer and Mokopane Hospitals | Continuation of monitoring and supervision. 50% progress target. | Continuation of monitoring and supervision. 70% progress target. | Final inspection, release retention and close the project. 100% target |
|  |  | Whitoc | R17m | Continuation of monitoring and supervision. 40% progress target. | Continuation of monitoring and supervision. 70% progress target. | Final inspection, release retention and close the project. 100% target |  |
|  |  | Health Projects Staff Accommodation | R87m | Site Handover | Continuation of monitoring and supervision. 50% progress target. | Continuation of monitoring and supervision. 70% progress target. | Final inspection, release retention and close the project. 100% target |
|  |  | EMS (6 Projects) | R23.m | Site Handover | monitoring and supervision. 50% progress target. | Continuation of monitoring and supervision. 70% progress target. | Final inspection, release retention and close the project. 100% target |
|  |  | Forensic Pathological Services (1) | R4.9m | Under planning | Site Handover | Continuation of monitoring and supervision. 50% progress target. | Continuation of monitoring and supervision. 70% rogress target. |
|  |  | Clinic Electrification (59) | R10m | Site Handover | monitoring and supervision. 50% progress target. | Final inspection, release retention and close the project. 100% targe |  |
|  |  | Philadelphia-Groblersdaal Hospital | R6.9m | Site Handover | monitoring and supervision. 50% progress target. | Final inspection, release retention and close the project. 100% targe |  |
|  |  | Social Development One Stop Centres (15) | R30m | Monitoring and supervision. 90% progress target. | Final inspection, release retention and close the project. 100% target |  |  |
|  |  | Extention of Polokwane of Place of safety | R6.5m | Site Handover 50% progress target | monitoring and supervision. 75% progress target. | Final inspection, release retention and close the project. 100% target |  |
|  |  | Community Based Rehabilitation Centres (3) | R5.7m | Site Handover 50% progress target | monitoring and supervision. 75% progress target. | Final inspection, release retention and close the project. 100% target |  |
|  |  | Drop in Centres(10) | R4m | Site Handover 25% progress target. | monitoring and supervision. 75% progress target. | Final inspection, release retention and close the project. 100% target |  |
|  |  | Victim Empowerment Centre(5) | R3m | Site Handover 70% progress target. | Final inspection, close the project. 100% target. | Final inspection, release retention and close the project. 100% target. |  |
|  |  | Staff Accommodation (2X2 Flats) | R5m | Site Handover 55% progress target. | Final inspection, close the project. 100% target. | Final inspection, release retention and close the project. 100% target. |  |
|  |  | Transport Projects |  |  |  |  |  |
|  |  | -Construction of six (4 at Masia and 2 at Makuleke ) houses | R1.5m | Monitoring and supervision and 100% progress targeted. | - Final inspection, release retention and close the project. 100% target |  |  |
|  |  | Convention of Warehouse to Offices | R5.8m | Continuation of monitoring and supervision and 100 % progress targeted. | - Final inspection, release retention and close the project. 100% target |  |  |
|  |  | Agriculture Projects - Vet Clinics - Processing Plants | R4m | - Final inspection, release retention and close the project. 100% target |  |  |  |
|  |  | - - Tompi Seleka College | R 1m | - Continuation of monitoring and supervision. 60% progress target. | Monitoring and supervision and 80% progress targeted. | Monitoring and supervision and 100% progress targeted. | - Final inspection, release retention and close the project. 100% target |
|  |  | Environmental Affairs Projects | R 14.5 m | - - Final inspection, release retention and close the project. 100% target |  |  |  |
|  |  | Dept. Of Economic Development |  |  |  |  |  |
|  |  | Marketing Stalls at Mogalakwena and | R2.4 | Continuation of monitoring and supervision and 100% progress targeted. commissioning | - Final inspection, release retention and close the project. 100% target |  |  |
|  |  | Office of the Premier |  |  |  |  |  |
|  |  | Offices of Traditional Leaders | R9.4m | Continuation of monitoring and supervision and 60% progress targeted. commissioning | Continuation of monitoring and supervision and 100% progress targeted. commissioning | - Final inspection, release retention and close the project. 100% target |  |
|  |  | Modimolle Municipality | R 51m | Continuation of monitoring and supervision and 100% progress targeted. commissioning | - Final inspection, release retention and close the project. 100% target |  |  |
|  |  | -Installation of A/C and fire fighting equipment. -Installation of standby- generators. | R 5 m | monitoring and supervision and 90% progress targeted. Commissioning of new projects | monitoring and supervision and 100% progress targeted. Commissioning of new projects . | - Final inspection, release retention and close the project. 100% target | Continuation of monitoring and supervision and 100% progress targeted. Commissioning of new projects |
|  |  | - Provision of boreholes at road camps and cost centers | R 10 m | Continuation of monitoring and supervision and 100% progress targeted. - Commissioning | - Final inspection, release retention and close the project. 100% target |  |  |
|  |  | Roof and structural repairs to offices and government complexes. | R 5 m | Continuation of monitoring and supervision and 100% progress targeted. | - Commissioning |  |  |
|  |  | EPWP-school, Giyani Multi Purpose Education Centre | - R 5 m | Commissioning |  |  |  |
|  |  | Installation and upgrading of lifts in Thohoyandou and Giyani Gov. Complex. | - R8m | - Supervision & monitoring and 100% targeted progress | Commissioning |  |  |
|  |  | Electrical Upgrade at Thohoyandou and Giyani Gov. Complex | - R6.3m | - Supervision & monitoring and 100% targeted progress | Commissioning |  |  |
|  |  | Construction of Offices at Thulamahashe Gov. Complex | - R2.4m | Supervision & monitoring and 100% targeted progress. | Commissioning |  |  |
|  |  | Installation of Supplementary Water Supply | - R3.6m | Supervision & monitoring and 100% targeted progress. | Commissioning |  |  |

EXECUTIVE PROGRAMME: BUILDINGS AND MAINTENANCE

| Sub Program: Buildings and Maintenance | Strategic Goal: Efficient and effective maintenance of government buildings and grounds. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable objectives | Performance measure Indicator | 2007/08 Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Maintenance of government buildings for safe and reliable use in accordance with norms and standards. | Infrastructure maintenance plan in place and fully implemented | Maintenance of 203 residential houses in all districts completed. | Current : | Implement maintenance on 30 %( 66) of the 203 residential houses. | Implement 50% (111) of maintenance work required on the 203 houses. | Implement 80%(178) of maintenance on 203 residential houses | Implement 100% (223) of maintenance on all 203 residential houses |
|  |  | Renovation and upgrading of 17 government offices in all districts in line with the audit report completed. | R6,7Million | Implement 30% of maintenance on 17 government offices. | Implement 60% of maintenance on the 17 government offices. | Implement 90% of maintenance on the 17 government offices | Implement 100% of maintenance on the 17 government offices |
|  |  | Renovation and upgrading of 4 government complexes at Giyani, Thohoyandou, Makwarela and Sekhukhune completed by end of financial year | R 53Million | Evaluation of bids and handover of project sites to contractors | Monitoring and supervision of progress and attainment of 40% of planned work | Monitoring and supervision of progress and attainment of 80% of planned work | Monitoring and supervision of progress and attainment of 100% of planned work |
|  |  | Well maintained gardens, landscapes and grounds. | Current Expenditure | Implementation of gardens, landscapes and grounds in line with the maintenance program. | Implementation of gardens, landscapes and grounds in line with the maintenance program. | Implementation of gardens, landscapes and grounds in line with the maintenance program. | Implementation of gardens, landscapes and grounds in line with the maintenance program. |
|  |  | Development of 49 545 square meters of landscaping. | R 5,400,000 | Evaluation of bids and handover of project sites to contractors | Monitoring and supervision of progress and attainment of 40% of planned work | Monitoring and supervision of progress and attainment of 80% of planned work | Monitoring and supervision of progress and attainment of 100% of planned work |
|  |  | Construction of 134 staff houses at roads camps | R 6.700,000 | Implement 30% of the projects | Implement 50% of the projects. | Implement 70% of the projects | Implement 100% of projects |

EXECUTIVE PROGRAMME: REAL ESTATE

| Sub Programme: Real Estate |  | Strategic Goal: Sustainable provincial building infra-structure to support service delivery. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives | Measurable Objectives | Performance Measure Indicator |  | 2007/08 Budget |  | Quarter 1 |  | Quarter 2 | Quarter 3 | Quarter 4 |
| Efficient management of immovable property utilized for government service delivery | Disposal of redundant properties | Number of properties disposed |  | R200 000 |  | 10 properties disposed |  | 20 properties disposed | 20 properties disposed | 10 properties disposed |
|  | Transfer of towns to municipalities | Number of R293 towns transferred to Municipalities |  | R80 000 |  | 30 R293 Towns transferred towns |  | 30 R293 Towns transferred | 6 R293 Towns transferred | - |
|  | Ownership of provincial properties | Number of provincial properties vested |  | R 20 000 |  | 5 Properties vested |  | 10 Properties vested | 10 Properties vested | 5 Properties vested |
|  | Management of provincial office and residential accomodation | Develop user immovable Assets Management Plan |  | R8000 000 |  | Develop an immovable Assets Management Plan for districts 30% of project done |  | Develop an immovable Assets Management Plan for districts 50% of project completed | Develop an immovable Assets Management Plan for districts 75% of project completed | Finalisean immovable Assets Management Plan for districts 100% of project completed |
|  |  | 90% reduction in arrear rentals |  |  |  | 15 % reduction in arrear rentals |  | 30% reduction in arrear rentals | 85% reduction in arrear rentals | 95% reduction in arrear rentals |
|  | Comprehensive reliable Provincial Asset Register | Updated assets register of all government owned immovable assets |  | R9000 000 |  | 25% updated |  | 50% updated | 75% updated | 100% completed |
|  | Acquisition of land for Socio-economic develoment | Acquisition of Gateway Airport |  |  | Phase 4 and 5acquired |  | Facilitate the acquisition of land for phase 4 and 5 |  | Registration of land for phase 4 and 5 | Registration of land for phase 4 and 5 |

EXECUTIVE PROGRAMME: EXPANDED PUBLIC WORKS PROGRAMME

| Reduction of Unemployment | Job creation | Number jobs created. | R4M | - | 65 | 65 | 65 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Number of Women |  |  | 26 | 26 | 26 |
|  |  | Number of Youth |  |  | 20 | 20 | 20 |
|  |  | Number of disabled persons |  |  | 2 | 2 | 2 |
|  | Poverty alleviation | Number of beneficiaries |  | 195 | 65 | 65 | 65 |
|  | Skills development | Number of People trained in soft skills | R126 750 | 195 |  |  |  |
|  |  | Number of Women trained |  |  | 26 | 26 | 26 |
|  |  | Number of Youth trained. |  |  | 20 | 20 | 20 |
|  |  | Number of Disabled trained. |  |  | 2 | 2 | 2 |
|  |  | P&G | R1,39M |  |  |  |  |
|  |  | Number of emerging and LIC contractors trained. | R4,5M | 40 | 40 | 40 | 40 |

1.2.  OTHER PROVINCIAL DEPARTMENTS: (PROVINCIAL INFRASTRUCTURE GRANTS)

| Reduction of Unemployment | Job creation | Number jobs created. | R505.3M | 6 250 | 6 250 | 6 250 | 6 250 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Number of Women |  | 2 500 | 2 500 | 2 500 | 2 500 |
|  |  | Number of Youth |  | 1 875 | 1 875 | 1 875 | 1 875 |
|  |  | Number of disabled persons |  | 500 | 500 | 500 | 500 |
|  | Poverty alleviation | Number of beneficiaries | 25 000 |  |  |  |  |
|  | Skills development | Number of People trained in soft skills | R16.25M | 6 250 | 6 250 | 6 250 | 6 250 |
|  |  | Number of Women trained |  | 2 500 | 2 500 | 2 500 | 2 500 |
|  |  | Number of Youth trained. |  | 1 875 | 1 875 | 1 875 | 1 875 |
|  |  | Number of Disabled trained. |  | 500 | 500 | 500 | 500 |
|  |  | P&G | R10M |  |  |  |  |
|  |  | Number of emerging and LIC contractors trained. | R1,7M | 15 | - | 15 | 30 |

1.3.  MUNICIPALITIES: (MUNICIPAL INFRASTRUCTURE GRANTS)

| Reduction of Unemployment | Job creation | Number jobs created. |  | - | 6 500 | 6 500 | 6 500 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Number of Women |  | - | 2 600 | 2 600 | 2 600 |
|  |  | Number of Youth |  | - | 1 950 | 1 950 | 1 950 |
|  |  | Number of disabled persons |  | - | 130 | 130 | 130 |
|  | Poverty alleviation | Number of beneficiaries | 19 500 |  |  |  |  |
|  | Skills development | Number of People trained in soft skills |  | - | 6 500 | 6 500 | 6 500 |
|  |  | Number of Women trained |  | - | 2 600 | 2 600 | 2 600 |
|  |  | Number of Youth trained. |  |  | 1 950 | 1 950 | 1 950 |
|  |  | Number of Disabled trained. |  |  | 130 | 130 | 130 |
|  |  | P&G | R14M |  |  |  |  |
|  |  | Number of emerging and LIC contractors trained. | R8,5M | - | - | - | 75 |

1.4.  OTHER PROVINCIAL DEPARTMENTS: SOCIAL, (PROVINCIAL EQUITABLE SHARE)

| Reduction of Unemployment | Job creation: HCBC ECD NYS | Number jobs created. | R226,046M | 7 235 |  |  | 7 235 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Number of Women |  |  |  |  | 5 788 |
|  |  | Number of Youth |  |  |  |  | 3 618 |
|  |  | Number of disabled persons |  |  |  |  | 36 |
|  | Poverty alleviation | Number of beneficiaries |  | 7 235 |  |  |  |
|  | Skills development | Number of People trained in soft skills |  | 7 235 |  |  |  |
|  |  | Number of Women trained |  | 5 788 |  |  |  |
|  |  | Number of Youth trained. |  | 3 618 |  |  |  |
|  |  | Number of Disabled trained. |  | 36 |  |  |  |
|  |  | P&G |  |  |  |  |  |
|  |  | Number of Practitioners |  |  |  |  |  |
|  |  | TOTAL | R226,046M |  |  |  |  |

1.5.  OTHER PROVINCIAL DEPARTMENTS: ECONOMIC, (PROVINCIAL EQUITABLE SHARE)

| Reduction of Unemployment | Job creation: Corporative Sakhasonke | Number jobs created. |  | 6 815 |  |  | 6815 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Number of Women |  | 40% |  |  |  |
|  |  | Number of Youth |  | 30% |  |  |  |
|  |  | Number of disabled persons |  | 2% |  |  |  |
|  | Poverty alleviation | Number of beneficiaries |  | 6 815 |  |  | 6 815 |
|  | Skills development | Number of People trained in soft skills |  | 6 815 |  |  | 6 815 |
|  |  | Number of Women trained |  | 40% |  |  |  |
|  |  | Number of Youth trained. |  | 30% |  |  |  |
|  |  | Number of Disabled trained. |  | 2% |  |  |  |
|  |  | P&G |  |  |  |  |  |
|  |  | Number of Corporative |  | 195 |  |  | 195 |
|  |  | Number of Sakhasonke Contractors |  | 80 |  |  | 80 |

1.6.  OTHER PROVINCIAL DEPARTMENTS: ENVIRONMENT, (PROVINCIAL EQUITABLE SHARE)

| Reduction of Unemployment | Job creation: -Working for Tourism -Environment management; -Working on waste | Number jobs created. | R30m | 2 385 | 2 385 | 2 385 | 2 385 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Number of Women |  | 954 | 954 | 954 | 954 |
|  |  | Number of Youth |  | 716 | 716 | 716 | 716 |
|  |  | Number of disabled persons |  | 48 | 48 | 48 | 48 |
|  | Poverty alleviation | Number of beneficiaries |  | 9 540 |  |  |  |
|  | Skills development | Number of People trained in soft skills |  |  |  |  |  |
|  |  | Number of Women trained |  | 954 | 954 | 954 | 954 |
|  |  | Number of Youth trained. |  | 716 | 716 | 716 | 716 |
|  |  | Number of Disabled trained. |  | 48 | 48 | 48 | 48 |
|  |  | P&G |  |  |  |  |  |
|  |  |  | R335,528 | 26 |  |  | 26 |
|  |  | Number of Cultural projects | - | Lobby the Department of Sports – Arts and Culture |  |  |  |
|  |  | Environmental projects | R20m | Lobby with implementing local municipalities to identify and implement projects |  |  |  |
|  |  | TOTAL | R50.335M |  |  |  |  |

1.7.  NATIONAL DEPARTMENTS: (DIVISION OF REVENUE ACT

| Reduction of Unemployment | Job creation: -Department of Environment & Toursim -Department of Water Affairs -Public Works -South African Defence Force -National Justice | Number jobs created. |  | 1,578 |  |  | 1,578 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Number of Women |  |  |  |  |  |
|  |  | Number of Youth |  |  |  |  |  |
|  |  | Number of disabled persons |  |  |  |  |  |
|  | Poverty alleviation | Number of beneficiaries |  | 1,578 |  |  | 1,578 |

2. REALIZATION OF SHARED GOALS

| Realize shared goals for government and society | Coordinate intesector/departmental committees | Implement a coordinated EPWP | R21m | Submit first progress review | Submit second progress review | Submit third progress review | Evaluate and Plan for the next financial year |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Do baseline audit | R614 000 | Appoint service provider | Conduct audit | Evaluate | Plan for the next financial year. |
|  |  | Do an overall mid-term review with all stakeholders |  | implement outcomes | implement outcomes | implement outcomes | implement outcomes |
|  |  | Number of sectoral meetings |  | 12 Sectors meetings; One PSC meeting 8 Technical coordination meetings | 12 Sectors meetings; One PSC meeting 8 Technical coordination meetings | 12 Sectors meetings; One PSC meeting 8 Technical coordination meetings | 12 Sectors meetings; One PSC meeting 8 Technical coordination meetings |
|  |  | Number of emerging projects planned and implemented. |  | Assist in reviewing and realigning twenty (20) projects | Assist in reviewing and realigning twenty (20) projects | Assist in reviewing and realigning twenty (20) projects | Assist in reviewing and realigning twenty (20) projects |
|  |  | Number of sectoral plans |  | 4 Operational Sector plans | 4 Operational Sector plans | 4 Operational Sector plans | 4 Operational Sector plans |
|  |  | Number of Large EPWP Projects |  | Lobby implementing bodies | Lobby implementing bodies | Lobby implementing bodies | Lobby implementing bodies |
|  |  | Number of Facilities for social sector programmes |  | Allocation or donation of facilities for HCBC and ECD sites | Allocation or donation of facilities for HCBC and ECD sites | Allocation or donation of facilities for HCBC and ECD sites | Allocation or donation of facilities for HCBC and ECD sites |
| Implement an EPWP SDIP | Evidence based decision support | Number of interventions |  | Two workshops and one roadshow | Two workshops and one roadshow | Two workshops and one roadshow | Two workshops and one roadshow |

3.  MONITORING AND EVALUATION

| Monitoring and Evaluation | Set Monitoring and Evaluation norms and standards | Sectoral norms and standards |  | Develop One norms and standards | Develop One norms and standards | Develop One norms and standards | Develop One norms and standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Measured outputs | Number of jobs, |  | 12,000 | 13,000 | 15,000 | 17,421 |
|  |  | number of workers, |  | 12,000 | 13,000 | 15,000 | 17,421 |
|  |  | numbers of training interventions |  | 2 reorientation training workshop | 2 reorientation training workshop | 2 reorientation training workshop | 2 reorientation training workshop |
|  |  | amount of infrastructure developed. |  | 20 infrastructure developed | 20 infrastructure developed | 20 infrastructure developed | 20 infrastructure developed |
|  | Sectoral outputs | Infrastructure |  | Jobs = 6,930 Learnership = 48 Workers training = 6,930 | Jobs = 6,930 Learnership = 48 Workers training = 6,930 | Jobs = 6,930 Learnership = 48 Workers training = 6,930 | Jobs = 6,930 Learnership = 48 Workers training = 6,930 |
|  |  | Economic |  | Jobs:1, 700 Learnership:533 Workers training: 1700 | Jobs:1, 700 Learnership:533 Workers training: 1700 | Jobs:1, 700 Learnership:533 Workers training: 1700 | Jobs:1, 700 Learnership:533 Workers training: 1700 |
|  |  | Social |  | Jobs: 1,810 Learnership: 1,810 | Jobs: 1,810 Learnership: 1,810 | Jobs: 1,810 Learnership: 1,810 | Jobs: 1,810 Learnership: 1,810 |
|  |  | Environmental |  | Jobs: 3, 910 Learnership: 25 Workers training:3,910 | Jobs: 3, 910 Learnership: 25 Workers training:3,910 | Jobs: 3, 910 Learnership: 25 Workers training:3,910 | Jobs: 3, 910 Learnership: 25 Workers training:3,910 |
|  | Measured outcomes | Number of |  | 72,000 | 76,000 | 83,000 | 89,265 |

PART C: BUDGET

2007 – 08 BUDGET ESTIMATES

| PROGRAM | NAME | ALLOCATION |
| --- | --- | --- |
|  |  | R'000 |
| PROGRAM 1 | ADMINISTRATION | 218,438 |
|  | SP: STATUTORY PAYMENTS | 714 |
|  | SP: MANAGEMENT | 15,201 |
|  | SP: CORPORATE SERVICES | 92,374 |
|  | SP: STRATEGIC FINANCE | 43,316 |
|  | SP: STRATEGIC HUMAN RESOURCE | 37,527 |
|  | SP: GITS | 29,306 |
| PROGRAM 2 | PUBLIC WORKS | 368,007 |
|  | SP: PROJECT MANAGEMENT | 20,928 |
|  | SP: PROFESSIONAL SERVICES | 1,126 |
|  | SP: BUILDINGS & MAINTENANCE | 304,071 |
|  | SP: REAL ESTATE MANAGEMENT | 39,119 |
|  | SP: SUPPORT SERVICES | 2,763 |
| PROGRAM 3 | EXPANDED PUBLIC WORKS PROGRAM (EPWP) | 15,153 |
| TOTAL |  | 601,598 |
| DEPARTMENTAL SUMMARY | ECONOMIC CLASSIFICATION | R'000 |
|  | COMPENSATION OF EMPLOYEES | 367,503 |
|  | GOODS & SERVICES | 130,066 |
|  | INTEREST & RENT ON LAND | 15 |
|  | PROVINCIAL & LOCAL GOVT | 3,600 |
|  | HOUSEHOLDS | 3,000 |
|  | BUILDINGS & OTHER FIX STRUCT | 80,814 |
|  | MACHINERY & EQUIPMENT | 16,600 |
| TOTAL |  | 601,598 |